DAIRY DEVELOPMENT CORPORATION

(AN UNDERTAKING OF GOVT. OF NEPAL)

BIDDING DOCUMENT

For

- eXPANSION OF SKIMMED MILK POWDER PLANT

- ADDITION FOR PRODUCTION OF  DAIRY WHITENER

- modification of husk fired boiler

International Competitive Bidding (ICB)

(Single Stage Bidding)

Tender NOTICE NO.: DDC/ICB/06/EXP/072/073
ISSUED ON: 11 February 2016

Employer: Dairy Development Corporation

City : Kathmandu

Country: Nepal

Table of Contents

Invitation of bids

PART I	BIDDING PROCEDURES

Section 1 -	Instructions to Bidders (ITB)	1

Section 2 -	Bid Data Sheet (BDS) 	18

Section 3 -	Evaluation and Qualification Criteria (EQC) 	24

Section 4 -	Bidding Forms (BDF) 	  28

PART II  	Supply REQUIREMENTS

Section 5 -	Schedule of Requirements……………………………...55

PART III	CONDITIONS OF CONTRACT AND CONTRACT FORMS

Section 6 -	General Conditions of Contract (GCC) 	109

Section 7 -	Special Conditions of Contract (SCC) 	122

Section 8 -	Contract of Forms (COF)	176

Dairy Development Corporation (DDC)

Central Office Lainchaur, Kathmandu, Nepal

( AN Undertaking OF GOVerment Of Nepal )

Invitation For Bid (IFB)

( First date of publication: 11 February 2016 )

| Bid Reference | Name of Project |  | Description | Source of Funds |
| --- | --- | --- | --- | --- |
| DDC/ICB/06/EXP /072/73 | Expansion of Powder Plant |  | Design, Supply, Erection, Testing & Commissioning for Expansion and Revamping of Powder Plant Machineries on turnkey basis including production of dairy whitener machineries and modification of Husk Boiler in Biratnagar Milk Supply Scheme,Kanchanbari,Biratnagar, Nepal. | Equity Financing Govt. of Nepal |
| Earnest Money Deposit (EMD) / Bid Bond |  |  | In NRs. 2,700,000.00 (Rupees Two Million Seven Hundred Thousand Only) or equivalent in any convertible currency, which shall be valid for minimum 30 days beyond the bid validity period. |  |
| Duration of Job Completion |  |  | Earliest Completion : 8 Months Latest Completion : 10 Months |  |
| Bidding Document Sale |  | Start | From the First Publication Date : 11 February 2016 |  |
|  |  | Stop | 10 April 2016 at office hours |  |
| Last Date, Time & Place of Bid |  | Submission | at 12.00 hours on 11 April 2016 |  |
|  |  | Tender Opening | at 13.00 hours on 11 April 2016 |  |
|  |  | Place | At the office of Dairy Development Corporation, Central Office, Lainchaur, Kathmandu, Nepal |  |
| Date of Pre-Bid Meeting |  |  | At the office of Dairy Development Corporation, Central Office, Lainchaur, Kathmandu, Nepal at 13.00 hour on 21st March 2016. |  |

1. Eligibility Criteria

1.1 	The Bidder/Supplier must have executed, in the last five years at least two contract of upgrading/establishment of  SMP Plant with Reverse Osmosis  and  dairy whitener of value not less than  80% of the estimated cost of the job. The bidder should have design back up of such plants to carry out the job.

2. Purchase of Bidding Document

  - The bid document may be purchased from  the office of DDC, Central Office,Lainchaur, Kathmandu Milk Supply Scheme, Balaju, Kathmandu and Biratnagar Milk Supply Scheme, Biratnagar, Nepal by interested bidders on submission of a written application and upon payment of a non-refundable fee of Nepalese Rupees 5,000/- or equivalent in any convertible currency in cash or in form of bank receipt for fee deposited in DDC revenue Current Account No. 109005534501,Rastriya Banijya Bank, Bishal Bazar, Kathmandu or NRs. or equivalent in any convertible currency in the form of bank draft in favor of the Dairy Development Corporation, Kathmandu, Nepal during office hours on working days of Sunday to Friday (except public holiday). Incase the Bidder choose to download and submit bid electronically, the Bidders shall be required to deposit the non refundable fee for bidding document in the above bank account of DDC and electronic scanned copy(*.pdf format) of the bank deposit voucher shall also be submitted along with the electronic bid files.

  - Bidders, who wish to receive the bidding document by post/courier, may send a request to the Employer with a payment of additional fee of NRs.10,000.00 or equivalent in any convertible currency in a form of bank draft in favor of DDC. If so requested, DDC will send the document to the address requested by them. However, the Employer will not be responsible for delayed or non delivery of the documents so sent.

3. Submission of Bid

3.1 	The bidder who purchase the bidding document, are eligible for submission of bids in their name only.

3.2 	Bidders who choose to submit their bid electronically through website: www.gepson.gov.np, the bidder either may purchase the hardcopy of bidding documents from the above office or may choose to download the necessary parts of the bidding documents, prepare their bid and submit their electronic bids as specified in the instruction to bidders.

3.3 	Bidders, who choose to submit their bid electronically shall be required to submit original documents within 15 (Fifteen) days from bid opening. Non-submission of original documents by the bidder within that time causes forfeiture of bid security.

3.4 	If the last date of purchasing, submission and opening falls on a government holiday then the next working day shall be considered the last day. In such a case the bid validity and bid security validity shall be recognized with effect from the original bid submission deadline.

4. Bid Security

4.1 	All bids must be accompanied by bid security (Earnest Money Deposit – EMD) in the form specified in the bidding document. The bids not accompanied with EMD shall be summarily rejected. The bid security should be in Nepalese Currency or Equivalent in any convertible currency and shall be in the form of Bank Guarantee from the “A” Class Commercial Bank or Demand draft in favor of DDC, Kathmandu, payable at Kathmandu with counter signed from Nepalese "A" class Bank. The Bid security may be forfeited if a bidder or supplier withdraws its bid during the period of bid validity specified by the bidder/ supplier on the bid form or In case of successful bidder/ supplier, if the bidder/ supplier fail to sign the contract.

5. Rights Reserved by DDC NEPAL

5.1 	DDC reserves the right to accept and / or reject the bids received in accordance with prevailing laws.

6. Validity: - The offer should be valid for 120 days from the date of tender opening.

Table of Contents

PART I: BIDDING PROCEDURES

Section 1 - Instructions to Bidders

A.	General	1-4

1.	Scope of Bid

2.	Source of Funds

3.	Fraud and Corruption

4.	Eligible Bidders

5.	Eligible Materials, Equipment and Services

B.	Contents of Bidding Document	4-5

6.	Sections of Bidding Document

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting

8.	Amendment of Bidding Document

C.	Preparation of Bids	5-10

9.	Cost of Bidding

10.	Language of Bid

11.	Documents Comprising the Bid

12.	Bid Submission Form

13.	Alternative Bids

14.	Price Adjustment.

15.	Bid Currency and Payment

16.	Documents Establishing The Eligibility of The Goods & Related Services.

17.	Documents Establishing The Conformity of The Goods & Related Services.

18.	Documents Establishing The Qualification of The Bidder

19	Bid Prices and discount

20.	Period of Validity of Bids

21.	Bid Security

22.	Format and Signing of Bid

D.	Submission and Opening of Bids	10-12

23.	Sealing and Marking of Bids

24.	Deadline for Submission of Bids

25.	Late Bids

26.	Withdrawal, and Modification of Bids

27.	Bid Opening

E.	Evaluation and Comparison of Bids	12-16

28.	Confidentiality

29.	Clarification of Bids

30.	Deviations, Reservations, and Omissions

31.	Determination of Responsiveness

32.	Nonconformities, Errors, and Omissions

33.	Correction of Arithmetical Errors

34.	Conversion to Single Currency….

35.	Domestice Preference

36.	Evaluation of Bids

37.	Comparison of Bids

38.	Post Qualification of the Bidder

39.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids

F.	Award of Contract	16-17

40.	Award Criteria

41.	Letter of Intent to Award the Contract/ Notification of Award

42.	Performance Security

43.	Signing of Contract

44.	Complain and Review

Section 2 – Bidding Data Sheet………………………………..…18-23

45.	Special Instruction to Bidders for E-Bidding

PART I: BIDDING PROCEDURES

Section 1 - Instructions to Bidders

| - General |  |  |
| --- | --- | --- |
| - Scope of Bid | 1.1 The Contractor is responsible for the supply, modification / renovation / supply of equipment/revamping of existing evaporator and drying plant, rectification, installation, testing, commissioning & start –up for expansion of Powder Plant from 3 MTPD to 6 MTPD, production of dairy whitener with machineries and modification of husk fired boiler from 10 kg/cm2 to 13 kg/cm2 on turnkey basis at Biratnagar Milk Supply Scheme, Kanchanbari, Biratnagar, Nepal. Also, the Contractor will be full responsible for proper design, manufacturing, supply, transportation and testing of the SMP Plant, dairy whitener machineries & Husk boiler (Modification) to be supplied. The supply shall conform to the technical Specifications described under “Specification” include all possible modification works on existing SMP plant & husk boiler plant. The Contractor will be allowed to use, under his full responsibility and the conditions specified by the Employer, the lifting equipment available in the plants. Possible damages caused by the Contractor during the utilization of such equipment and, in general, damages caused by him during site works shall be covered by an insurance, which cost shall be included in the contract price, remaining at the Contractor charge the repair of the damages caused to the equipment. The job shall include transportation, supply and installation of all services & product piping including ancillary items, interconnections of services & electrical with equipments. The name, identification and number of contracts of the International Competitive Bidding (ICB) are in the BDS. . |  |
| - Source of Funds | - In accordance with DDC Equity financing from the GoN annual program and budget, approved by the Board of Director and Budget allocated from the Ministry of Agriculture Development, the implementing agency indicated in the BDS plans to apply a portion of the allocated budget to eligible payments under the contract(s) for which this Bidding Document is issued. |  |
| - Fraud and Corruption | - The Government of Nepal (GoN) requires that the procuring entities as well as bidders, suppliers, and contractors and their sub-contractors under GoN-financed contracts, shall adhere to the highest standard of ethics during the procurement and execution of such contracts. In this context, the Employer; - defines, for the purposes of this provision, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; - “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; - “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; - “Collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party. - “obstructive practice” means: - deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a GoN investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or - Acts intended to materially impede the exercise of the GoN’s inspection and audit rights provided for under sub-clause 3.5 below. (b) will reject bid(s) if it determines that the bidder has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question; (c) will sanction a firm or individual, including declaring ineligible, for a stated period of time, to be awarded a GoN-financed contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for, or in executing, a GoN -financed contract. - The Bidder shall not carry out or cause to carryout the following acts with an intention to influence the implementation of the procurement process or the procurement agreement : - give or propose improper inducement directly or indirectly, - distortion or misrepresentation of facts, - engaging in corrupt or fraudulent practice or involving in such act, - interference in participation of other competing bidders, - coercion or threatening directly or indirectly to cause harm to the person or the property of any person to be involved in the procurement proceedings, - collusive practice among bidders before or after submission of bids for distribution of works among bidders or fixing artificial/uncompetitive bid price with an intention to deprive the Employer the benefit of open competitive bid price, - contacting the Employer with an intention to influence the Employer with regards to the bids or interference of any kind in examination and evaluation of the bids during the period from the time of opening of the bids until the notification of award of contract. - PPMO on the recommendation of the Employer may blacklist a Bidder for a period of one (1) to three (3) years for its conduct including the following grounds and seriousness of the act committed by the bidder: - if convicted by a court of law in a criminal offence which disqualifies the Bidder from participating in the contract, - if it is established that the contract agreement signed by the Bidder was based on false or misrepresentation of Bidder’s qualification information, - A bidder declared blacklisted and ineligible by the GoN, Public procurement Monitoring Office (PPMO) and/or the DP in case of DP funded project, shall be ineligible to bid for a contract during the period of time determined by the GoN, PPMO. - The Contractor shall permit the DDC’s Board to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by auditors appointed by the DDC’s Board, if so required by the DDC’s Board. |  |
| - Eligible Bidders | - A Bidder may be a natural person, private entity, or government-owned entity—subject to ITB 4.5—or any combination of them in the form of a Joint Venture (JV) under an existing agreement, or with the intent to constitute a legally-enforceable joint venture. In the case of a JV: - all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. The qualification requirement of the parties to the JV shall be as specified in the BDS, and - the JV shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the bidding process and, in the event the JV is awarded the Contract, during Contract execution. - A Bidder, and all parties constituting the Bidder, shall have the nationality of Nepal or any country or eligible countries mentioned in the BDS. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, or incorporated, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed sub Contractors or suppliers for any part of the Contract including related services. - A Bidder shall not have a conflict of interest. A Bidder found to have a conflict of interest shall be disqualified. A Bidder may be considered to be in a conflict of interest with one or more parties in this bidding process, if: - they have controlling partners in common; or - they receive or have received any direct or indirect subsidy from any of them; or - they have the same legal representative for purposes of this bid; or - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about or influence on the Bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or - a Bidder participates in more than one bid in this bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which the party is involved. However, this does not limit the inclusion of the same sub Contractor in more than one bid; or - a Bidder or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the Contract that is the subject of the Bid; or - a Bidder or any of its affiliates has been hired (or is proposed to be hired) by the Employer as Engineer for the Contract. - A firm that is under a declaration of ineligibility by the GoN/DP in accordance with ITB 3, at the date of the deadline for bid submission or thereafter, shall be disqualified. The list of debarred firm is available at the electronic address specified in the BDS. - Enterprises owned by GoN shall be eligible only if they can establish that they are legally and financially autonomous and operate under commercial law, and that they are not a dependent agency of the GoN. - Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. - In case a prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. - Firms shall be excluded in any of the cases, if - by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Employer’s country prohibits any import of goods or Contracting of works or services from that country or any payments to persons or entities in that country. - Domestic Bidder shall be eligible only if the bidder has obtained Permanent Account Number (PAN) and Value Added Tax (VAT) Registration Certificate(s) and Tax Clearance Certificate or proof of submission of income return as stated in BDS from the Inland Revenue Office. Foreign bidder shall be eligible only if the bidder submits the documents indicated in the BDS at the time of bid submission and a declaration to submit the document(s) indicated in the BDS at the time of contract agreement. |  |
| - Eligible Materials, Equipment and Services | - The materials, equipment and services to be supplied under the Contract shall have their origin in any source countries as defined in ITB 5.2 above and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, Bidders shall provide evidence of the origin of materials, equipment and services. - For purposes of ITB 5.1 above, “origin” means the place where the materials and equipment are mined, grown, produced or manufactured, and from which the services are provided. Certified materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that differs substantially in its basic characteristics or in purpose or utility from its components. |  |
| - Contents of Bidding Document |  |  |
| - Sections of Bidding Document | - The Bidding Document consist of Parts I, II, and III, which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART I Bidding Procedures Section 1 - Instructions to Bidders (ITB) Section 2 - Bid Data Sheet (BDS) Section 3 - Evaluation and Qualification Criteria (EQC) Section 4 - Bidding Forms (BDF) PART II Employer's Requirements Section 5 – Employer's Requirements (ERQ) PART III Conditions of Contract and Contract Forms Section 6 - General Conditions of Contract (GCC) Section 7 - Special Conditions of Contract (SCC) Section 8 – Contract of Forms (CoF) - The Invitation for Bids issued by the Employer is not part of the Bidding Document. - The Employer is not responsible for the completeness of the Bidding Document and their Addenda, if they were not obtained directly from the source stated by the Employer in the Invitation for Bids. - The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the bid. |  |
| - Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | - A prospective Bidder requiring any clarification of the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise any question or curiosity during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer shall be required to make available as soon as possible the answer to such question or curiosity in writing to any request for clarification, provided that such request is received as mentioned in BDS. The Employer shall forward copies of its response to all Bidders who have acquired the Bidding Document in accordance directly from it, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 22.2. - The Bidder is encouraged to visit and examine the Site where the plant is to be modified/renovated/supply of equipment / revamping of existing evaporator and drying plant, addition of dairy whitener production, rectification, installation, testing & commissioning and modification of husk fired boiler and its surroundings and obtain for itself, on its own risk and responsibility, all information that may be necessary for preparing the bid and entering into a Contract for the provision of plant and installation services. The costs of visiting the Site shall be at the Bidder’s own expense. - The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. - The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. - The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer as mentioned in BDS. - Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. - Non attendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |  |
| - Amendment of Bidding Document | - At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Document by issuing addenda. - Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. - To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB 22.2 |  |
| - Preparation of Bids |  |  |
| - Cost of Bidding | - The Bidder shall bear all costs associated with the preparation and submission of its bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |  |
| - Language of Bid | - The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |  |
| - Documents Comprising the Bid | 11.1 The bid prepared by the Bidder/Supplier shall comprise the following Components: • A Bid Form and a Price Schedule completed in accordance with Clauses 12, 15 & 19. • Documentary evidence established in accordance with Clause 16 that the Bidder/Supplier is qualified to perform the contract if its bid is accepted. • Documentary evidence established in accordance with Clause 16 that the goods and ancillary services to be supplied by the Bidder/Supplier conform to the Bidding Document. • Bid security (Earnest Money Deposit) furnished in accordance with Clause 21 along with the bid security details form. |  |
| - Bid Submission Form | 12.1 The Bidder/Supplier shall complete the Bid Form and appropriate Price Schedule furnished in the Bidding Document, indicating for the goods to be supplied, a brief description of the goods, their country of origin, year of manufacture, quantity and prices. |  |
| - Alternative Bids | - Unless otherwise indicated in the BDS, alternative bids shall not be considered. - When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different times for completion. - When specified in the BDS pursuant to ITB 13.1, and subject to ITB 13.4 below, Bidders wishing to offer technical alternatives to the requirements of the Bidding Document must first price the Employer’s design as described in the Bidding Document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. - When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the Works. Such parts will be identified in the BDS and described in Section 5 (Employer’s Requirements). The method for their evaluation will be stipulated in Section 3 (Evaluation and Qualification Criteria). |  |
| - Price Adjustment | 14.1 Price quoted by the Bidder shall be subject to adjustment during the performance of the contract to reflect changes in the cost of labor and material components in accordance with the procedure specified in the special conditions of the contract. A bid submitted with a fixed price quotation will not be rejected but the price adjustment shall be treated as zero. |  |
| - Bid Currency and Payment 16. Documents Establishing the Eligibility of the Goods and Related Services 17. Documents Establishing the Conformity of the Goods and Related Services 18. Documents Establishing the Qualific ations of the Bidder | - Prices shall be quoted in Nepalese Rupees/ Indian Rupees / American Dollar /Euro or equivalent in any convertible currency for the goods and services, which the Bidder/Supplier will supply if a contract is awarded against this invitation for bid. For import, ceiling amount in respective currencies should be mentioned along with exchange rates considered. The price adjustment shall be allowed on account of any changes in the landed cost due to variation in the Exchange rates and / or Customs Duty (combined effect). For arriving at the variation in landed cost, the actual invoice value (from the foreign supplier) with bank certificate for Exchange Rates & bill of entry for Customs Duty paid has to be submitted as supporting documents. However, such changes shall be allowed only within the ceiling amount quoted and within the period of the contract. The variation will be worked out on the difference between Customs Duty rate / exchange rate mentioned in the Bid and the actual respective rates levied during the time of actual imports multiplied by the actual CIF value and not the ceiling value. All claims shall be against the supporting documents. - The currency (ies) of the bid shall be, as specified in the BDS. - Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements. 16.1 To establish the eligibility of the Goods and Related Services in accordance with ITB Clause 5, Bidders shall complete the country of origin declarations in the Price Schedule Forms, included in Section IV, Bidding Forms. 17.1 To establish the conformity of the Goods and Related Services to the Bidding Documents, the Bidder shall furnish as part of its Bid the documentary evidence that the Goods conform to the technical specifications and standards specified in Section VI, Schedule of Requirements. 17.2 The documentary evidence may be in the form of literature, drawings or data, and shall consist of a detailed item by item description of the essential technical and performance characteristics of the Goods and Related Services, demonstrating substantial responsiveness of the Goods and Related Services to the technical specification, and if applicable, a statement of deviations and exceptions to the provisions of the Schedule of Requirements. 17.3 The Bidder shall also furnish a list giving full particulars, including available sources and current prices of spare parts, special tools, etc., necessary for the proper and continuing functioning of the Goods during the period specified in the BDS following commencement of the use of the goods by the Purchaser. 17.4 Standards for workmanship, process, material, and equipment, as well as references to brand names or catalogue specified by the Purchaser in the Schedule of Requirements, are intended to be descriptive only and not restrictive. The Bidder may offer other standards of quality, brand names or catalogue, provided that it demonstrates, to the Purchaser’s satisfaction, that the substitutions ensure substantial equivalence or are superior to those specified in the Schedule of Requirements. 18.1 The documentary evidence of the Bidder’s qualifications to perform the contract if its bid is accepted shall establish the Purchaser’s satisfaction: (a) that, if required in the BDS, a Bidder that does not manufacture or produce the Goods it offers to supply shall submit the Manufacturer’s Authorization using the form included in Section IV, Bidding Forms to demonstrate that it has been duly authorized by the manufacturer or producer of the Goods to supply these Goods in the Purchaser’s Country; (b) that, if required in the BDS, in case of a Bidder not doing business within the Purchaser’s Country, the Bidder is or will be (if awarded the contract) represented by an Agent in the country equipped and able to carry out the Supplier’s maintenance, repair and spare parts-stocking obligations prescribed in the Conditions of Contract and/or Technical Specifications; and (c) That the Bidder meets each of the qualification criterions specified in Section III, Evaluation and Qualification Criteria. |  |
| 19. Bid Prices and Discounts | 19.1 Unless otherwise specified in the BDS, bidders shall quote for the entire Plant and Installation Services on a by filling in prices for entire expansion of Plant and installation services on a "single responsibility " basis that the total bid price covers all the contractor's obligations mentioned in or to be reasonably inferred from the bidding document in respect of the design, manufacture, including procurement and subcontracting ( if any ), delivery, installation, commissioning and trial basis of the SMP plant, addition of dairy whitener production and modification of husk boiler. This includes all requirements under the Contractor’s responsibilities for testing, pre-commissioning and commissioning of the plant and, where so required by the bidding document, the acquisition of all permits, approvals and licenses, etc.; the operation, maintenance and training services and such other items and services as may be specified in the Bidding Document, all in accordance with the requirements of the General Conditions. Items against which no price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed to be covered by the prices for other items. 19.2 Bidders are required to quote the price for the commercial, contractual and technical obligations outlined in the bidding document. 19.3 Bidders shall give a breakdown of the prices in the manner and detail called for in the Price Schedules included in Section 4, Bidding Forms. 19.4 Depending on the scope of the Contract, the Price Schedules may comprise up to the Plant and Installation Services of SMP Plant, dairy whitener and husk boiler. The total amount corresponding to an element of the Plant and Installation Services shall be summarized in the schedule titled Grand Summary, (Schedule 5), giving the total bid price(s) to be entered in the Letter of Bid. 19.5 In the Schedules, bidders shall give the required details and a breakdown of their prices as follows: (a) Plant to be supplied from abroad: The price of the plant shall be quoted on CIP-named place of destination basis as specified in the BDS (b) Plant manufactured within the Employer’s country(Schedule No.1& 2): N/A (i) The price of the plant shall be quoted on an EXW Inco term basis (such as “ex-works,” “ex-factory,” “ex-warehouse” or “off-the-shelf,” as applicable), (ii) Tariffs all other taxes payable in the Employer’s country on the plant if the contract is awarded to the Bidder, and (iii) The total price for the item. (c) Design Services (Schedule No. 3). (d) Installation Services shall be quoted separately (Schedule No. 4) and shall include rates or prices for local transportation to named place of final destination as specified in the BDS, insurance and other services incidental to delivery of the plant, all labor, contractor’s equipment, temporary works, materials, consumables and all matters and things of whatsoever nature, including operations and maintenance services, the provision of operations and maintenance manuals, training etc., where identified in the Bidding Document, as necessary for the proper execution of the installation and other services, including all taxes, duties, levies and charges payable in the Employer’s country as of twenty-eight (28) days prior to the deadline for submission of bids. 19.6 The current edition of Inco terms, published by the International Chamber of Commerce shall govern. 19.7 The prices shall be either fixed or adjustable as specified in the BDS:BDS(Fixed Price Contract ) 19.8 In the case of Fixed Price, prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A bid submitted with an adjustable price quotation will be treated as non responsive and rejected. 19.8 In the case of Adjustable Price, prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, transport and contractor’s equipment in accordance with the procedures specified in the corresponding Appendix to the Contract Agreement. A bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. Bidders are required to indicate the source of labor and material indices in the corresponding Form in Section 4, Bidding Forms. 19.9 If so indicated in ITB 1.1, bids are being invited for individual lots (contracts) or for any combination of lots (packages). Bidders wishing to offer any price reduction (discount) for the award of more than one Contract shall specify in their Letter of Bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package, and the manner in which the price reductions will apply. 19.10 Bidders wishing to offer any unconditional discount shall specify in their Letter of Bid the offered discounts and the manner in which price discounts will apply |  |
| - Period of Validity of Bids | - Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as non responsive. - In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 21, it shall also be extended 30 days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its Bid. |  |
| - Bid Security | - Unless otherwise specified in the BDS, the Bidder shall furnish as part of its bid, in original form, a bid security as specified in the BDS. In the case of a bid security, the amount shall be as specified in the BDS. - If a bid security is specified pursuant to ITB 21.1, the bid security shall be, at the Bidder’s option, in any of the following forms: - an unconditional bank guarantee; - Cash or certified cheque; - Bank draft All from a “A” class commercial Bank from Nepal. In the case of a bank guarantee, the bid security shall be submitted either using the Bid Security Form included in Section 4 (Bidding Forms) or in another substantially similar format approved by the employer prior to bid submission. The form must include the complete name of the Bidder. The bid security shall be valid for minimum thirty (30) days beyond the original validity period of the bid, or beyond any period of extension if requested under ITB 20.2. - The bid security issued by any foreign Bank outside Nepal must be counter guaranteed by an “A” class commercial Bank in Nepal. - Any bid not accompanied by an enforceable and substantially compliant bid security, if required in accordance with ITB 21.1, shall be rejected by the Employer as nonresponsive. - If a bid security is specified pursuant to ITB 21.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful bidder has furnished the required performance security and signed the Contract Agreement pursuant to ITB 42. - The bid security may be forfeited: - if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid, except as provided in ITB 20.2 or - if the successful Bidder fails to: #### Sign the Contract in accordance with ITB 41.1; or #### Furnish a performance security in accordance with ITB 43. #### Furnish a domestic preference security if so required. - The Bid Security of a JV shall be in the name of the JV that submits the bid. If the JV has not been legally constituted at the time of bidding, the Bid Security shall be in the names of all future partners as named in the letter of intent mentioned in ITB 4.1. |  |
| - Format and Signing of Bid | - The Bidder shall prepare one original of the documents comprising the bid as described in ITB 11 and clearly mark it “ORIGINAL”. Alternative bids, if permitted in accordance with ITB 13, shall be clearly marked “ALTERNATIVE”. In addition, the Bidder shall submit copies of the bid in the number specified in the BDS, and clearly mark each of them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. - The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the bid, except for un -amended printed literature, shall be signed or initialed by the person signing the bid. - A bid submitted by a JVA shall comply with the following requirements: (a) Unless not required in accordance with ITB 4.1 (a),be signed so as to be legally binding on all partners and (b) Include the Representative’s authorization referred to in ITB 4.1 (b), consisting of a power of attorney signed by those legally authorized to sign on behalf of the JVA. - Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the bid. |  |
| - Submission and Opening of Bids |  |  |
| - Sealing and Marking of Bids | - Bidders may always submit their bids by mail or by hand or by courier. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Procedures for submission, sealing and marking are as follows: - Bidders submitting bids by mail, by hand shall enclose the original and each copy of the Bid, including alternative bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “ORIGINAL”, “ALTERNATIVE” and “COPY.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. The rest of the procedure shall be in accordance with ITB sub-Clauses 23.2 and 23.3. - Bidders submitting bids electronically shall follow the electronic bid submission procedures specified in the BDS. - The inner and outer envelopes shall: - bear the name and address of the Bidder; - be addressed to the Employer as provided in BDS 24.1; - bear the specific identification of this bidding process indicated in BDS 1.1; and - Bear a warning not to open before the time and date for bid opening. - If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid. |  |
| - Deadline for Submission of Bids | - Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. - The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. - No telegraphic/fax bids shall be considered. However, any amendment sent by a telegram or fax to the bid already submitted / received shall be considered provided it is received before the date and time of opening of the bids & it is confirmed in writing by post. |  |
| - Late Bids | - The Employer shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB 24. Any bid received by the Employer after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the Bidder. |  |
| - Withdrawal, and Modification of Bids | - A Bidder may withdraw, or modify its bid after it has been submitted by sending a written notice in a sealed envelope, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 22.2, (except that withdrawal notices do not require copies). The corresponding modification of the bid must accompany the respective written notice. All notices must be: - prepared and submitted in accordance with ITB 22 and ITB 23 (except that withdrawal notices do not require copies), and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL”, “MODIFICATION;” and - Received by the Employer prior to the deadline prescribed for submission of bids, in accordance with ITB 24. - Bids requested to be withdrawn in accordance with ITB 26.1 shall be returned unopened to the Bidders. - No bid may be withdrawn, or modified in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |  |
| - Bid Opening | - The Employer shall open the bids in public at the address, date and time specified in the BDS in the presence of Bidders` designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1 shall be as specified in the BDS. - First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “MODIFICATION” shall be opened and read out with the corresponding bid. No bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at bid opening. Only envelopes that are opened and read out at bid opening shall be considered further. - All other envelopes shall be opened one at a time, reading out: the name of the Bidder; the Bid Price(s), including any discounts and alternative bids and indicating whether there is a modification; the presence or absence of a bid security or bid securing declaration and any other details as the Employer may consider appropriate. Only discounts and alternative offers read out at bid opening shall be considered for evaluation. No bid shall be rejected at bid opening except for late bids, in accordance with ITB 25.1. - The Employer shall prepare a record of the bid opening that shall include, as a minimum: the name of the Bidder and whether there is a withdrawal, substitution, or modification; the Bid Price, per Contract if applicable, including any discounts and alternative offers; and the presence or absence of a bid security, if one was required. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders who submitted bids in time, and posted online when electronic bidding is permitted. 25.5 Preliminary Examination 25.5.1 The Purchaser will examine the bids to determine: - Whether they are complete, - Whether any computational errors have been made, - Whether required sureties have been furnished, - Whether the documents have been properly signed and stamped, - Whether the bids are generally in order. |  |
| - Evaluation and Comparison of Bids |  |  |
| - Confidentiality | - Information relating to the evaluation, comparison, and post-qualification of bids and recommendation of Contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders. - Any attempt by a Bidder to influence the Employer in the evaluation of the bids or Contract award decisions may result in the rejection of its bid. - Notwithstanding ITB 28.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it may do so in writing. |  |
| - Clarification of Bids | - To assist in the examination, evaluation, and comparison of the bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the prices or substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the bids, in accordance with ITB 32. - If a Bidder does not provide clarifications of its bid by the date and time set in the Employer’s request for clarification, its bid may be rejected. |  |
| - Deviations, Reservations, and Omissions | - During the evaluation of bids, the following definitions apply: - “Deviation” is a departure from the requirements specified in the Bidding Document; - “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and - “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |  |
| - Determination of Responsiveness | - The Employer’s determination of a bid’s responsiveness is to be based on the contents of the bid itself, as defined in ITB11. - A substantially responsive bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - if accepted, would: #### Affect in any substantial way the scope, quality, or performance of the Plant and installation Services specified in the Contract; or #### Limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - If rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive bids. - The Employer shall examine the technical aspects of the bid in particular, to confirm that all requirements of Section 5 Employer's Requirements have been met without any material deviation, reservation or omission. - If a bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |  |
| - Nonconformities, Errors, and Omissions | - Provided that a bid is substantially responsive, the Employer may waive any non-conformity in the bid that do not constitute a material deviation, reservation or omission. - Provided that a bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the bid. Failure of the Bidder to comply with the request may result in the rejection of its bid. - Provided that a bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. The adjustment shall be made using the methods indicated in Section 3 (Evaluation and Qualification Criteria). - If minor discrepancies are found such as in technical specification, description, feature which do not make the bid to be rejected, then the cost, which is calculated to the extent possible due to such differences shall be included while evaluating the bid. |  |
| - orrection of Arithmetical Errors | - Provided that the bid is substantially responsive, the Employer shall correct arithmetical errors on the following basis: - where there are errors between the total of the amounts given under the column for the price breakdown and the amount given under the Total Price, the former shall prevail and the latter will be corrected accordingly; (b) where there are errors between the total of the amounts of Schedule Nos.1 to 4 and the amount given in Schedule No. 5 (Grand Summary), the former shall prevail and the latter will be corrected accordingly; and (c) if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. 31.2 If the Bidder that submitted the lowest evaluated bid does not accept the correction of errors, its bid shall be declared nonresponsive. |  |
| - Conversion to Single Currency | - For evaluation and comparison purposes, the currency of the bid shall be converted into a single currency as specified in the BDS. |  |
| - Domestic Preference | - Unless otherwise specified in the BDS, a domestic preference shall be a factor in bid evaluation. |  |
| - Evaluation of Bids | - The Employer shall use the criteria and methodologies listed in this Clause. No other evaluation criteria or methodologies shall be permitted. Technical Evaluation 36.2 The Employer will carry out a detailed technical evaluation of the bids to determine whether the technical aspects are in compliance with the Bidding Document. The bid that does not meet acceptable standards of completeness, consistency and detail, and the specified requirements for specified functional guarantees, will be rejected for non responsiveness. In order to reach its determination, the Employer will examine and compare the technical aspects of the bids on the basis of the information supplied by the bidders, taking into account the following: (a) overall completeness and compliance with the Employer’s Requirements; conformity of the Plant and Installation Services offered with specified performance criteria, including conformity with the specified requirement corresponding to each functional guarantee, as indicated in the Specification and in Section III Evaluation and Qualification Criteria; suitability of the Plant and Installation Services offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the bid; (b) type, quantity and long-term availability of mandatory and recommended spare parts and maintenance services; and (c) all the Goods are new, unused, and of the most recent or current models, and that they incorporate all recent improvements in design and materials, unless provided otherwise in the Contract. (d) Other relevant factors, if any, listed in Section III, Evaluation and Qualification Criteria. 36.3 Where alternative technical solutions have been allowed in accordance with ITB 13, and offered by the Bidder, the Employer will make a similar evaluation of the alternatives. Where alternatives have not been allowed but have been offered, they shall be ignored. Evaluation of Commercial Aspect of Bids as per PPR, 2064 : (1) The evaluation committee shall, after the technical aspect of a bid is evaluated pursuant to Rule 62, while evaluating the commercial aspect of such bid pursuant to Sub-rule (5) of Rule 61, have to evaluate the following matters:- (a) Period for supply of goods or completion of construction works or other services, (b) Conditions of payment, (c) Liquidated damages to be paid by the bidder for not completing work on time and the bonus entitled to for completing the work before time by the bidder, (d) Bidders liability towards warranty, (e) Liability to be fulfilled by the bidders, (f) If the bidder has added any other conditions to the proposed procurement contract, such conditions, (2) If, in evaluating pursuant to Sub-rule (1), a discrepancy is found between the matter stated in the bidding documents and in the matter stated by the bidder in bid, the evaluation committee shall note such discrepancy as well.(3) The evaluation committee shall ,while fixing the price of discrepancy under Sub-rule (2), fix the price of discrepancy by computing as per the criteria and method set out in the bidding documents. Financial Evaluation 36.4 To evaluate a bid, the Employer shall consider the following: (a) the bid price, excluding provisional sums and the provision, if any, for contingencies in the Price (b) price adjustment for correction of arithmetic errors in accordance with ITB 33.1; (c) price adjustment due to discounts offered in accordance with ITB 19.9 or ITB17.10; (d) price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 32.3; (e) converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 34; and (f) the evaluation factors indicated in Section III, Evaluation and Qualification Criteria. 34.5 If price adjustment is allowed in accordance with ITB 19.6,the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. 34.6 If this Bidding Document allows Bidders to quote separate prices for different lots (contracts), and the award to a single Bidder of multiple lots (contracts), the methodology to determine the lowest evaluated price of the lot (contract) combinations, including any discounts offered in the Letter of Bid, is specified in Section III, Evaluation and Qualification Criteria. 34.7 If the bid, which results in the lowest Evaluated Bid Price, is seriously unbalanced or front loaded in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Price Schedules, to demonstrate the internal consistency of those prices with the methods and time schedule proposed. After evaluation of the price analyses, taking into consideration the terms of payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. |  |
| - Comparison of Bids | - The Employer shall compare all substantially responsive bids in accordance with ITB 36 to determine the lowest evaluated bid. |  |
| - Post Qualification of the Bidder | - The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive bid is qualified to perform the contract satisfactorily. - The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 20. - An affirmative determination of qualification shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the bid, in which event the Employer shall proceed to the next lowest evaluated bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. |  |
| - Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | - The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to Contract award, without thereby incurring any liability to Bidders. In case of annulment, all bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |  |
| - Award of Contract |  |  |
| - Award Criteria | - The Employer shall award the Contract to the Bidder whose offer has been determined to be the lowest evaluated bid and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be qualified to perform the Contract satisfactorily. |  |
| - Letter of Intent to Award the Contract/ Notification of Award | - The Employer shall notify the concerned Bidder whose bid has been selected in accordance with ITB 38.1 within seven days of the selection of the bid, in writing that the Employer has intention to accept its bid and the information regarding the name, address and amount of selected bidder shall be given to all other bidders who submitted the bid. - If no bidder submits an application pursuant to ITB 42 within a period of seven days of the notice provided under ITB 39.1, the Employer shall, accept the bid selected in accordance with ITB 38.1 and Letter of Acceptance shall be communicated to the selected bidder prior to the expiration of period of Bid validity, to furnish the performance security and sign the contract within fifteen days. - At the same time, the Employer shall affix a public notice on the result of the award on its notice board and may make arrangements to post the notice into its website, if it has; and if it does not have, into the website of the Public Procurement Monitoring Office, identifying the bid and lot numbers and the following information: (i) name of each Bidder who submitted a Bid; (ii) bid prices as read out at Bid Opening; (iii) name and evaluated prices of each Bid; (iv) name of bidders whose bids were rejected and the reasons for their rejection; and (v) name of the winning Bidder, and the Price it offered, as well as the duration and summary scope of the Contract awarded. |  |
| - Performance Security | - Within Fifteen (15) days of the receipt of Letter of Acceptance from the Employer, the successful Bidder shall furnish the performance security in accordance with the conditions of Contract using Sample Form for the Performance Security included in Section 8 (Contract Forms), or another form acceptable to the Employer. - Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security. In that event the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |  |
| - Signing of Contract | - The Employer and the successful Bidder shall sign the Contract Agreement within the period as stated ITB 42.1. - Within 30 (thirty) days from the date of issuance of notification pursuant to ITB 41. Unsuccessful bidders may request in writing to the Employer for a debriefing seeking explanations on the grounds on which their bids were not selected. The Employer shall promptly respond in writing to any unsuccessful Bidder who, requests for debriefing within 30 days of publication of the contract award. |  |
| - Complain and Review | - If a Bidder is dissatisfied with the Procurement proceedings or the decision made by the Employer in the intention to award the Contract, it may file an application to the Chief of the Public Entity (Employer) within Seven (7) days of providing the notice under ITB 41.1 by the Public Entity, for review of the proceedings stating the factual and legal grounds. - Late application filed after the deadline pursuant to ITB 44.1 shall not be processed. - The chief of Public Entity(Employer) shall, within five (5) days after receiving the application, give its decision with reasons, in writing pursuant to ITB 44.1: - whether to suspend the procurement proceeding and indicate the procedure to be adopted for further proceedings; or - to reject the application. The decision of the chief of Public Entity shall be final for the Bid amount up to the value as stated in BDS. - If the Bidder is not satisfied with the decision given in accordance with ITB 44.3, or the decision is not given within five (5) days of receipt of application pursuant to ITB 44.1, it can, within seven (7) days of receipt of such decision, file an application to the Review Committee of the GoN, stating the reason of its disagreement on the decision and furnishing the relevant supporting documents, provided that its Bid amount is more than the Bid amount as specified in the BDS.. The application may be sent by hand, by post, by courier, or by electronic media at the risk of the Bidder itself. - Late application filed after the deadline pursuant to ITB 44.4 shall not be processed - The Review Committee, after inquiring from the Bidder and the Public Entity, if needed, shall give its decision within one (1) month of the receipt of the application filed by the Bidder, pursuant to ITB 44.4. - The Bidder, filing application pursuant to ITB 44.4, shall have to furnish a cash amount or Bank guarantee equivalent to zero point five percent (0.5%) of its quoted Bid amount with the validity period of at least ninety (90) days from the date of the filing of application pursuant to ITB 44.4. - If the claim made by the Bidder pursuant to ITB 44.4 is justified, the Review Committee shall return the security deposit pursuant to ITB 44 to the applicant, within seven (7) days of such decision made. |  |

Section 2 – Bidding Data Sheet (BDS)

A.  General

| ITB 1.1 | The number of the Invitation for Bids is : DDC/ICB/06/EXP/072/073 |
| --- | --- |
| ITB 1.1 | The Employer is: Dairy Development Corporation (DDC), Nepal |
| ITB 1.1 | The name of the ICB is: Procurement of Expansion of Existing Skimmed Milk Powder Plant, dairy w hitener machineries and Modification of Husk Fired Boiler at Biratnagar Milk Supply Scheme, Biratnagar. The identification number of the ICB is: DDC/ICB/06/EXP/072/073 The number and identification of lots comprising this ICB is: 01 (One) |
| ITB 2.1 | Source of funds :- Equity Financing from Govt. of Nepal |
| ITB 4.1 (a) | The individuals or firms in a joint venture, consortium or association Shall be jointly and severally liable. |
| ITB 4.4 | A list of debarred firms is available at http:/www.ppmo.gov.np |

B.  Bidding Document

| ITB 7.1 | For clarification purposes only, the Employer’s address is: The General Manager Dairy Development Corporation, Lainchaur, Kathmandu, Nepal. Telephone : + 977-01- 4428665 / 4414841/4024029 Fax number: + 977-01-4417215 E-mail address: info@dairydev.com.np |
| --- | --- |
| ITB 7.4 Site Visit | The bidder or his official representative is advised to attend a pre-bid meeting which will be convened at the following date, time and place: Date: 21st March, 2016 Time: 13.00 Noon ( Nepal Standard Time ) Place: Dairy Development Corporation, Central Office, Lainchaur, Kathmandu, Nepal. Telephone : + 977-01- 4428665 / 4414841/4024029 Fax number: + 977-01-4417215 E-mail address: info@dairydev.com.np The bidders are requested to visit the existing SMP plant at Biratnagar Milk Supply Scheme, Kanchanbari, Biratnagar before bidding at bidders own cost. Contact : Project Manager, Phone No:00977- 9852028640/021-520236 |

C.  Preparation of Bids

| ITB 10.1 | The language of the bid is: English |
| --- | --- |
| ITB 11.1 | The Bidder shall submit with its bid the following additional documents: 1. (i) Firm Registration or incorporation certificates issued by respective government office of their country for foreign bidders. |
|  | (ii). Importer-Exporter Certificate (IEC). 2. The foreign Bidder must mention whether any local agent / representative for this tender is appointed or not. If any local agent/representative appointed, the foreign Bidder should mention as follows :- i. Name and address of the agent/representative in Nepal, ii. Rate of commission, Type of currency and mode of payment to the agent/representative. iii. Other terms and conditions with agent / representative, if any. 3. i. Nepalese bidders / Local Agent or Representatives of Foreign Bidders must submit the Firm Registration (duly renewed copies) Certificate, PAN Certificate.. ii. Tax clearance certificate of Tax Assessment for the fiscal year 2071/72. 4. Acceptance letter of Local agent / Representatives to the foreign bidders; 5. Manufacturer Authorization: If the Bidder is not the manufacturers, the Bidder must have been duly authorized by the equipment manufacturers to supply the equipment in the Purchaser's country under this contract. Such authorization shall be necessary for following machineries of SMP Plant and dairy whitener and husk boiler. - Reverse Osmosis Plant (RO) for milk. - Buffer Tank - Pumps - Milk Chiller - Reverse Osmosis (RO) for water - Booster Pump with high pressure feed pump - Atomizer Assembly - Moisture Test Machine - Instrumentation and control panel - Powder Packing Machine 6. A written declaration made by the bidder, with a statement that s/he is not ineligible to participate in the procurement proceedings; has no conflict of interest in the proposed procurement proceedings, and has not been punished for a profession or business related offense and also not in black list. 7. If the bid has been submitted stating that no local agent has been appointed and later on it is found that local agent had been appointed or if it is proved that the amount of commission stated is less than the actual amount then the bidder will be fined an amount equivalent to the amount to be received by the agent and action will be taken as per the Public Procurement Act (GoN). |
| ITB 13.1 | Alternative bids: are not permitted. |
| ITB 13.2 | Alternative to the time schedule: shall not be permitted. |
| ITB 14.1 | The prices quoted by the Bidder shall not be subject to price adjustment. |
|  | The prices quoted by the Bidder are fixed and shall not be subject to adjustment during the time frame of the Contract. |
|  | The date for all duties, taxes, and other levies payable by the Contractor under the contract or for any other cause, as of the date 30 days prior to the deadline for submission of bids. |
| ITB 20.1 | The bid validity period shall be 120 days from the date of last submission. |
| ITB 21.1 | The amount and currency of the bid security shall be: NRs. 27,00,000/- or equivalent in any convertible currency. The bank guarantee shall be issued by an “A” class commercial bank of Nepal. If the bank guarantee is issued by a foreign bank, it shall be endorsed by an "A" class commercial bank of Nepal. Bid security shall be in the form of unconditional bank guarantee. |
| ITB 22.1 | In addition to the original of the bid, the number of copies is: One. |
| ITB 22.2 | The written confirmation of authorization to sign on behalf of the Bidder shall indicate: - Power of Attorney; and - In the case of Bids submitted by an existing or intended JV, an undertaking signed by all parties (i) stating that all parties shall be jointly and severally liable, and (ii) nominating a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the bidding process and, in the event the JV is awarded the Contract, during the signing of contract and execution. |

D.  Submission and Opening of Bids

| ITB 23.1 | Bidders shall have the option of submitting their bids electronically. |
| --- | --- |
| ITB 23.1 (b) | Electronic Bid submission procedure: As specified in subsequent section below. |
| ITB 24.1 | For bid submission purposes only, the Employer’s address is: The General Manager Dairy Development Corporation, Lainchaur City : Kathmandu Country : Nepal Telephone : + 977-01- 4428665 / 4414841/4024029 Fax number: + 977 1 4417215 E-mail address: info@dairydev.com.np The deadline for bid submission is: Date: 11 April 2016 Time 12.00 hours (NST) |
| ITB 27.1 | The bid opening shall take place at: Dairy Development Corporation, Lainchaur City : Kathmandu Country : Nepal Date: 11 April 2016 Time 13.00 hours (NST) |
| ITB 27.1 | Any specific electronic bid opening procedures shall be: As specified in Special Instruction to Bidders for e-Bidding below. |

E.  Evaluation and Comparison of Bids

| ITB 34.1 | The currency that shall be used for bid evaluation and comparison purposes to convert all bid prices if permitted and expressed in various currencies into a single currency is: The source of exchange rate shall be: Nepal Rastra Bank The date for the exchange rate shall be: 30 days prior to the deadline for submission of bids. |
| --- | --- |
| ITB 34.1 | A margin of preference shall be apply only for JV of foreign bidders with domestic bidders. |
| ITB 36.6 | Pursuant to Sub-Clause 34.6 of the Instructions to Bidders : Not Applicable |

| F. Award of Contract |  |
| --- | --- |
| ITB 43.1 | The amount of the performance security shall be 10% of the contract amount. The Bank guarantee shall be issued by an “A” class commercial bank of Nepal. If the Bank guarantee is issued by a foreign Bank, it shall be endorsed by an “A” class commercial bank located in Nepal. Performance security shall be in the form of unconditional Bank guarantee. |
|  | The Employer reserves the right at the time of award of contract to increase or decrease by up to 15% ( Fifteen Percent ) the quantity of goods and services specified in the Schedule of Requirements without any change in unit rates as specified in the price break-up or other terms and conditions. |

Special Instruction to Bidders for e-Bidding

- Bid submission procedures through electronically (e-submission) only:

- Interested eligible bidders shall, either purchase the hard copy of the bidding document directly from the Employer’s office as specified in the Invitation for Bid (IFB) or may download the necessary parts of the bidding documents from website http://www.gepson.gov.np. In case, the bidders choose to download the bidding documents, prepare the bids on downloaded documents, and submit their bids electronically. The Bidders shall be required to deposit the non refundable fee for the bidding document (as specified in the bid notice) in the bank account specified in the IFB and electronic scanned copy (*.pdf format) of the bank deposit voucher shall also be submitted along with the electronic bid files.

- The Bidder shall fill the following documents and forms (in hard copy of issued bid documents), signed by the authorized representative with seal of the company.  a) Bill of Quantity (BOQ) with rate, amount, b) Forms of Bid, Qualification Information The Bidder shall then scan the completed original documents, forms in PDF formats with appropriate filename shown in the table below.

| S. N. | Document | PDF File name | Requirement | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Voucher of Cost of Bidding documents | Voucher -1 | Mandatory |  |
| 2 | Form of Bid | Bid form -2 | Mandatory |  |
| 3 | Bid Security | Bid security-3 | Mandatory |  |
| 4 | Company Registration, | Company reg-4 | Mandatory | All firms in case of JV |
| 5 | VAT registration, | VAT reg-5 | Mandatory for National firms | All firms in case of JV |
| 6 | Tax clearances certificate | Tax-6 | Mandatory for National firms | All firms in case of JV |
| 7 | Power of Attorney of Bid signatory | Power of att-7 | Mandatory |  |
| 8 | Joint venture agreement | JV doc-8 | Mandatory | In case of JV |
| 9 | Qualification Information - Sub Contract Declaration - Specific Experience - General Experience - Annual Turnover certified by Auditor - Cash Flow | Qualification doc.-9 | Mandatory |  |
| 10 | BOQ with rate, amount and total amount | BOQ-10 | Mandatory |  |
| 11 | Manufacturers Authorization | Authorization -11 | Mandatory |  |
| 12 | Technical Data Sheet | TDS-12 | Mandatory |  |
| 13 | Declaration Letter | Declaration-13 | Mandatory |  |
| 14 | Export Permit License | Export License-14 | Mandatory |  |

Note:  Mandatory means the mentioned files shall be included in e-submission and non-submission   of such file shall be considered as non-responsive bid.

- For e-submission purpose the Bidder shall, at first, register in the PPMO’s website http://www.gepson.gov.np.

- After preparing all the required bidding documents in PDF, scan the files as specified in (ii).

- The Bidder shall upload the PDF bid files and submit the complete bid online through PPMO’s website http://www.gepson.gov.np within the specified date and time.

- The e-procurement system will accept the e-submission of bid from the date after publishing of notice and will automatically disallow the e-submission of bid after the deadline for submission of bid, as specified above.

- The standard time for e-submission is Nepalese Standard Time as set out in the server of PPMO.

- When a bidder submits bid in hard copy, the e-procurement section does not allow the bidder to submit Substitution or Modification or Withdrawal through e-procurement section of PPMO’s website.

- Bidders shall submit Substitution or Modification or Withdrawal of Bid offer in the same medium as submission of offer.

- For Modification or Withdrawal of bid, the Bidder is required to submit PDF scan copy of their Substitution or Modification or Withdrawal letter and a written Power of Attorney of the signatory for Modification/ Withdrawal, duly signed by Authorized Representative/s of the Firm / Company all authorized Joint Venture partners.

- In case the Bidder choose to download the bidding documents and deposit the cost of bidding documents (as specified in the bid notice), such deposited amount shall be verified by the office during bid evaluation process. The bid shall be considered as non-responsive and shall not be evaluated if the specified cost for bidding document is not deposited in the Employer’s Revenue account.

B) 	Requirements and Conditions for e-submission of bid:

- The Bidder shall submit his bid electronically in PDF files in the manner as specified above, and additional submission of hard copy of “original plus one copy of bid” is not mandatory.

- In case, if both the electronic bid and original bid in hard copy are submitted to the Employer within the bid submission deadline, the Bidder's electronic bid and original bid in hard copy will be accepted for evaluation provided the facts and figures in hard copy confirm to the PDF files in electronic bid. If there is any discrepancy in fact and figures between the electronic bid and original bid in hard copy, it will be treated as two separate bids from one Bidder and hence, both the electronic bid and original bid in hard copy shall be disqualified. However, for electronically submitted bid in PDF files, the Bidder shall be required to submit documents within 15 days.

- In case of e-submission of bid, the Bidder shall be required to submit the original completed Bid consisting of Forms of Bid, Qualification Information, Special Conditions of Contract, Bill of Quantities, Supplementary Information and other clarifications for verification purpose upon notification to do so from the Employer within 15 days.

- In addition to electronically submitted PDF files, the Bidder shall be required to submit documents and clarifications as required by the Employer. Non-submission of such documents and or clarifications by the Bidder within specified time may cause forfeiture of Bid Security.

- In case of major discrepancy found between electronically submitted PDF bid files and documents/ clarifications provided by the Bidder, the bid shall not be considered for further evaluation.

- The Bidder shall attach the unconditional Bid Security Guarantee issue by an  "A" class commercial bank registered in Nepal or incase of bank guarantee issued by foreign bank should be endorsed from an "A" class Nepalese Commercial Bank..

The Bid Security may be forfeited;

- If the Bidder does not respond to and/or submit the documents and or clarifications when requested by the Employer.

- If major discrepancy is found between e-submitted bid information and documents/clarifications provided by the Bidder during verification process as requested by the Employer.

C) Bid Opening process for e-submitted bid

- Electronically submitted bid shall be opened first at the bid opening process.

- The e-procurement system allows the Employer to download and open the e-submitted bid files from the bidders only after the time for opening the bids.

- The e-submitted bids must be readable through open standards interfaces. Unreadable and or partially submitted bid files (not complying with the ITB Clauses) shall be considered incomplete and rejected for further bid evaluation.

- After opening of e-submitted bids files, all files shall be printed and recorded at the time of bid opening.

- In case of "WITDRAWAL" or "MODIFICATION" or "SUBSTITUTION" by the Bidder through e-submission, the e-submitted PDF files under "WITDRAWAL" or "MODIFICATION" or "SUBSTITUTION" shall be opened and read out first. Bids for which acceptable notice of "WITDRAWAL" or "SUBSTITUTION" has been submitted pursuant to ITB Clause shall not be opened.

D) Bid Evaluation and Comparison process for e-submitted bid

- In case of e-submitted bids, the Employer evaluates the bid based on the information as per electronically submitted bid files. For clarification/ verification purpose, the Employer may request the Bidder to submit documents/ clarifications within given time.

- In case, the Bidder could not substantiate or provide evidence to prove the information provided in e-submitted bid through documents/clarifications, the bid shall not be considered for further evaluation and respective ITB Clause for forfeiture of bid security shall be applicable.

Section 3 - Evaluation and Qualification Criteria

Content

  - Evaluation Criteria

  - Technical Criteria

  - Multiple Contract

  - Completion Time

  - Post Qualification Requirements

  - Training of Personnel

  - Technical Alternative

  - Spare Parts

  - Qualification Criteria

Section 3 - Evaluation and Qualification Criteria

1. Evaluation Criteria (ITB 36.3 (d))

To evaluate a Bid, the Purchaser shall consider the following:

(a) 	Evaluation will be carried out as specified in the BDS; and the Bid Price as quoted in accordance with clause 17;

(b)	Price adjustment for correction of arithmetic errors in accordance with ITB Sub-Clause 31;

(c) 	Price adjustment due to discounts offered in accordance with ITB Sub-Clause 17.4;

(d) 	Adjustments due to the application of the evaluation criteria specified in the BDS from amongst those set out in Section III, Evaluation and Qualification Criteria

(iii)   Technical Experience

Evidence from end user supporting goods supplied should be submitted along with the bid.

The manufacturer shall hold valid quality ISO certificate and a copy of ISO certificate shall be included in the bid.

The bid shall include copy of Test certificate for the Goods offered. Such test certificate shall bear a date that is not earlier than five years from the last date of bid submission.

##### 2. Technical Criteria

The purchaser will evaluate and compare the technical merits of the bids based on the information supplied by the bidders taking into account the following factors:

2.1 Suitability of the process with regards to ultimate product quality conforming to the standards specified in the tender.

2.2 Specifications of individual equipment as well as the system as a whole for material of construction, throughput, operating parameters, level of automation etc.

2.3 Energy efficiency of individual equipment and system as a whole.

2.4 Determination of filling accuracy of the product packaging machines and product losses.

2.5 Product losses during processing and product manufacturing for individual equipment and ultimately in the effluent system.

2.6 Consumption of consumable materials.

2.7 Space requirement.

2.8 Cost of Spare Parts

# 3. Multiple Contracts : Not Applicable

The Purchaser shall award multiple contracts to the Bidder that offers the lowest evaluated combination of bids (one contract per bid) and meets the post qualification criteria (this Section III, Sub-Clause ITB Clause 38.2 Post Qualification Requirements). The Purchaser shall:

(a) 	evaluate only LOTS or Contracts that include at least the percentage of items per LOT and quantity per item as specified in ITB Sub Clause 14.8.

(b)	 take into account: (i) the lowest evaluated bid for each LOT and (ii) the price reduction per LOT and the methodology for its application as offered by the Bidder in its bid.

# 4. Completion Time

An alternative Completion Time, if permitted under ITB 13.2, will be evaluated                                        as follows:  “Not Applicable”

5. Post-qualification Requirements (ITB 38.2)

After determining the lowest-evaluated bid in accordance with ITB Sub-Clause 37.1, the Purchaser shall carry out the post qualification of the Bidder in accordance with ITB Clause 38, using only the requirements specified. Requirements not included in the text below shall not be used in the evaluation of the Bidder’s qualifications.

(a) Financial Capability

- The Bidder shall furnish documentary evidence that it meets the following financial requirement(s):

- Bidder shall demonstrate that his average annual turnover in the last three years is not less than US Dollor 0.67 Million

- The Average Annual Turnover requirements for Joint Venture Bidder: Lead Partner must meet minimum USD 0.36 Million and other partner(s) must meet minimum USD 0.23 Million.

- The Bidder shall furnish audit statement from last three years as evidence for the annual turnover as specified above.

(b) Experience and Technical Capacity

The Bidder shall furnish documentary evidence to demonstrate that it meets the following experience requirement(s):-

1. Bidders/Supplier must provide evidence of at least two contracts of upgrading/establishment of SMP Plant with Reverse Osmosis  and  dairy whitener value not less than  80% of the bid price of the job that have been execute in the last five years. The bidder should have design back up of such plants to carry out the job.

2. The Experience and Technical Capacity for Joint Venture Bidder:

All Partners Combined must provide evidence of at least two contracts of upgrading/establishment of SMP Plant with Reverse Osmosis and  dairy whitener value not less than  80% of the bid price of the job that have been execute in the last five years or 2 (two) contracts each with a value 50% of the bid price for the lot that have been successful establishment or expansion of skimmed milk powder plant and dairy whitener.

# 6. Training of Personnel

6.1 The Bidder/Supplier for operating the plant as may be deputed by the Purchaser shall train necessary staff. The personnel will be associated for the training during the installation; testing, commissioning and start-up period and the training tenure shall be extended for a minimum period of one month from the date of commissioning and start-up.

6.2.	The Bidder/Supplier should provide training to production and engineering personnel in the field of instrumentation, automation, management system, plant operation & control, maintenance & repair of systems & equipment for one week free of cost.

6.3 After satisfactory commissioning and start-up the Bidder/Supplier shall keep his representatives under whose supervision the Purchaser's staff shall be operating and maintaining the plant and equipment for a minimum period of one month.

6.4 The Bidder/Supplier's representatives should be present at all times during the running and operation of plant and equipment. During this period the Bidder/Supplier shall ensure proper working of complete plant and equipment and attend any works required to be done and shall also take complete responsibility for proper operation and maintenance of the complete plant and equipment.

6.5.	The Bidder/Supplier should also provide one year immediate support as and when required for the breakdown/repair/periodic maintenance/repair of the supplied equipment, accessories & fittings & also train purchaser technical staff.

7. Technical Alternative

7.1 Alternative technical solutions, if permitted under ITB 13.4, will be evaluated as follows:                “Not Applicable”

8. Spare parts

8.1 The bidder should provide spare parts for one year consumption of the machineries supplied which should be included in the quoted  bid price. The list should be attached along with the tender.

8.2 The bidder must give at least 10 years guarantee to supply spare parts in written agreement with the manufacturer of equipment offered in this tender. If the manufacturer has authorized any other manufacturer to manufacture and supply spares parts of concerned machineries, the bidder should also submit the details of the manufacturer along with the tender.

8.3 	In the event of termination of production of the spare parts:

-  Advance notification should be given to procure needed requirements.

-  Furnish soft copies, blue prints, drawings and specifications of the spare parts 	when    requested at no cost.

# 9. Qualification

9.1 Pursuant to Clause 11 the Bidder/Supplier shall furnish, as part of its bid, documents        establishing the Bidder/Supplier's qualifications to perform the Contract if its bid is accepted.        The Bidder/Supplier should also give information in the format attached to the Bidding        Document.

i.       The documentary evidence of the Bidder/Supplier's qualifications to perform the Contract                   if its bid is accepted, shall establish to the Purchaser's satisfaction.

ii.     That in the case of a Bidder/Supplier offering to supply goods and services under the    Contract which the Bidder/Supplier did not manufacture or otherwise produce, the   Bidder/Supplier has been duly authorized by the goods manufacturer or producer to                   supply the goods. The bid shall include manufacturer’s authorization sample form given in    the bidding documents. The list of machineries which requires authorization has been 	 mentioned in the   authorization sample form.

iii.    That the Bidder/Supplier has the financial, technical and production capability necessary                   to perform the Contract. To ascertain this, all bids submitted shall include the information                 as per the pro-forma along with qualification application (Table 1, 2 & 3) in Appendices.

iv. Qualification and experience of key personnel for successful execution of the contract.

v. Reports on financial standing of the Bidder/Supplier such as profit and loss statements, balance sheets, cash flow statement and, auditor's report of the past three years and also certificate of financial soundness from Bankers.

vi.    Information regarding any current litigation in which the Bidder/Supplier is involved.

vii.   The bidder or manufacturer should submit commitment letter for the upgrading the SMP

Plant,supply of diary whitener machineries and modification of husk boiler.

9.2   Bidder/Suppliers who meet the criteria given above are subject to be disqualified if they have made untrue or false representations in the forms, statements and attachments submitted in proof of the qualification requirements or have record of poor performance such as abandoning the work, not properly completing the contract, inordinate delays in completion or financial failures etc.

Section 4: Bidding Forms

Table of Forms

- Bidder Information Form

- Joint Venture Partner Information Form

- Bid Submission Form

- Manufacturer’s Authorization

- Price Schedule

- Bid Security (Bank Guarantee)

Check List of Bid Submission

| S N | Requirement | Tick (√) |
| --- | --- | --- |
| 1 | Bidder Information Form |  |
| 2 | Joint Venture Partner Information Form Bidder Information Form |  |
| 3 | Bid Submission Form |  |
| 4 | Check list for supporting (Qualification Application and supporting) |  |
| 5 | Manufacturers’ Authorization Form |  |
| 6 | Price schedule summary sheet and item wise break-up sheet |  |
| 7 | Bid Security (Earnest Money Deposit) |  |
| 8 | Power-of-attorney for authorized signatory |  |

Bidder Information Form

[The Bidder shall fill in this Form in accordance with the instructions indicated below. No alterations to its format shall be permitted and no substitutions shall be accepted.]

Date: [insert date (as day, month and year) of Bid Submission]

ICB No.: ______________________

Page ________ of_ ______ pages

1. Bidder’s Legal Name [insert Bidder’s legal name]

2. In case of JV, legal name of each party: [insert legal name of each party in JV]

3. Bidder’s actual or intended Country of Registration: [insert actual or intended Country of Registration]

4. Bidder’s Year of Registration: [insert Bidder’s year of registration]

5. Bidder’s Legal Address in Country of Registration: [insert Bidder’s legal address in country of registration]

6. Bidder’s Authorized Representative Information Name: [insert Authorized Representative’s name] Address: [insert Authorized Representative’s Address] Telephone/Fax numbers: [insert Authorized Representative’s telephone/fax numbers] Email Address: [insert Authorized Representative’s email address]

7. Attached are copies of original documents of: [check the box(es) of the attached original documents] - Articles of Incorporation or Registration of firm named in 1, above, in accordance with ITB Sub-Clauses 4.1 and 4.2. - In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB Sub- Clause 4.1. - In case of government owned entity from the Purchaser’s country, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB Sub-Clause 4.5.

Joint Venture Partner Information Form

Bidder Information Form

[The Bidder shall fill in this Form in accordance with the instructions indicated below].

Date: [insert date (as day, month and year) of Bid Submission]

ICB No.: ______________________

Page ________ of_ ______ pages

1. Bidder’s Legal Name [insert Bidder’s legal name]

2. JV’s Party legal name: [insert JV’s Party legal name]

3. JV’s Party Country of Registration: [insert JV’s Party country of registration]

4. JV’s Party Year of Registration: [insert JV’s Part year of registration]

5. JV’s Party Legal Address in Country of Registration: [insert JV’s Party legal address in country of registration]

6. JV’s Party Authorized Representative Information Name: [insert name of JV’s Party authorized representative] Address: [insert address of JV’s Party authorized representative] Telephone/Fax numbers: [insert telephone/fax numbers of JV’s Party authorized representative] Email Address: [insert email address of JV’s Party authorized representative]

7. Attached are copies of original documents of: [check the box(es) of the attached original documents] - Articles of Incorporation or Registration of firm named in 2, above, in accordance with ITB Sub-Clauses 4.1 and 4.2. - In case of government owned entity from the Purchaser’s country, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB Sub-Clause 4.5.

Bid Submission Form

( To be furnished in the letter head of the company )

[The Bidder shall fill in this Form in accordance with the instructions indicated No alterations to its format shall be permitted and no substitutions shall be accepted.]

Date: [insert date (as day, month and year) of Bid Submission]

ICB No.: ______________________

Alternative No.: NA

To: [insert complete name of Purchaser]

We, the undersigned, declare that:

(a) We have examined and have no reservations to the Bidding Documents, including Addenda No.: ______________[insert the number and issuing date of each Addenda];

(b) We offer to supply in conformity with the Bidding Documents and in accordance with the Delivery Schedules specified in the Schedule of Requirements the following Goods and Related Services _______________________ [insert a brief description of the Goods and Related Services];

(c) The total price of our Bid, excluding any discounts offered in item (d) below, is:

______________________________[insert the total bid price in words and figures,indicating the various amounts and the respective currencies];

(d) The discounts offered and the methodology for their application is:

Discounts. If our bid is accepted, the following discounts shall apply._______

[Specify in detail each discount offered and the specific item of the Schedule of Requirements to which it applies.]

Methodology of Application of the Discounts. The discounts shall be applied using the following method:__________ [Specify in detail the method that shall be used to apply the discounts];

(e) 	Our bid shall be valid for the period of time specified in ITB Sub-Clause 18.1, from the date fixed for the bid submission deadline in accordance with ITB Sub-Clause 22.1, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

(f) 	If our bid is accepted, we commit to obtain a performance security in accordance with ITB Clause 40 and GCC Clause 12 for the due performance of the Contract;

(g) We, including any subcontractors or suppliers for any part of the contract, have nationality from eligible countries_________ (insert the nationality of the Bidder including that of all parties that comprise the Bidder, if the Bidder is a JV, and the nationality each subcontractor and supplier]

(h) We have no conflict of interest in accordance with ITB Sub-Clause 4.2;

(i) 	Our firm, its affiliates or subsidiaries—including any subcontractors or suppliers for any part of the contract—has not been declared ineligible by the Bank, under the Purchaser’s country laws or official regulations, in accordance with ITB Sub-Clause 4.3;

(j) 	The following commissions, gratuities, or fees have been paid or are to be paid with respect to the bidding process or execution of the Contract: [insert complete name of each Recipient, its ful address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity]

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

(k) We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

(l) 	We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive.

Signed:_______________ [insert signature of person whose name and capacity are shown]

In the capacity of _______[insert legal capacity of person signing the Bid Submission Form]

Name:____________ [insert complete name of person signing the Bid Submission Form]

Duly authorized to sign the bid for and on behalf of:_____ [insert complete name of Bidder]

Dated on ____________ day of __________________,  [insert date of signing]

| Table 1 Checklist for Supporting |  |
| --- | --- |
| Supporting Required | Please (√) |
| Latest Balance sheet filed with (Name of Authority) on (Date) |  |
| Latest Profit & Loss Statement from (date) to (date) filed with (Name of Authority) on (date). |  |
| Cash Flow Statement for last 3 years |  |
| Audited copies of annual accounts and P & L account of latest 3 years |  |
| Certificate of Financial Soundness from Bankers of Bidder/Suppliers |  |
| Income Tax Clearance or tax assesment certificate of Inland Revenue Office of FY 2071/072 of Domestic Bidder or Local Agent / Representative of Foreign Bidder. |  |
| Firm Registration Certificate / Incorporation Certificate of Bidder |  |

| Table 2 Financial Soundness |  |  |  |  |
| --- | --- | --- | --- | --- |
| General Information |  |  |  |  |
| Name |  |  |  |  |
| Address |  |  |  |  |
| Phones |  |  |  |  |
| Mobile |  |  |  |  |
| Fax |  |  |  |  |
| E-mail |  |  |  |  |
| Contact Personnel with designation |  |  |  |  |
| Financial Information |  |  |  |  |
| S N | Description |  |  | Value (Rs) |
| 1 | Cash Balance |  | In Bank |  |
|  |  |  | In Hand |  |
|  |  |  | Total |  |
| 2 | Fixed Assets |  | Gross |  |
|  |  |  | Net |  |
| 3 | Current Assets |  | Inventories |  |
|  |  |  | Others |  |
|  |  |  | Total |  |
| 4 | Current liabilities |  | Bank Cash Credit |  |
|  |  |  | Sundry creditors |  |
|  |  |  | Others |  |
|  |  |  | Provisions |  |
|  |  |  | Contingent Liabilities (including claims not acknowledged, please specify) |  |
|  |  |  | Total |  |

| 5 | Capital | Share capital |  |
| --- | --- | --- | --- |
|  |  | Free reserves |  |
|  |  | Other reserves (please specify) |  |
| 6 | Term loans from financial institutions and banks |  |  |
| 7 | Working capital |  |  |
| 8 | Net worth |  |  |
| 9 | Debtors and advances considered good | More than 6 months |  |
|  |  | Less than 6 months |  |

| Significant Financial Ratios |  |  |  |
| --- | --- | --- | --- |
| SN | Ratio | Definition | Value |
| 1 | Current | Current Assets to Current Liabilities |  |
| 2 | Acid Test | (Cash + temporary investment held in lieu of cash + current receivable) / current liabilities |  |
| 3 | Solvency | Total Liability to Net Worth |  |
| Net Profit before Tax |  |  |  |
| S N | Period |  | Value |
| 1 | Current period |  |  |
| 2 | During the last Financial Year |  |  |
| 3 | During the year before last Financial Year |  |  |
| Financial Arrangements |  |  |  |
| S N | Period |  | Value |
| 1 | Own |  |  |
| 2 | Bank Credits |  |  |
| 3 | Others (Specify) |  |  |

| Sales |  |  |  |
| --- | --- | --- | --- |
| SN | Category of Customers | Value of orders to be executed/ anticipated Sales | Value |
|  |  | Current | Next Financial Year |
| 1 | Government Department |  |  |
| 2 | Commercial |  |  |
| 3 | Others |  |  |
|  | Total |  |  |
| Annual Turnover |  |  |  |
| SN | Financial Year (Please begin with current year) |  | Turnover |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |

| Table 3 |  |  |
| --- | --- | --- |
| Technical Competency |  |  |
| Classifications |  |  |
| SN | Category | Please (√) |
| 1 | Manufacturer |  |
| 2 | Clearing & Forwarding Agent |  |
| 3 | Stockist |  |
| 4 | Wholesale Dealer |  |
| 5 | Authorized Reseller |  |
| 6 | Authorized Service Agent |  |
| 7 | Retailer |  |
| 8 | Trader |  |
| 9 | Others (please specify) |  |
| Details on Plant |  |  |
| SN | Plant | Details |
| 1 | Location |  |
| 2 | Description |  |
| 3 | Type |  |
| 4 | Size of building |  |
| 5 | Is property on lease or free hold? |  |
| 6 | If on lease, indicate date of expiry of lease in each case. |  |
| 7 | Others (please specify |  |
| Plant Facilities |  |  |

| SN | Facilities | Ans | Remark |
| --- | --- | --- | --- |
| 1 | Space available for manufacturing (in m2) |  |  |
| 2 | Space available for store (in m2) |  |  |
| 3 | Space available for inspection (in m2) |  |  |
| 4 | Are buildings fire resistant? (Y/N) |  |  |
| 5 | Are premises approved by Municipal fire Department? (Y/N) |  |  |
| 6 | Are buildings under Municipal fire protection? |  |  |
| 7 | Are power & fuel supply adequate to meet production requirements? (Y/N) |  |  |
| 8 | Are adequate transportation facilities available? (Y/N) |  |  |
| 9 | Are safety measures adequate for performance of proposed contract? (Y/N) |  |  |
| 10 | Is adequate material handling equipment available? (Y/N) |  |  |
| Testing Facilities |  |  |  |
| SN | Facilities |  | Details |
| 1 | List testing equipment available |  |  |
| 2 | Give details of tests to be carried out on items offered. |  |  |
| 3 | Details of the testing organizations available. |  |  |
| Quality Control Organization |  |  |  |
| SN | Quality Control Method |  | Response |
| 1 | Are goods offered subject to Batch Test, Random Sampling or full 100% test for ……………. |  |  |
| 2 | Are tests carried out by factory employees or by a separate testing |  |  |
| 3 | Are independent Quality Control Organization checks made and ……. |  |  |

| Manufacturing Capacity |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | Description of Equipment | Capacity | Units Manufactured |  |  |  |  |  |
|  |  |  | Current Year |  | Last Year |  |  | 2nd last year |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| Personnel/ Organization |  |  |  |  |  |  |  |  |
| SN | Personnel in | Numbers in levels |  |  |  |  |  |  |
|  |  | Managerial |  | Supervisory |  |  | Skill Work men |  |
|  | Production |  |  |  |  |  |  |  |
|  | Marketing |  |  |  |  |  |  |  |
|  | Installation and Commissioning |  |  |  |  |  |  |  |
|  | Service |  |  |  |  |  |  |  |
|  | Spare parts |  |  |  |  |  |  |  |
|  | Administrative |  |  |  |  |  |  |  |
| Service Center nearest to our site location |  |  |  |  |  |  |  |  |
|  | Location |  |  |  |  |  |  |  |
|  | Phone no |  |  |  |  |  |  |  |
| SN | Information required on |  |  |  |  |  | Details |  |
| 1 | Number of skilled employees |  |  |  |  |  |  |  |
| 2 | Number of unskilled employees |  |  |  |  |  |  |  |
| 3 | Number of engineering employees |  |  |  |  |  |  |  |
| 4 | Number of administrative employees |  |  |  |  |  |  |  |
| 5 | List of special repair/ workshop facility available |  |  |  |  |  |  |  |
| 6 | The storage space available for spare parts (in m2) |  |  |  |  |  |  |  |
| 7 | Value of minimum stock of spares available at all the service centres in respective currency |  |  |  |  |  |  |  |
| 8 | List of the models/ types of equipment serviced by the Centre in last 2 years |  |  |  |  |  |  |  |

| References |  |  |
| --- | --- | --- |
| SN | Name of Organization | Address, Telephone, Fax, Contact Person |
| 1 |  |  |
| 2 |  |  |
| List of components usually subcontracted |  |  |
| 1 |  |  |
| 2 |  |  |

Workload for the current and forth coming financial year on quarterly basis

| SN |  | Financial Year |  |  | Quarterly Workload as % of Total Capacity |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | I |  |  | II | III |  | IV |
| 1 |  | Current Financial Year |  |  |  |  |  |  |  |  |  |
| 2 |  | Next Financial Year |  |  |  |  |  |  |  |  |  |
| List of major projects of similar size and nature previously executed |  |  |  |  |  |  |  |  |  |  |  |
| S N | Name of the client |  | Project | Year of Award |  | Year of completion | Capacity/ Products |  |  | Value (Currency) |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |
| Type of equipment manufactured and supplied (M & S) during last 2 years |  |  |  |  |  |  |  |  |  |  |  |
| S N | Equipment |  | Capacity | Qty |  | Projects |  |  |  | On Hand Order Qty |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |
| Type of equipment manufactured, supplied, installed and commissioned (MSIC) |  |  |  |  |  |  |  |  |  |  |  |
| S N | Equipment |  | Capacity | Qty |  | Projects |  |  |  | On Hand Order Qty |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |
| Schedules for furnishing technical data and certified drawings after receipt of orders |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| Number of weeks required for preparing a bid proposal |  |  |  |  |  |  |  |  |  |  |  |

Manufacturer’s Authorisation Sample Form

[The Bidder is required to submit the manufacturer authorization in accordance with the instructions indicated below. This letter of authorization should be on the original letterhead of the Manufacturer and should be signed by a person with the proper authority to sign documents that are binding on the Manufacturer.  The Bidder shall include it in its bid, if so indicated in the BDS.]

Date: [insert date (as day, month and year) of Bid Submission]

ICB No.: [insert number of bidding process]

To:  [insert complete name of Purchaser]

WHEREAS

We [insert complete name of Manufacturer], who are official manufacturers of [insert type of goods manufactured], having factories at [insert full address of Manufacturer’s factories], do hereby authorize [insert complete name of Bidder] to submit a bid the purpose of which is to provide the following Goods, manufactured by us [insert name and or brief description of the Goods], and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 30 of the General Conditions of Contract, with respect to the Goods offered by the above firm.

Signed: [insert signature(s) of authorized representative(s) of the Manufacturer]

Name: [insert complete name(s) of authorized representative(s) of the Manufacturer]

Title: [insert title]

Duly authorized to sign this Authorization on behalf of: [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

Note: The original authorization letter of the following machineries is a must. Failure to submit will be

rejection of  tender:

- Reverse Osmosis Plant (RO) for milk.

- Buffer Tank

- Pumps

- Milk Chiller

- Reverse Osmosis (RO) for water

- Booster Pump with high pressure feed pump

- Atomizer Assembly

- Moisture Test Machine

- Instrumentation and control panel

- Powder Packing Machine

Price Schedules

Goods Manufactured Outside The Purchaser’s Country To Be Imported

Schedule No. 1 :  Expansion of Powder Plant from 3 MTPD to 6 MTPD

| S. No. | Work & Supply Description | Make, Model, Year and Country of Origin | Quantity | CIP BMSS Unit Price |  | Total Price |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | In figure | In Word |  |
| 1 | Feed section |  | 1 Lot |  |  |  |
| 2 | Reverse osmosis arrays |  | 1 lot |  |  |  |
| 3 | Concentrate section |  | 1 lot |  |  |  |
| 4 | Permeate section |  | 1 lot |  |  |  |
| 5 | Frame |  | 1 lot |  |  |  |
| 6 | Controls |  | 1 lot |  |  |  |
| Total cost |  |  |  |  |  |  |
| Balancing equipment for concentrate storage and dispatch |  |  |  |  |  |  |
| 1 | Concentrate buffer tank |  | 1 No |  |  |  |
| 2 | Concentrate transfer pump |  | 1 No |  |  |  |
| 3 | Concentrate milk chiller |  | 1 No |  |  |  |
| 4 | CIP return pump |  | 1 No |  |  |  |
| 5 | Tanker loading hose with fittings |  | 1 Set |  |  |  |
| 6 | Tanker loading pump |  | 1 No |  |  |  |
| 7 | Mass flow meter |  | 1 No |  |  |  |
| 8 | Flow plate for tanker loading hose |  | 1 No |  |  |  |
| 9 | Dispatch control panel - mmi |  | 1 Set |  |  |  |
| 10 | SS pipes, valves and fittings |  | 1 lot |  |  |  |
| 10.1 | SS (product / cip) pipes & fittings |  | 1 lot |  |  |  |
| 10.2 | Valves |  | 1 lot |  |  |  |
| 10.2.1 | Sanitary pneumatic seat valves |  | 1 lot |  |  |  |
| 10.2.2 | SS Pneumatic Valves (All Types other than Mix Proof Valves) |  | 1 lot |  |  |  |
| 10.2.3 | SS pneumatic mix proof valves |  | 1 lot |  |  |  |
| 10.2.4 | SS manual valves & fittings |  | 1 lot |  |  |  |
| 10.2.5 | Actuated butterfly valves |  | 1 lot |  |  |  |
| 10.2.6 | Other process valves |  | 1 lot |  |  |  |
| 10.2.7 | Manual and Actuated Utility Valves |  | 1 lot |  |  |  |
| 10.3 | SS piping (Product/CIP) support |  | 1 lot |  |  |  |
| 11 | MCC panel and electrical |  | 1 Set |  |  |  |
| 12 | Electricals:- |  |  |  |  |  |
| 12.1 | Motor control centres |  | 1 lot |  |  |  |
| 12.2 | Power and control cables |  | 1 lot |  |  |  |
| 12.3 | Remote control panels |  | 1 lot |  |  |  |
| 12.4 | Earthing: |  | 1 lot |  |  |  |
| 12.5 | Miscellaneous items: (GI cable trays, Isolators, Rubber mats, Conduits, other items, All spare parts needed for trouble-free operation of the unit). |  | 1 lot |  |  |  |
| Total cost |  |  |  |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal :

Date :

| Reverse osmosis system on borewell water (ro plant) equipment specifications |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No. | Work & supply description | Make, Model, Year and Country of Origin | Quantity | Cip bmss unit price |  | Total price |
|  |  |  |  | In figure | In Word |  |
| 1 | Feed Section |  | 1 Set |  |  |  |
| 2 | Pre-Feed Pump and Feed Pump |  | 1 Set |  |  |  |
| 3 | Membrane Module |  | 1 Set |  |  |  |
| 4 | High Pressure Pump |  | 1 No. |  |  |  |
| 5 | CIP Systems |  | 1 Lot |  |  |  |
| 6 | Frame |  | 1 No. |  |  |  |
| 7. | Instruments and controls |  | 1 Set |  |  |  |
| Total cost |  |  |  |  |  |  |
| 1 | Regenerative heater with flash vessle (one stage), moc: ss 304 |  | 1 No. |  |  |  |
| 2 | Tangetial swirl heater ( two stage), moc : AISI 304 |  | 1 No. |  |  |  |
| 3 | Hydro- cyclone, MOC AISI 304 |  | 1 Set |  |  |  |
| 4 | Thermo Vapor re-compressor MOC of Head : AISI 304 Mixing Passage /diffuser : AISI 304 Motive nozzles : AISI 304 Steam Chest : AISI 304 Flanges : CS |  | 1 No. |  |  |  |
| 5 | Product transfer pump, MOC AISI 304 |  | 3 Nos. |  |  |  |
| 6 | Vacuum pump |  | 2 Nos. |  |  |  |
| 7 | Instrumentation and control Panel An Instrument panel shall be of SS 304 It shall consist of I. Mimic diagram of the Evaporator Ii. Auto Feed Control (Flow meter) with VFD in feed pump, magnetic flow meter & PID.\ Iii. Density meter Iv. Steam Pressure Control Loop for Calandria TVR (Pressure Transmitter, Pressure Controller, Steam Control Valves With I/P Converter,AFR, Tubing & Fitting ). V. Temperature Control Loop for DSI ( Temperature transmitter, Temperature Controller, Steam Control Valve with I/P Convertor, AFR, Tubing & Fitting ) Vi. Digital Temperature indicators. ( Cal Jackets, Vapor Separators, Feed temperature, DSI and flash vessel temperature, Concentrate temperature ) Vii. Local instrumentation and indicators ( Dial type Thermometer indicating temperature of : Cooling water Inlet / Outlet temperature, First effect Calandria Chest, All vapor separators ( 0 to 110 °C). Dial type Pressure Gauge for TVR(0 to 10 bar g ). Dial type vacuum gauge (For calandria chest, for vapor separator, for Condenser.) |  | 1 Set |  |  |  |
| 8 | Cable, cable tray, earthing material & any modification in the exiting MCC & miscellaneous jobs |  | 1 lot |  |  |  |
| 9 | SS ducting |  | 1 lot |  |  |  |
| 10 | Ms pipes, valves, fittings for steam, condensate & water lines. |  | 1 lot |  |  |  |
| 11 | Ss pipes, valves & fittings |  | 1 lot |  |  |  |
| 12 | The existing evaporating plant various stage pumps if not found suitable or beyond maintenance, the same 9 No’s shall be considered in scope. |  | 1 lot |  |  |  |
| 13 | All the defective SS Pipes & fittings as well as utility valves shall be considered in supply. |  | 1 lot |  |  |  |
| 14 | The existing evaporating plant various stage all 9 nos. pumps to be replaced |  | 1 lot |  |  |  |
| 15 | Replacement of existing evaporator safety valves. |  | 1 lot |  |  |  |
| 16 | Miscellaneous job (any other defective parts & equipments) |  | 1 lot |  |  |  |
| Total cost |  |  |  |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal :

Date :

| D1. Spray drying plant equipments |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No. | Work & Supply Description | Make, Model, Year and Country of Origin | Quantity | CIP BMSS Unit Price |  | Total Price |
|  |  |  |  | In Figure | In Words |  |
| 1 | Feed pipes and fittings |  | 1 lot |  |  |  |
| 2 | Concentrate Preheater system |  | 1 No. |  |  |  |
| 3 | Booster Pump with High Pressure Feed Pump with Motor. |  | 1 No. |  |  |  |
| 4 | Atomizer Assembly with 1 No. Nozzle MOC SS : 304 |  | 1 Lot |  |  |  |
| 5 5.1 | DRYING CHAMBER SYSTEM AIR disperser and cooling system : |  | 1 No |  |  |  |
| 5.2 | Existing chamber |  | 1 No. |  |  |  |
| 6 | Modification in cyclone if necessary |  | 1 No. |  |  |  |
| 7 | Exhaust fan with motor with damper |  | 1 Set |  |  |  |
| 8 | Fine return system |  | 1 Set |  |  |  |
| 9 | Modification of vibro fludizer |  | 1 No. |  |  |  |
| 10 | Safety System :- |  |  |  |  |  |
| i | Over pressure relief panel |  | 1 Set |  |  |  |
| ii | Fire extinguishing system for DC |  | 1 Set |  |  |  |
| iii | Fire extinguishing system for VF |  | 1 Set |  |  |  |
| iv | Fire water tank, MOC : M.S. |  | 1 No. |  |  |  |
| v | Fire extinguishing pump, MOC : CI body with SS Impeller |  | 1 No. |  |  |  |
| vi | Control Panel for fire system |  | 1 Set |  |  |  |
| 11 | Instrumentation & Control System i. Mimic diagram of the Dryer ii. Auto temperature control iii. 1 No. Auto feed control – VFD for high pressure Pump to control the feed with exhaust air temperature & PID iv Auto Fire Extinguisher system v. Local Instruments ( Pressure Guage on steam header, vacuum gauge on feed pre-heater, pressure switch for Blow Through Valve, Pressure Transmitter on Drying Chamber for Alarm & Exhaust Fan cut-off) vi Temp. Indicators, Range 0 to 100 Deg. C.( for FBD hot air ) vii. Vacuum/ Differential Pressure indicator ( for chamber, for cyclone, for FBD ) |  | 1 Set |  |  |  |
| 12 | Electricals, Cables, earth pit, starters cable tray, earthing material etc. |  | 1 Lot |  |  |  |
| 13 | Utility Pipes & Fittings ( Steam pipes and fittings, Compressed air pipes and fittings, Condensate pipe and fittings, Chilled water pipes & fittings ) |  | 1 lot |  |  |  |
| 14 | Electro Magnetic Hammers |  | 1 Lot |  |  |  |
| 15 | Quick Moisture Test Machine |  | 1 Set |  |  |  |
| 16 | Structural modification with Consumable |  | 1 lot |  |  |  |
| 17 | Miscellaneous |  | 1 lot |  |  |  |
| Total cost |  |  |  |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal :

Date :

Dairy Whitener Machinery

| S. No. | Work & Supply Description | Make, Model, Year and Country of Origin | Quantity | CIP BMSS Unit Price |  | Total Price |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | In Figure | In Words |  |
| 1 | Sugar Dissolving Vat |  | 1 No |  |  |  |
| 2 | Sugar Syrup Transfer Pump |  | 1 No |  |  |  |
| 3 | Hopper |  | 1 No |  |  |  |
| 4 | Pouch Filling Machine for Powder |  | 1 Lot |  |  |  |
| 5. | SS Table |  | 1 No |  |  |  |
| 6. | Instrumentation and Control Panel |  | 1 Lot |  |  |  |
| 7. | SS 304 interconnecting pipes, valves and fittings with complete work |  | 1 Lot |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal :

Date :

Schedule No. 2: Modification of the existing husk boiler in proper FBC Working Pressure Maximum 13 kg./ cm2

| S. No. | Work & Supply Description | Make, Model, Year and Country of Origin | Quantity | CIP BMSS Unit Price |  | Total Price |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | In Figure | In Words |  |
| 1 | High pressure feed pump. Pump mode:- CR_-5-36, Make :- GRUNDFOS Flow 4.8 M³/hr. @ 210 MLC head Power :- 5.5 KW |  | 2 Nos. |  |  |  |
| 2 | High pressure safety valve |  | 2 Nos. |  |  |  |
| 3 | High pressure switch |  | 1 No. |  |  |  |
| 4 | New FBC furnace systems with air plenum chamber and FBC nozzle |  | 1 Set |  |  |  |
| 5 | Fuel feeding pneumatic speeder |  | 1 Set |  |  |  |
| 6 | Screw feeder with gear motor, 2 HP motor |  | 1 Set |  |  |  |
| 7 | SFD fan with motor, 2 HP motor |  | 1 Set |  |  |  |
| 8 | High pressure FD fan 20 HP motor |  | 1 Set |  |  |  |
| 9 | Refectories work modification and supply as per new requirement, |  | 1 Set |  |  |  |
| 10 | Modification in control panel systems |  | 1 Set |  |  |  |
| Total cost |  |  |  |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal:

Date:

Schedule No. 3:    Installation, Testing & Commissioning and other Services

| Item | Description | Qty. | Unit Price |  | Total Price |
| --- | --- | --- | --- | --- | --- |
|  |  |  | In Figure | In Words |  |
| 1 | Expansion of Powder Plant from 3 MTPD to 6 MTPD | 1 Lot |  |  |  |
| 2 | Dairy Whitener | 1 Lot |  |  |  |
| 3 | Modification of the existing husk boiler in proper FBC Working Pressure Maximum 13 kg./ cm2 | 1 Lot |  |  |  |
|  | Total |  |  |  |  |

Signature of Authorized Signatory of Bidder / Supplier:

Seal:

Date:

Schedule No. 4: Summary Sheet

| SN | Summary Heads | Amount |
| --- | --- | --- |
| 1 | Total CIP Biratnagar, Nepal Price of modification machineries for existing SMP Plant including spare parts |  |
|  | Total Installation, Testing & Commissioning Charges of existing SMP Plant |  |
| 2 | Total CIP Biratnagar, Nepal Price of machineries for dairy whitener including spare parts |  |
|  | Total Installation, Testing & Commissioning Charges of Dairy Whitener. |  |
| 3 | Total CIP Biratnagar, Nepal Price of modification equipment for the existing Husk Boiler |  |
|  | Total Installation, Testing & Commissioning Charges of the existing Husk Boiler |  |
| 4 | Training for the operation, maintenance of SMP Plant, Dairy Whitener & Husk Boiler |  |
|  | Total Bid Price |  |

Note:

1 Bid must be submitted strictly as per this Summary Sheet.

Signature of Authorized Signatory of Bidder / Supplier:

Seal :

Date :

Bid Security Sample Form

Bank’s Name, and Address of Issuing Branch or Office

[on letter head of the “A” class commercial Bank]

Beneficiary: 	name and address of Employer

Date:

Bid Security No.:

We have been informed that . . . . . name of the Bidder. . . . .  (hereinafter called “the Bidder”) has submitted to you its bid dated . . . . . . . . . (hereinafter called “the Bid”) for the execution of . . . . . . . . name of Contract . . . . . . . under Invitation for Bids No. . . . . . . . . . (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we  . . . . . name of Bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . . . . . .amount in figures . . . .  . . . . .  (. . . . . . .amount in words . . . . . . .  ) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a)	has withdrawn its Bid during the period of bid validity specified by the Bidder in the Form of Bid; or

(b)	does not accept the correction of errors in accordance with the Instructions to Bidders (hereinafter “the ITB”); or

(c)	having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Agreement, or (ii) fails or refuses to furnish the performance security, in accordance with the ITB.

This guarantee will expire: (a) if the Bidder is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Bidder and the performance security issued to you upon the instruction of the Bidder; and (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy your notification to the Bidder of the name of the successful Bidder; or (ii) thirty days after the expiration of the Bidder’s bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

. . . . . . . . . . . .Bank’s seal and authorized signature(s) . . . . . . . . . .

____________________________________________________________________________

Note:	 All italicized text is for use in preparing this form and shall be deleted from the final document

The bid security of ……………….. has been counter guaranteed by the Bank ………… on ………………. (Applicable for Bid security of Foreign Banks)

Part II

Supply Requirements

Section 5 -  Schedule of requirements

Contents

- Delivery Schedule

- Technical Details

- Sub-Section 1, Introduction

- Sub-Section 2, Acceptance of working condition

- Sub-Section 3, Basis of design

- Sub-Section 4, Responsibilities

- Sub-Section 5, Project Management

- Sub-Section 6, Technical Specification

- Sub-Section 7, Battery Limits

- Sub-Section 8, Process proformance and consumption gaurentee

- Sub-Section 9, Spare parts

- Sub-Section 10, Warrnty

- Sub-Section 11, Tools, Manuals and Catalogue

- Sub-Section 12, Training

- Sub-Section 13, Drawing Data & Documents

- Existing plant drawings

Delivery Schedule

| Line Item No. | Description of Goods | Quantity | Final ( Project Site ) Destination as specified in BDS | Delivery ( as per Incoterms ) Date |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Earliest Delivery Date | Latest Delivery Date | Bidder’s offered Delivery date ( to be provided by the bidder ) |
| Schedule No. 1 : Expansion of Powder Plant from 3 MTPD to 6 MTPD |  |  |  |  |  |  |
| 1 | Feed section | 1 Lot |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | Reverse osmosis arrays | 1 lot |  |  |  |  |
| 3 | Concentrate section | 1 lot |  |  |  |  |
| 4 | Permeate section | 1 lot |  |  |  |  |
| 5 | Frame | 1 lot |  |  |  |  |
| 6 | Controls | 1 lot |  |  |  |  |
| Balancing equipment for concentrate storage and dispatch |  |  |  |  |  |  |
| 1 | Concentrate buffer tank | 1 No |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | Concentrate transfer pump | 1 No |  |  |  |  |
| 3 | Concentrate milk chiller | 1 No |  |  |  |  |
| 4 | CIP return pump | 1 No |  |  |  |  |
| 5 | Tanker loading hose with fittings | 1 Set |  |  |  |  |
| 6 | Tanker loading pump | 1 No |  |  |  |  |
| 7 | Mass flow meter | 1 No |  |  |  |  |
| 8 | Flow plate for tanker loading hose | 1 No |  |  |  |  |
| 9 | Dispatch control panel - mmi | 1 Set |  |  |  |  |
| 10 | Ss pipes, valves and fittings | 1 lot |  |  |  |  |
| 10.1 | Ss (product / cip) pipes & fittings | 1 lot |  |  |  |  |
| 10.2 | Valves | 1 lot |  |  |  |  |
| 10.2.1 | Sanitary pneumatic seat valves | 1 lot |  |  |  |  |
| 10.2.2 | SS Pneumatic Valves (All Types other than Mix Proof Valves) | 1 lot |  |  |  |  |
| 10.2.3 | Ss pneumatic mix proof valves | 1 lot |  |  |  |  |
| 10.2.4 | Ss manual valves & fittings | 1 lot |  |  |  |  |
| 10.2.5 | Actuated butterfly valves | 1 lot |  |  |  |  |
| 10.2.6 | Other process valves | 1 lot |  |  |  |  |
| 10.2.7 | Manual and Actuated Utility Valves | 1 lot |  |  |  |  |
| 10.3 | Ss piping (product/cip) support | 1 lot |  |  |  |  |
| 11 | Mcc panel and electricals | 1 Set |  |  |  |  |
| 12 | Electricals:- |  |  |  |  |  |
| 12.1 | Motor control centres | 1 lot |  |  |  |  |
| 12.2 | Power and control cables | 1 lot |  |  |  |  |
| 12.3 | Remote control panels | 1 lot |  |  |  |  |
| 12.4 | Earthing: | 1 lot |  |  |  |  |
| 12.5 | Miscellaneous items: (GI cable trays, Isolators, Rubber mats, Conduits, other items, All spare parts needed for trouble-free operation of the unit). | 1 lot |  |  |  |  |
| Reverse osmosis system on borewell water (ro plant) equipment specifications |  |  |  |  |  |  |
| 1 | Feed Section | 1 Set |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | Pre-Feed Pump and Feed Pump | 1 Set |  |  |  |  |
| 3 | Membrane Module | 1 Set |  |  |  |  |
| 4 | High Pressure Pump | 1 No. |  |  |  |  |
| 5 | CIP Systems | 1 Lot |  |  |  |  |
| 6 | Frame | 1 No. |  |  |  |  |
| 7. | Instruments and controls | 1 Set |  |  |  |  |
| 8 | Regenerative heater with flash vessle (one stage), moc: ss 304 | 1 No. |  |  |  |  |
| 9 | Tangetial swirl heater ( two stage), moc : AISI 304 | 1 No. |  | 3 Months from the establishment of LC | 4 Months |  |
| 10 | Hydro- cyclone, MOC AISI 304 | 1 Set |  |  |  |  |
| 11 | Thermo Vapor re-compressor | 1 No. |  |  |  |  |
| 12 | Product transfer pump | 3 Nos. |  |  |  |  |
| 13 | Vacuum pump | 2 Nos. |  |  |  |  |
| 14 | Instrumentation and control Panel | 1 Set |  |  |  |  |
| 15 | Cable, cable tray, earthing material & any modification in the exiting MCC & miscellaneous jobs |  |  |  |  |  |
| 16 | Ss ducting | 1 lot |  |  |  |  |
| 17 | Ms pipes, valves, fittings for steam, condensate & water lines. | 1 lot |  |  |  |  |
| 18 | Ss pipes, valves & fittings | 1 lot |  |  |  |  |
| 19 | All the defective SS Pipes & fittings as well as utility valves | 1 lot |  |  |  |  |
| 20 | The existing evaporating plant various stage all 9 nos. pumps to be replaced | 1 lot |  |  |  |  |
| 21 | Replacement of existing evaporator safety valves. | 1 lot |  |  |  |  |
| 22 | Miscellaneous job (any other defective parts & equipments) | 1 lot |  |  |  |  |
| D1. Spray drying plant equipments |  |  |  |  |  |  |
| 1 | Feed pipes and fittings | 1 lot |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | Concentrate Preheater system | 1 No. |  |  |  |  |
| 3 | Booster Pump with High Pressure Feed Pump with Motor. | 1 No. |  |  |  |  |
| 4 | Atomizer Assembly with 1 No. Nozzle | 1 Lot |  |  |  |  |
| 5 5.1 | DRYING CHAMBER SYSTEM AIR disperser and cooling system | 1 No |  |  |  |  |
| 5.2 | Existing chamber | 1 No. |  |  |  |  |
| 6 | Modification in cyclone if necessary | 1 No. |  |  |  |  |
| 7 | Exhaust fan with motor with damper | 1 Set |  |  |  |  |
| 8 | Fine return system | 1 Set |  |  |  |  |
| 9 | Modification of vibro fludizer | 1 No. |  |  |  |  |
| 10 | Safety System :- |  |  |  |  |  |
| i | Over pressure relief panel | 1 Set |  |  |  |  |
| ii | Fire extinguishing system for DC | 1 Set |  |  |  |  |
| iii | Fire extinguishing system for VF | 1 Set |  |  |  |  |
| iv | Fire water tank | 1 No. |  |  |  |  |
| v | Fire extinguishing pump | 1 No. |  |  |  |  |
| vi | Control Panel for fire system | 1 Set |  |  |  |  |
| 11 | Instrumentation & Control System | 1 Set |  |  |  |  |
| 12 | Electricals, Cables, earth pit, starters cable tray, earthing material etc. | 1 Lot |  |  |  |  |
| 13 | Utility Pipes & Fittings ( Steam pipes and fittings, Compressed air pipes and fittings, Condensate pipe and fittings, Chilled water pipes & fittings ) | 1 lot |  |  |  |  |
| 14 | Electro Magnetic Hammers | 1 Lot |  |  |  |  |
| 15 | Quick Moisture Test Machine | 1 Set |  |  |  |  |
| 16 | Structural modification with Consumable | 1 lot |  | 3 Months from the establishment of LC | 4 Months |  |
| 17 | Miscellaneous | 1 lot |  |  |  |  |

| Line Item No. | Description of Goods | Quantity | Final ( Project Site ) Destination as specified in BDS | Delivery ( as per Incoterms ) Date |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Earliest Delivery Date | Latest Delivery Date | Bidder’s offered Delivery date ( to be provided by the bidder ) |
| Schedule No. 2 : Dairy Whitener |  |  |  |  |  |  |
| 1 | Sugar Dissolving Vat | 1 No |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | Sugar Syrup Transfer Pump | 1 No |  |  |  |  |
| 3 | Hopper | 1 No |  |  |  |  |
| 4 | Pouch Filling Machine for Powder | 1 Lot |  |  |  |  |
| 5 | SS Table | 1 No |  |  |  |  |
| 7 | Instrumentation and Control Panel | 1 Lot |  |  |  |  |
| 7 | SS 304 interconnecting pipes, valves and fittings with complete work | 1 Lot |  |  |  |  |
| Schedule No.3 : Modification of the existing husk boiler in proper FBC Working Pressure Maximum 13 kg./ cm2 |  |  |  |  |  |  |
| 1 | High pressure feed pump. | 2 Nos. |  | 3 Months from the establishment of LC | 4 Months |  |
| 2 | High pressure safety valve | 2 Nos. |  |  |  |  |
| 3 | High pressure switch | 1 No. |  |  |  |  |
| 4 | New FBC furnace systems with air plenum chamber and FBC nozzle | 1 Set |  |  |  |  |
| 5 | Fuel feeding pneumatic speeder | 1 Set |  |  |  |  |
| 6 | Screw feeder with gear motor, 2 HP motor | 1 Set |  |  |  |  |
| 7 | SFD fan with motor, 2 HP motor | 1 Set |  |  |  |  |
| 8 | High pressure FD fan 20 HP motor | 1 Set |  |  |  |  |
| 9 | Refectories work modification and supply as per new requirement, | 1 Set |  |  |  |  |
| 10 | Modification in control panel systems | 1 Set |  |  |  |  |

1 - INSTRUCTION

i. BACKGROUND:

Biratnagar Milk Supply Scheme, has one Spray Drying and Evaporation Plants installed at Kanchanbari, Biratnagar plant. It is proposed to go for expansion / Revamping of the plants as per the following details:

Evaporator Plant:

The plant is designed to manufacture 3 Tons per day of Skimmed Milk Powder.

It is proposed to:

• 	Increase the production capacity to 6 MT per day of SMP by adding membrane 	concentrating plant to concentrate skim milk from 8% to 23 % and further concentrate to 45 to 48 % in the existing evaporation plant after carrying out suitable modifications.

•		Modifications in spray drying system as envisaged / explained later.

•		Addition of dairy whitener machineries & installation

• 	A boiler modification

ii. PROJECT TIME SCALE:

Project execution shall be scheduled to mutually agreed time bound programme, which should not exceed 8 -10 months from the date of signing of contract.

iii. SITE CONDITIONS:

Altitude above Mean Sea Level (Meters) : __80______

| Climate data for Biratnagar Airport (1981-2010) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year |
| Average high °C (°F) | 22.7 (72.9) | 26.1 (79) | 30.9 (87.6) | 33.9 (93) | 33.3 (91.9) | 32.9 (91.2) | 32.1 (89.8) | 32.5 (90.5) | 32.1 (89.8) | 31.6 (88.9) | 29.3 (84.7) | 25.4 (77.7) | 30.23 (86.42) |
| Average low °C (°F) | 9.0 (48.2) | 11.1 (52) | 15.6 (60.1) | 20.4 (68.7) | 23.3 (73.9) | 25.2 (77.4) | 25.6 (78.1) | 25.8 (78.4) | 24.7 (76.5) | 21.1 (70) | 15.3 (59.5) | 10.5 (50.9) | 18.97 (66.14) |
| Precipitation mm (inches) | 11.7 (0.461) | 13.2 (0.52) | 13.2 (0.52) | 53.1 (2.091) | 186.0 (7.323) | 302.4 (11.906) | 530.8 (20.898) | 378.3 (14.894) | 298.8 (11.764) | 91.8 (3.614) | 5.9 (0.232) | 6.6 (0.26) | 1,891.8 (74.483) |
| Source: Department of Hydrology and Meteorology (Nepal) |  |  |  |  |  |  |  |  |  |  |  |  |  |

iv. SITE ADDRESS:

Biratnagar Milk Supply Scheme, Kanchanbari, Biratnagar, Nepal

2. INSTRUCTION

- Bidders are required to structure the presentation of the technical section of their bids..

- All technical data required by the tender is to be provided in the format given in the respective sub-section. If no format is given for any item the bidder may submit bid in their format.

- Any bidder not following the required bid document structure of presenting technical data that is not in the required format is liable to be deemed nonresponsive.

BID STRUCTURE OF TECHNICAL SECTION

- The technical section of the bid is to be structured in the same order as Tender Document. Each statement is to be numbered with the same Sub-section as in the Tender Document. Every page of the technical section of the bid is to be numbered as per section 5, schedule of requirements.

- The bidder is to cover each requirement by statements, technical data and descriptive material and, in particular to detail.

SUB- SECTION 1 : INTRODUCTION

Preamble

The bidder is to describe his technical proposal in details, stating the processes and systems, which he has, applies in designing the plant. Also to highlight any special technical innovations that the bidder proposes to include in the plant that will improve the performance, reduce operating cost or improve product quality. The “Preamble” should commence at the start of the process and work logically through the process. Any such highlights should be cross-referenced with the Bid sub-Section and paragraph number to which they apply.

SUB- SECTION 2 :	ACCEPTANCE OF WORKING CONDITION

A statement is required accepting the “working Conditions” that have been described in Tender.

SUB-SECTION 3:	BASIS OF DESIGN

The bidder is to require to follow the Basic of Design in the tender, and indicate clearly where additional processes or alternative processes of equipment are considered to be necessary or desirable to achieve optimum plant operation efficiency, optimum product quality within the standards specified, and optimum plant operation convenience. Under the utilities sections quantified the peak and daily loads of each utility and cross-reference this two service load histogram data to be provided with this bid.

SUB-SECTION 4: RESPONSIBILITIES

To be submitted as per GGC clause 16 & 17

Responsibilities of the Bidder

The bidder is required to specifically state his acceptance or non-acceptance of each clause in this sub-section.

Responsibilities of Client

The bidder is required to state here any additional responsibilities that he consider that are to be borne by Client besides those described in the tender.

SUB SECTION 5:	PROJECT MANAGEMENT

• Time Schedule

The bidder is to state in this subsection the proposed programme of implementation from receipt of order to commencement of product trials, to be provided as per Sub - Section.

• Management Team

The bidder is to detail the makeup of the management team in terms of designation, accordance with this Sub - Section of the tender. Also to quantify the support that will be given by foreign collaborators, with designation and man months of attendance in Nepal and at site.

This bidder is to ensure that the following Sub - Sections are fully detained and quantify the duration and manpower supplied to each.

• Commissioning

• Product trials

• Training

SUB-SECTION 6:	TECHNICAL SPECIFICATIONS

The bidder is required to follow the sequence of the tender Document and to make a statement on each paragraph. Do not leave any item without a clarify statement.

SUB-SECTION 7:	BATTERY LIMIT

Supplier will be responsible to undertake all the works involved in completing the project within the battery limits

SUB-SECTION 8:Process Performance and Consumption Guarantee

The bidder is required to specifically state his acceptance or non-acceptance of the clause in this sub-section. Non acceptance is deemed non-responsive.

SUB-SECTION 9:	SPARE PARTS

The bidder is to state and provide all the documents required as per section 3 evaluation and qualification criteria.

SUB-SECTION 10:	WARRANTY

The bidder should accept the warranty terms and conditions mentioned in GCC 30.

SUB-SECTION 11:	TOOLS, MANUALS AND CATALOGUES

To be submitted as per sub-section.

SUB-SECTION 12 : TRAINING

To be submitted as per section 3 (Evaluation & Qualification Criteria).

SUB-SECTION 13 : DRAWINGS, DATA & DOCUMENTS

The list of drawings and technical documents required for technical evaluation should be included. These should include a number of data sheet formats to be completed by the bidder. The completion of this format is mandatory.

##### Sub – Section 3

##### BASIS of DESIGN

INTRODUCTION

In general the plant is proposed to be modified / revamped based on the following design consideration;

- The SMP powder and dairy whitener produced shall be of good quality and with minimum

modifications.

- Minimum Energy consumption & Product losses

- Maximum utilization of existing equipments.

This section defines the overall processing plant and utilities parameters on which the modification / revamping should be based. Bidders should take into account all relevant local conditions while offering plant and equipment.

EVAPORATOR PLANT

The proposed Evaporator Plant expansion is to be designed for manufacturing 6 MT of SMP per day. The milk being fed in the Powder Plant contains about 8 % TS at a maximum temperature of 5 deg C

The existing plant has the following features:

- Capable to produce 6 MT per day of Skimmed Milk Powder.

Existing Evaporation Plant

- 2 effect falling film type evaporation system.

- External pre-heaters installed with calandria.

- Surface Condenser with cooling tower as cooling media.

- Year of design / installation May 1994 of M/s RICA-TEC A/S Denmark

Following are the design data for evaporator plant;

- No. Of Effect: 2 FF type Calandria with Vapor separator & pre-heater arrangement.

- Feed Rate: 2000 Kg/Hr. at 8. % TS at 5 Deg. C.

- Evaporation rate: 1650 Kg/Hr.

- Conc. Outlet: 350 Kg/Hr. with 45 % TS at 43 Deg. C.

- Temperature Profile: 80 -70 – 45 Deg. C

- Pasteurizing temperature: 90 Deg. C

- Steam to Thermo Compressor: 700 Kg/Hr. at 8 Kg/cm2 g Pressure.

- Condenser Water: 25 M3 /Hr. with 32 Deg. C in & 40 Deg. C out temperature.

- Total Power Consumption: 30 HP

- Pre- heater steam consumption: 50 Kg/Hr.

- Calandria 1 Tubes: 51 mm dia, 1.2 mm thk. 12 M Length. 43 Nos.(21+13+9)

- Calandria 2 Tubes: 51 mm dia, 1.2 mm thk. 12M Length.17 Nos.(7+5+3+2)

Following are the suggested modifications to achieve the desired output as mentioned in table below;

- Milk shall be concentrated from 8% to 23 % in membrane concentrate plant.

- Concentrate of 23 % shall be further concentrated by existing plant to 45 to 48 %.

- There should be minimum possible modification in the existing plant. We feel only distribution plates and the thermo compressor may require minor modifications. Please see the details further.

- The existing plant PID is attached here with layout for information. .

Expected design technical data

|  |  | Design Basis |
| --- | --- | --- |
|  | PRODUCT | SMP |
|  | Capacity (MT per day) | 6 |
|  | Configuration | As stated above |
| 1 | Feed |  |
|  | Kg/Hr. | 4000 ( AVG ) -5000 max |
|  | % TS (Minimum) | 8. % |
|  | Deg. C (Maximum) | 10 |
|  | Maximum Heating to 0 C | 90 |
| 2 | Concentrate |  |
|  | Kg/Hr. | 711 |
|  | % TS | 45 |
|  | Deg. C (Maximum) | 48 to 50 |
| 3 | Water Evaporation | As required |
| 4 | Steam consumption (Kg/Hr.) at 6 Kg/cm2 dry saturated | No change |
| 5 | Cooling Water |  |
|  | M3/Hr. | 25 |
|  | In/Out | 32/40 |
| 6 | Power | To be calculate by bidder |

1.	DRYER PLANT

The existing plant consist of;

- Single stage Spray Dryer with nozzle atomization.

- Powder separation is done by Cyclone. The powder is collected from the cyclone bottom and fed to vibro cooler outlet of vibro is fed to  on line sifter and is packed manually in 25 kgs  craft paper bags

The plant design data are as follows;

- Concentrate: 350 Kg/Hr. at 45 % TS at 40 Deg C.

- Evaporation: 186 Kg/Hr.

- Powder: 164 Kg/Hr.

- Inlet Air Temp: 185  to 190 Deg. C

- Outlet Air Temp: 83 - 85 Deg C.

- Chamber outlet powder Temp: 73 Deg. C

- Powder Temp. after conveying before bagging: 27 Deg. C

- Drying Air: 6000 to 7000 M3/Hr.

- High pr pump -450 l/hr. 300 bar  motor of 5.5 KW 725 rpm

- Cooling Air: 1250 M3/Hr. at 250 mmWC

- Atomizer Details Delavan  nozzle 1 no

- Drying Chamber Details

- Diameter: 3.5 M

- Height: 7.75 M

- Outlet Duct Diameter: 630 mm

- Main Cyclone dia. 1260 mm ,

- Steam Consumption: 360 Kg/Hr. up to 145 deg further heated through electric heater.

Expected design technical data

|  |  | Design Basis |
| --- | --- | --- |
| 1 | PRODUCT | SMP |
|  | Capacity (MT Per day) | 6.0 |
|  | Configuration | Single stage |
| 2 | Concentrate |  |
|  | Kg/Hr | 711 |
|  | % TS (Maximum) | 45 |
|  | Deg. C (Maximum) | 52 |
| 3 | Powder |  |
|  | Kg/Hr | 335 |
|  | Deg. C | Ambient |
| 4 | Steam Consumption | To be calculate by bidder. Only on steam. No electrical heating. |
| 6 | Power | To be calculate by bidder |

Expectations after modifications in powder plant:

- The plant should be capable of producing 6 MT per day of Skimmed milk powder and also capable of producing dairy whitener.

- The plat should be designed for minimum utility & production cost.

- Consistent product quality & reliability of operation.

- The output quality and stack losses of the Skimmed Milk Powder should be as follows:

Moisture Content		-	4% (Maximum)

Stack loss 		-	2.5 % (Maximum)

Solubility		-	2.0% (Maximum)

Scorched Particles	-	22.5 mg (Maximum disc C)

Bulk Density		-	0.6 – 0.8 gr/cm3

- The husk fired boiler is 4000 kg/hr of 10 Bar (INdCON Make) and should be synchronized with the capacity of the plant, the expected suggested modification is attached.

- The list of the drawings is attached with the tender. Bidder has to submit the revised drawing incorporating the scheme proposed by him including P & Ids.

Note : The Bidder / Supplier should visit the plant and who are capable of producing the required SMP output and dairy whitener should only participate in the tender.

Modification of the existing husk boiler in proper FBC working pressure maximum 13 Kg/cm²

| Work and supply description |  |  |
| --- | --- | --- |
| 1.0 | High pressure feed pump. Pump mode:- CR_-5-36, Make :- GRUNDFOS Flow 4.8 M³/hr @ 210 MLC head, Power :- 5.5 KW | 2 Nos |
| 2.0 | High pressure safety vale | 2 Nos |
| 3.0 | High pressure switch | 1 No |
| 4.0 | New FBC furnace systems with air plenum chamber and FBC nozzle, | 1 Set |
| 5.0 | Fuel feeding pneumatic speeder, | 1 Set |
| 6.0 | Screw feeder with gear motor, 2 HP motor | 1 Set |
| 7.0 | SFD fan with motor, 2 HP motor | 1 Set |
| 8.0 | High pressure FD fan 20 HP motor | 1 Set |
| 9.0 | Refectories work modification and supply as per new requirement, | 1 Set |
| 10.0 | Modification in control panel systems | 1 Set |

##### Sub Section 5

##### Project Management

1 TIIME SCHEDULE

1.1	Project execution shall be scheduled to mutually agreed time bound program, which should not exceed 8 -10 months from the date of signing of contract along with payment terms to commencement of product trials and service load trials. The Project Manager of bidder will provide the Project Manager of the Purchaser with monthly expediting and progress reports, which clearly indicate the actual vs., planned progress and the new likely completion dates of supply, erection, and commissioning and product trials.

1.2	The project-staffing pattern shall be submitted before commencement of work and should include sufficient personnel to meet the execution time schedule.

2.   BIDDERS MANAGEMENT TEAM

2.1 	A Project Manager who shall be adequately experienced in projects of similar magnitude and type shall head a competent executive team.

Reputed experts in various fields who shall be responsible for satisfactory execution of the project shall assist the Project Manager. He shall be responsible for overall implementation of the project, from commencement to final takeover of the plant.

2.2 	A Project Engineer shall be appointed for day to day operation and coordination, and to ensure successful and satisfactory design, procurement, manufacture, inspection, erection, testing and commissioning of all the equipment/facilities/systems within the time bound schedule.

2.3 	The Project Manager and Project Engineer shall attend technical and review meeting between various parties involved in the project, and ensure implementation of all decision taken in the meetings.

2.4 	The Project Manager shall also be responsible for detailed material accounting at site and management of project materials and equipment stored at site.

2.5 	The Purchaser will nominate a Project Manger with whom the Project Manager of the supplier shall communicate/co-ordinate.

2.6 	For smooth execution of the project, a team of Project Manager and Key Personnel shall remain consistent throughout the execution period.

2.7 	The Bidders Project Manager in consultation and approval of the purchaser project manager can   take on-spot decision with regards to:

• Minor modification in layout and execution programme to suit local condition.

• To purchase essential materials from local market to avoid delays.

3.  APPROVAL

3.1 	Purchaser shall give approval on technical documentation within 7 working days after submission. Amendments, which are not in the original scope of work or due to changes in concept, shall be taken up by the supplier as per mutually agreed and decided before execution, and shall be binding on the supplier.

3.2 	Supplier shall obtain approval for purchase of specific makes of equipment whose makes are not mentioned in his offer. If two or more makes of equipment are mentioned in the form of alternatives in the approved list, the purchaser shall select any one of the particular make from the approved list after mutual discussions with the Supplier.

4.   INSPECTION

4.1 	For indigenous items, the suppliers shall invite Purchaser for inspection and preliminary testing. Inspection may be required at various stages of manufacture/assembly for some items. The Purchaser will arrange to complete such inspection as maybe necessary along with clearance within 10 days from the date of intimation by the supplier.

4.2 	For imported items SCC 15.2 clause will be applied for inspection at the cost of Bidders.

4.3 SITE WORK AND INSTALLATION

4.3.1 Protection of electronic equipment.

It is the responsibility of the bidder to ensure that all electronic equipment and control system shall be fully protected against hostile environment, humidity, heat and dust that will be encountered during storage and installation.

4.3.2 Power supplies.

Power supply at Dairy is normally very stable, but the bidder is responsible to ensure that delicate electronic equipment used during construction, such as welding machine, testing devices etc. are protected against damage from mains supply. In the event of a major power failure in the system, it shall be the responsibility of the bidder to hire a diesel generator if this proves to be necessary.

4.4 COMMISSIONING

4.4.1 After satisfactory erection and testing, a competent team shall be deputed to commission the plant and to run product trials and to establish performance parameters.

5.5 PRODUCT TRIAL AND PERFORMANCE GUARANTEE

5.5.1 On completion of the Commissioning period, the plant will be operated at full capacity to the satisfaction of the Project Authority for a period of seven days on the designed product.

5.5.2 If shut down occurs due to External Force Majeure reasons after 16 hours of operation in any day, this shall be considered as a full day of testing. If at less than 16 hours of operation, the trials shall be continued for an additional full day.

5.5.3 Performance Guarantee: Performance and services consumption guarantees, and the relevant penalties for not meeting the rated capacities and efficiencies are covered in the tender.

##### Sub – Section 6

##### TECHNICAL specifications

Brief specifications of equipments:

EVAPORATING PLANT:

REVERSE OSMOSIS SYSTEM FOR MILK CONCENTRATE

PROCESS DESIGN

Mass Balance for Concentration for Standardized Cow’s/Buffalo Milk

Feed Rate 		: 	5000 Liters/hr.

Initial Solid 		: 	8%

Final Solid 		: 	23%

Concentrate Rate 		: 	1,740Liters/hr.

Permeate Rate		:	 3,260 Liters/hr.

The plant is designed to operate in a continuous mode and is based on 20-hr/day operation on product and 4 hours of CIP. The systems will be built to meet current 3A Standards. Usually the recovery is calculated on RO water systems.

The feed material will be introduced into the plant on a continuous basis while the concentrate and Permeate will be continuously withdrawn from the plant. Processing conditions will be controlled Automatically from the control system. The feed rate will be pre-set and will remain constant over 20 hours. As the feed passes through the successive RO arrays, it is progressively concentrated until the product of the desired composition is reached in the last array. In this manner, the concentrate will be continuously removed from the plant at the pre-set concentration level.

The RO Polisher plant is designed for cleaning in place. Capabilities are provided in the control system with the appropriate valves for circulation of a cleaning agent followed by a water rinse.

The steps involved in the cleaning cycles will be timed and sequenced automatically by the supplied PLC control system.

Automatic dosing system

  - Addition of cleaning chemicals

  - Heating of cleaning solution

  - Circulation of wash

  - Water flush (at beginning of CIP and between each cleaning step.

# EQUIPMENT SPECIFICATIONS

| S.No. | Equipment | Quantity |
| --- | --- | --- |
| 1. | FEED SECTION The feed section is designed to provide adequate flow to the RO Polisher plant during both production and CIP. This section consists of: Set of Valves: Comes with flow switches and control tops Feed Balance Tank Sock Filters Sock filters arrangement designed to prevent foreign material from entering into the RO plant. Air actuated valves with flow switches are provided to allow automatic switching of filters from the control panel Pre-Feed Pump and Feed Pump To provide adequate feed flow at desired pressure during production and CIP. CIP Shell & Tube Heat Exchanger The heat exchanger is of sanitary standards and is used to maintain the cleaning temperature by means of steam. Pressure Gauges/Pressure Transmitters Temperature Transmitter Sample Valve To sample feed Set of Stainless Steel Pipes and Fittings | 01 Lot |
| 2. | REVERSE OSMOSIS ARRAYS Arrays Consists of stainless steel housings/vessels and membranes in different arrays Pressure Gauges/Pressure Transmitters Set of Stainless Steel Pipes and Fittings Completing the total recirculation loop section, inclusive of the corresponding pipe connections between the arrays. | 01 Lot |
| 3. | CONCENTRATE SECTION To direct the concentrate to either downstream processing, drain or recycled to feed balance tank. This section consists of: Set of Valves Comes with flow switches and control tops Sample Valve To sample the concentrate. Pressure Gauges | 01 Lot |
| 4. | PERMEATE SECTION To direct the permeate to either downstream processing, drain or recycled to feed balance tank. This section consists of: Set of Valves Comes with flow switches and control tops Flow meter(s) Rota meter type, to measure permeates flow in array. Sample Valve(s) To sample permeate from each array. Set of Stainless Steel Piping and Fittings | 01 Lot |
| 5. | FRAME For mounting of system vessels, valves, solenoid boxes, etc. Should be common for RO concentration of raw milk and RO polisher. | 01 Lot |
| 6. | CONTROLS The controls for the RO polisher are included in the PLC system designed for the RO system. | 01 Lot |
|  | MAKE : GEA / TETRAPAK / NIRO / APV EU/US or other EU/US equivalent company. |  |

# BALANCING EQUIPMENT FOR CONCENTRATE STORAGE AND DISPATCH

| S.No. | Equipment | Quantity |
| --- | --- | --- |
| 1. | CONCENTRATE BUFFER TANK Capacity : 3 KL Material : a) Inner shell - 2 mm AISI 304 b) Outer cladding - 1.6 to 2 mm AISI 304 Finish : 150 grit Insulation : PUF- 15 mm, Thermocole 2 layers of 50 mm each. Ports and fittings: Inlet / outlet, CIP spray ball, high low level sensors, temperature sensor, agitator, level transmitter and manhole. Proximity switches for manhole indication. Instruments : RTD for temperature indication on MMI, level switch for high & low level & interlock, Level transmitter for liquid level indication on MMI, proximity switch for man way status indication & interlock. The Level Switch shall be of sanitary type. Level Transmitter shall be of digital type 24 VDC & 4 – 20 million output, 2 wire system (Hydrostatic Remote type ) There should be at least three level defined for controlling of agitator ON/OFF (low level), high level alarm & very high level alarm to avoid the spillage of product. Painting : All the mild steel stiffeners used in the construction of the equipment shall be painted with two coats of epoxy primer after through de-rusting. | 01 No. |
| 2. | CONCENTRATE TRANSFER PUMP Capacity : 5 KLPH Type : Centrifugal Fittings : Quick opening sanitary fittings Material : AISI 316 Coupling : Mono-block Mounting : Free standing with adjustable SS ball feet Shaft sealing : Mechanical shaft seal Gasket : Nitrile rubber Shroud : AISI 304 Motor : 415V, AC, 3 phase, 50 Hz. Squirrel cage induction motor with TEFC/IP 55 Enclosure | 1 No. |
| 3. | CONCENTRATE MILK CHILLER Capacity : 5 KLPH Plate Thickness : 0.6 MM Type : Plate heat exchanger MOC : SS 316 Pressed plates with SS 304 cladded frame Gaskets : Snap on nitrile rubber gaskets Accessories : Temp. probes on all inlet & outlet connections Duty : 10°C to 3°C Chilled water : 30 KLPH at 1.5 Deg C Duty : To chill concentrated milk to 3 Deg C by chilled water at 1.5 Deg. C FUNCTIONAL REQUIREMENT The Plate Heat Exchanger would be used for chilling concentrated milk with chilled water. DESIGN REQUIREMENTS Capacity : 5 LPH Milk composition : 23 % TS Design Parameters : Milk feed temperature :10 deg. Celsius Milk discharge temperature : 4 deg. Celsius Chilled water feed temp. : 2.0 deg. Celsius Maximum pressure drop : 8 MWC on product side 12 MWC on chilled water side Test pressure : 8 bar Finish : All welding joints are to be ground smoothly and finish to 150 grits. All stainless surfaces are to be polished to 150 grits. SCOPE OF SUPPLY Plates : Plates shall be made from Stainless Steel confirming to AISI – 316, shall be of sanitary design. All milk contact and exterior surface shall be easily accessible or readily removable for cleaning and inspection purpose. Gasket : The sealing gasket must ensure complete sealing and prevent any cross leakage between product and service liquids. Gasket shall be of Nitrile material and Clip on type. It shall be continuously bonded to the heat transfer surface. Frame : MS with SS 304 cladding ACCESSORIES Inlet / Outlets : The inlet and out lets for chilled water and products shall be provided with complete stainless steel (AISI – 304) SMS union. Thermo well : Stainless Steel (AISI 304) pocket for thermometer on inlets and out lets. Each pocket shall be complete with stainless steel (AISI –304) guard of at least 200 mm length for mounting thermometer sensors. Ball feet : The frame shall be provided with adjustable stainless steel ball feet with provision for height adjustment of 50mm. | 01 No. |
| 4. | CIP RETURN PUMP Capacity : 5KLPH Type : Self priming, centrifugal. Duty : To return CIP solution MOC : Liquid contact parts in SS 316 Head : 25 MWC | 01 No. |
| 5. | TANKER LOADING HOSE WITH FITTINGS Type : Crush proof reinforced plastic spiral construction flexible hose with vulcanized SS end connection & fittings, resistant to CIP cleaning liquids up to 1200C. Size : 76.2 mm bore size Length : 6 m long/suitable with SS 304 stand Material : Food grade Each set of hoses shall consist of required no. of hoses and fittings required for unloading of one tanker. | 01 Set |
| 6. | TANKER LOADING PUMP Capacity : 5 KLPH Type : Centrifugal Fittings : Quick opening sanitary fittings Material : AISI 316 Coupling : Mono-block Mounting : Free standing with adjustable SS ball feet Shaft sealing : Mechanical shaft seal Gasket : Nitrile rubber Shroud : AISI 304 Motor : 415V, AC, 3 phase, 50 Hz. Squirrel cage induction motor with TEFC/IP 55 Enclosure | 01 No. |
| 7. | MASS FLOW METER Capacity : 5 KLPH (Local Totalizer to be displayed in the field and taken into account as cumulative milk mass dispatch viz., tanker wise, day wise & so on in SCADA……) | 01 No. |
| 8. | FLOW PLATE FOR TANKER LOADING HOSE Type : Floor Mounted No. of Ports : Suitable Material : SS 304 | 01 No. |
| 9. | DISPATCH CONTROL PANEL – MMI Type : Wall mounted Material : SS 304 enclosure for Hosing LOP (Local operator panel, Push Button Station) Controls : As described under "Milk Reception" Enclosure : Lockable waterproof enclosure | 01 Set |
| 10. | ## SS PIPES, VALVES AND FITTINGS | 01 lot |
| 10.1 | SS (PRODUCT / CIP) PIPES & FITTINGS Type : TIG welded; annealed and de-scaled tubes shall be manufactured as per the standard ASTM- A270. Outer surface of the tubes shall be with dairy finish and inner surface shall be pickled as per dairy standard Material of construction and thickness: All the pipes unless otherwise stated shall confirms to AISI 304. The average wall thickness of tubes shall be 1.2 mm up to 76mm OD and 1.6 mm for diameters above 76 mm OD. The wall thickness at any point shall not vary more than 5% over and under from the average wall thickness specified. The ovality on the open ends shall be within the permissible limit specified in the ASTM A270. Support RHS shall have wall thickness of 2.5 mm for size up to 100 x 50 mm and above it shall be 3 mm thick. | 01 lot |
| 10.2 | ## VALVES | 01 Lot |
| 10.2.1 | SANITARY PNEUMATIC SEAT VALVES Type : Two ways / three way pneumatically operated sanitary valves of mix-proof (self cleaning), ON- OFF seat valves, flow diversion valves, shall be provided with AISI connectivity. All the valve battery valves shall be of self cleaning type mix proof valves having 3 solenoid (each). Material : AISI 316 Sealing : Positive Controls :Electrically/electronically operated The Pneumatic valves shall have the following features to cater to fulfill the above functional requirements: Housing shall be ball shaped for the ideal flow characteristics to ensure 100% cleanability by CIP. Housing closed by cover plates shall not create a sump or dead corners. Housing interconnections shall be by detachable type clamp connection. The seals such as housing seals, stem seals and disc seals shall be flush mounted. Valves shall have low/very low susceptibility for the pressure surge. The valve shall have the short leakage outlet to recognize the leakage immediately. Valve shall have open lantern installed between the actuator and the product area of the valve to assure that leakages occurring at the stem seal shall be immediately visible and also shall act as a protection against overheating of the actuator. Mix proof valves shall be used wherever the CIP and the process liquids are inter-crossing in the piping system. The CIP of the isolation area is possible and also the leakage shall be easily identified. The Supplier to quantify the number of transmitters required, based on the tender as well as functional requirement & offer accordingly. All pneumatic connections from the header up to individual valves shall be of SS-304 through suitable SS-304 distribution headers connected with FRL units/moisture separator etc. 500 mm pneumatic flexible tubing to be considered at control unit side for all valves. The pneumatic valves shall have required diagnostic features, to be monitored from HMI & recorded in the system. The valves shall also be configurable from the HMI/operator console. | 01 Lot |
| 10.2.2 | SS PNEUMATIC VALVES (All Types other than Mix Proof Valves) In addition to cream & CIP lines, SS pneumatic valves shall also be provided for water & air connections (after tapping from main header) to process application. The valves shall be sanitary type. All pneumatic valves in product & CIP lines shall be piston type seat valves. Required number of valves shall be finalized during detail engineering as per tender/functional requirement & standard engineering practice. As per general description given in basis of design, all pneumatic valves must have ON/OFF & fault feedback facility. | 01 Lot |
| 10.2.3 | SS PNEUMATIC MIX PROOF VALVES As per general description given in basis of design. All mix proof valves shall have 3 solenoids. Required number of valves to be finalized during detail engineering as per tender/functional requirement & standard engineering practice. As per general description given in basis of design, all pneumatic valves must have ON/OFF & fault feedback facility. | 01 Lot |
| 10.2.4 | SS MANUAL VALVE AND FITTINGS Required number of valves to be finalized during detail engineering as per tender/functional requirement & standard engineering practice. a. Manual butter fly Valve : The butter fly valve shall be of sanitary design and all liquid contacting parts shall confirm to AISI 316. The valve sealing gasket shall be EPDM /Nitrile rubber material suitable for hot water sterilization temperature of 100 Deg. Celsius and hot acid and lye solution of 2% concentration at 85 Deg. Celsius. The valve shall be provided with SS handle. The valve shall be with plain ends shall be suitable for direct welding on the pipes. b) Non Return Valve: The non return valve shall be of sanitary design and all liquid contacting parts shall confirm to AISI 304. The valve sealing gasket shall be EPDM / Nitrile rubber material suitable for hot water sterilization temperature of 100 Deg. Celsius and hot acid and lye solution of 2% concentration at 85 Deg. Celsius. The non return valve shall be with plain ends shall be suitable for direct welding on the pipes. c) Unions : All the parts unless otherwise specified shall be made out of investment casting using AISI 304 material The union shall be complete with liner, male part, nut and sealing ring (neoprene food grade rubber gasket). The liner and male parts shall be suitable for expansion joints. All the inside as well as outside surface of the union shall be with dairy finish. d) Bend, Tee, Elbow : These fittings shall be made out of AISI 304 unless otherwise specified, process tube, TIG welded, annealed, de-scaled having outer surface mirror polished and inside pickled, manufactured as per ASTM A270. The thickness of the fittings made from the tube section shall not be less than 1.6 mm up to 76 mm dia and shall not be less than 2.0 mm for above 76 mm dia. The wall thickness at any point shall not vary more than 12.5% over and under from the average wall thickness specified. Bends and elbows shall be free from wrinkles. Tee shall have uniform flaring on the branch connection. The ovality on the open ends shall be within the permissible limit specified in the ASTM A270. e)Pipe Clamps : Shall be quick open able type of sturdy design. MOC: AISI SS-304 2.5 mm thick up to 101mm dia.pipe. | 01 Lot |
| 10.2.5 | Actuated Butterfly Valves | 01 Lot |
| 10.2.6 | ## Other Process Valves | 01 Lot |
| 10.2.7 | Manual and Actuated Utility Valves | 01 Lot |
| 10.3 | SS PIPING (Product/CIP) SUPPORT Other details as per general description given. All process product & CIP pipe supports inside the plant & open corridor shall be of SS-304box section (2.5 mm thick). SS pipe with outer dairy finish would be acceptable. Support RHS shall have wall thickness of 2.5 mm for size up to 100 x 50 mm and above it shall be 3 mm thick | 01 Lot |
| 11. | ## MCC PANEL AND ELECTRICALS | 1 Lot |
| 12. | ## ELECTRICALS |  |
| 12.1 | MOTOR CONTROL CENTERS Type : Suitable for indoor installation with a provision for expansion. Feeders : Incoming feeders from both the sections of power control center to MCC for essential loads. All outgoing feeders shall have isolation facility, fuse, contactor, thermal/magnetic overload protection, necessary operating controls etc. All feeders above 10 HP shall have Star Delta starter with ammeters. Instruments : Process status transmitter up to central control management system. All necessary interlocks and controls. | 01 Lot |
| 12.2 | POWDER AND CONTROL CABLES All LT power cables shall be weatherproof, PVC sheathed, steel armored, PVC coated, aluminum conductor cables. Cable less than 4 sq.mm. shall not be used. All control cables laid in cable trunks shall be PVC sheathed, steel armored, PVC coated copper conductor cables. Power and control cables shall be terminated with compression glands at either end. | 01 Lot |
| 12.3 | REMOTE CONTROL PANEL Shall be provided wherever required. | 01 Lot |
| 12.4 | EARTHING To provide earth pits and Earthing cables to all sections of the plant with a max. earth resistance of one ohm or as per the regulations of local Electrical Inspectorate. The earth pits and Earthing system of instrumentation, computers and controls shall not share the Earthing system of electrical power equipment. | 01 Lot |
| 12.5 | MISCELLANEOUS ITEMS - GI cable trays - Isolators - Rubber mats - Conduits - Other items - All spare parts needed for trouble-free operation of the Unit | 01 lot |

REVERSE OSMOSIS SYSTEM ON BOREWELL WATER (RO PLANT)

PROCESS DESIGN

The RO plant to process 2 KLPH permeate from the Borewell with 70% recovery. The plant is designed to operate in a continuous mode and is based on 22-hr/day operation on borewell and should meet the engineering standard..

The design basis for the system should be as per the raw water analysis enclosed. However the high pressure pump should be designed to take care of TDS upto 1000ppm

The RO plant is designed for cleaning in place. Capabilities are provided in the control system with the appropriate valves for circulation of a cleaning agent followed by a water rinse.

EQUIPMENT SPECIFICATIONS

| S.No. | Equipment | Quantity |
| --- | --- | --- |
| 1. | FEED SECTION The feed section is designed to provide adequate flow to the RO plant during both production and CIP. This section consists of: Set of Valves: Feed Balance Tank Pre Filter : Sand Filter Sand filters arrangement designed to prevent foreign material from entering into the RO plant. The flow velocity of the filtration should be 10m/hr. The bottom collection should be strainer on button. The filter should be fabricated in Mild Steel duly epoxy painted from inside as outside with Top and bottom dish as flanged and shall should have on hand hole of 200mm on the side. | 01 Set |
| 2. | PRE-FEED PUMP AND FEED PUMP To provide adequate feed flow at desired pressure during production and CIP. ANTISCLANT DOSING SYSTEMS Electronic metering pump from seko/prominent/ ASIA LMI of capacity 05LPH@ 5BAR along with 100lit HDPE tank to be provided for dosing antisclant in the membranes. CARTRIDGE FILTER Filter Housing in 20” from PC/ SS316 with 5 micron melt blown filter in double open end should fitted on skid . The Filter element should be from Paul /Millipore/ GE Osmonics or equivalent. | 01 Set |
| 3. | MEMBRANE MODULE Skid in SS304 fitted with Membrane Housing, side port in 4” x 160” in GRP, complete with necessary piping and chemical dosing system, cartridge filter | 01 Set |
| 4. | HIGH PRESSURE PUMP Vertical multistage pump from the approved vendor is mounted on the skid with suitable pressure +15% buffer in pressure as per design on 1000ppm Load of salinity. | 01 No. |
| 5. | CIP SYSTEMS Membrane Cleaning systems should have a separate Cartridge Filter housing 20” from PC along with 150 to -200 LIT HDPE tank with necessary recirculation piping, valves connected to feed pump header. The loop for the return from permeate, reject water and CIP feed pump which is common as feed pump should be complete in all respect. Pressure Gauges/ Flow Meter (Rotameter)To measure pressure & flow at all sensitive points and inter stages of the R.O. module. Piping : All piping valves should be done in UPVC SCD 80 from Price/ASTRAL/George FISCHER however the valves to be provided from George fischer in UPVC | 01 Lot |
| 6. | FRAME For mounting of system vessels, valves, solenoid boxes, etc. | 01 No. |
| 7. | INSTRUMENTS AND CONTROLS The control system is provided for the automatic PLC control of production, displacement, cleaning, and flushing. | 01 Set |
| 8. | Standard / miscellaneous accessories and Equipments |  |
| 9. | MAKE : MANTRA MAKINA TURKEY / AQUATREAT SYSTEM & ENGINEERS ( MEGA ) / ION EXCHANGE /THERMAX , INDIA /OR EU/US Country. |  |

Proposed Scope of Supply for Modification of Existing Evaporating Plant

Existing Feed Rate: 2,000 kg/hr

| S. No. | Particulars | Unit | Data |
| --- | --- | --- | --- |
| 1.0 | Feed rate | lit/hr | 2,000 |
| 2.0 | Initial solids | % | 8.0 |
| 3.0 | Feed temperature | Deg C | 5 |
| 4.0 | Final solids | % | 45.0 |
| 5.0 | Product output | lit/hr | 355 |
| 6.0 | Water Evaporation | kg/hr | 1,645 |
| 7.0 | Steam consumption for main TVR @ 8 bar | kg/hr | 700 |
| 8.0 | Cooling water requirement | m3/hr | 25 |
| 9.0 | Air | - | Nominal |
| 10.0 | MOC of contact parts | - | SS 304 |
| 11.0 | Total electrical load installed (Kw) |  | 22.38 |
| 12.0 | Average use of power load (Kw) |  | 17.90 |

Proposed Feed Rate: 1,740 kg/hr

| S. No. | Particulars | Unit | Data |
| --- | --- | --- | --- |
| 1.0 | Feed rate | lit/hr | 1,740 |
| 2.0 | Initial solids | % | 23.0 |
| 3.0 | Feed temperature | Deg C | 5 |
| 4.0 | Final solids | % | 48.0 |
| 5.0 | Product output | lit/hr | 833 |
| 6.0 | Water Evaporation | kg/hr | 907 |
| 7.0 | Steam consumption at DSI @ 3.5 bar | kg/hr | 34 |
| 8.0 | Steam consumption for main TVR @ 9 bar | kg/hr | 363 |
| 9.0 | Cooling water requirement | m3/hr | 14 |
| 10.0 | Air | - | Nominal |
| 11.0 | MOC of contact parts | - | SS 304 |
| 12.0 | Total electrical load installed (Kw) |  | 26.78 |
| 13.0 | Average use of power load (Kw) |  | 21.42 |

| Sr. No. | Equipments | Quantity |
| --- | --- | --- |
| 1. | REGENERATIVE HEATER WITH FLASH VESSLE (One Stage) To heat the milk coming from the pre-heaters by the vapor generated through flashing. The heater is integrated with flash vessel as a single unit. The flash vessel section is also used for flash cooling of the pasteurized product provided with specially constructed tangential inlet connected to the regenerative heater of the heating section. The system should be complete with all standard accessories. MOC: SS 304 | 01 No. |
| 2. | TANGETIAL SWIRL HEATER ( Two Stage) To heat the milk to the required pasteurization temperature by tangential injection of filtered saturated steam in an on-line piping system. MOC:AISI 304 | 01 No. |
| 3. | HYDRO- CYCLONE To remove any burnt or suspended particle from condensed milk including drain valve. MOC: AISI 304 | 01 Set |
| 4. | THERMO VAPOR RE-COMPRESSOR Thermo Vapor compressor (TVR) shall be provided to compress and reefed a part of vapors generated in the second effect back to the first effect chest. Incoming steam shall be used for Compressing the vapors. MOC of Head: AISI 304 Mixing passage/diffuser : AISI 304 Motive nozzles: AISI 304 Steam chest: AISI 304 Flanges: CS | 01 No. |
| 5. | PRODUCT TRANSFER PUMP Centrifugal product pumps for transferring product through evaporating plant. Each pump should be equipped with open impeller and double mechanical seal box with sealing water connection. This item also includes replacement of existing pumps impellers incase it is decided to be use. MOC: AISI 304 | 03 Nos. |
| 6. | VACUUM PUMP Type : Water Ring, Double Stage Vacuum Pump Drive : TEFC Motor, direct coupled (flexible coupling) MOC : Cast Iron. Shaft Seal : Gland Packing Accessories: Common base frame, discharge silencer, non return valve, vacuum gauge, inlet water pressure gauge. | 02 Nos. |
| 7. | INSTRUMENTATION AND CONTROL PANEL An Instrument panel shall be of SS 304 It shall consist of | 01 Set. |
| i. | Mimic diagram of the Evaporator | - |
| ii. | Auto Feed Control ( Flow meter) with VFD in feed pump, magnetic flow meter & PID | - |
| iii. | Density meter | - |
| iv. | Steam Pressure Control Loop for Calandria TVR. • Pressure Transmitter • Pressure Controller • Steam Control valves with I/P Convertor • AFR, tubing & fitting | - |
| v. | Temperature Control Loop for DSI • Temperature Transmitter • Temperature Controller • Steam Control valves with I/P Convertor • AFR, tubing & fitting | - |
| vi. | Digital Temperature indicators • Cal Jackets • Vapor separators • Feed temperature • DSI and flash vessel temperature • Concentrate temperature | - |
| vii. | Local Instrumentation and Indicators Dial type Thermometer indicating temperature of • Cooling water Inlet / Outlet temperature, • First Effect calandria Chest, • All vapor separators (0 to 110°C). Dial type Pressure Gauge for TVR (0 to 10 bar g). Dial type vacuum gauge • For calandria chest, • For vapor separator, • For Condenser. | - |
| 8. | Cable , cable tray, earthing material & any modification in the existing MCC & miscellaneous jobs. | 01 Lot |
| 9. | SS Ducting | 01 Lot |
| 10. | MS Pipes, valves, fittings for steam, condensate & water lines. | 01 Lot |
| 11. | SS Pipes, valves & fittings | 01 Lot |
| 12. | The existing evaporating plant various stage all 9 NOS. pumps to be replaced | 01 Lot |
| 13. | All the defective ss pipes & fittings as well as utility valves shall be considered in supply. | 01 Lot |
| 14. | replacement of existing Evaporator safety valves. | 01 Lot |
| 15. | Miscellaneous job (any other defective parts & equipments) | 01 Lot |

Technical Specification & Parameters for Dryer

| S.No. | Particulars | Unit | Data |
| --- | --- | --- | --- |
| 1.0 | Feed rate | Kg/hr | 600 to 625 |
| 2.0 | Initial solids | % | 48 |
| 3.0 | Feed temperature | Deg C | 48 |
| 5.0 | Inlet air temperature | Deg C | 190 |
| 6.0 | Outlet air temperature | Deg C | 85 |
| 7.0 | Final moisture content of powder | % | 3.5 |
| 8.0 | Product output | Kg/hr | 300 min |
| 9.0 | Water Evaporation | Kg/hr | 325 |
| 10.0 | Steam consumption for dryers | Kg/hr | 964 |
| 11.0 | Chilled water requirement | m3/hr | 2 |
| 12.0 | MOC of contact parts | - | SS 304 |

Note: 1) Temperatures are indicative only.

| S.No | Equipments | Quantity |
| --- | --- | --- |
| 1.0 | FEED PIPES AND FITTINGS For the concentrate leading from feed pump to atomizer complete with necessary bends and fittings | 01 lot. |
| 2.0 | CONCENTRATE PREHEATER SYSTEM For preheating the feed product up to 75 Deg. C. temperature. The preheating system comprises of: -Shell & Tube pre-heater -Steam valves, pipes & fittings | 01 No. |
| 3.0 | BOOSTER PUMP WITH HIGH PRESSURE FEED PUMP ( Make: Nirosovia/FBE/APV or equivalent) WITH MOTOR Booster pump shall be centrifugal type with open impellor for pumping concentrate from the concentrate tank to HPP through filter. MOC SS 316 HPP shall be multi piston type to feed the concentrate to high pressure nozzles 3 nos. The pump shall be provided with necessary safety valve, local pressure gauges, electrical motor and other standard accessories. The pump speed should be regulated by variable speed drive. | 01 No. |
| 4.0 | AUTOMIZER ASSEMBLY WITH 1 No. NOZZLE MOC SS 304 For atomizer feed in to fine droplets of a concentrate of controllable and uniform size for obtaining optimum dryer performance and product characteristics. Complete with 3 sets of nozzles supporting units, manifold & pneumatically operated valves. Special tools for assembly of the nozzles atomizer and changing the nozzle orifice inserts are also included. Nozzle rod CIP stand and nozzle stand for cleaning of nozzles, all in SS 304 including tray & drain pipes. | 01 Lot. |
| 5.0 | DRYING CHAMBER SYSTEM |  |
| 5.1 | AIR DISPERSER AND COOLING SYSTEM New Air Disperser shall be placed in the center of existing chamber for introduction of drying air from the ceiling in to drying chamber. It will ensure uniform distribution of air in to chamber and also mixing of hot air and atomized particles in rigorously. All in SS 304. The air disperser shall be insulated and cladded with SS 304. Disperser cooling system shall consist of fan with motor, steam heater, temperature monitoring system with control valve, steam trap etc. | 01 No. |
| 5.2. | EXISTING CHAMBER Shall be added with Bustle at the end of cylindrical section of proper size and then connected to existing cone. All insulation and cladding included with hand / man hole covers for observation. There shall be four outlets for exhaust air of adequate size in SS 304. | 01 No. |
| 6.0 | Modification in cyclone if necessary | 01 Lot |
| 7.0 | Exhaust fan with motor with damper The fan shall be with variable frequency drive. | 01 Set |
| 8.0 | Fine return system Shall have blow through valve, root blower, dehumidifier, fine diversion valve and required pipes & fittings with valves and standard accessories. | 01 Set. |
| 9.0 | MODIFICATION OF VIBRO FLUDIZER The existing vibro fluidizer shall be converted to small heating & cooling section with filter, heating battery, fan, damper and ducting, where as for cooling existing equipments shall be used after conditioning. The VF exhaust ducts shall be connected with main dryer exhaust duct. | 01 No. |
| 10. | Safety System |  |
| i. | Over pressure relief panel Of the diaphragm type, placed in the cylindrical part of the multi-stage drying chamber and bag filter. Designed to burst at a certain air pressure in order to protect the chamber and bag filter. The diaphragm is fixed between flanges with bolts. The exhaust shall be vented into safe area. | 01 Set. |
| ii. | Fire extinguishing system for DC For the drying chamber, designed for water hosing of the total inner surface. The system comprises a set of nozzles placed in the chamber cylinder, connected to a ring-pipe with main valve and drain valve. The nozzles are flush with the inner surface during normal operation and are opened by the water pressure when the system is activated. A two-stage thermostat will be placed in the chamber outlet duct for detecting and signaling the preset temperature rise to the control panel. | 01 Set |
| iii. | Fire extinguishing system for VF For the Vibro-Fluidizer, designed for water hosing of the inner surface. The system comprises nozzle with main valve and drain valve and a two-stage thermostat to detect temperature rise beyond normal. The nozzle will be flush with the inner surface during normal operation and will open by the water pressure. The system will be connected to the control panel. | 01 Set |
| iv. | Fire water tank MOC : M.S This tank will be installed on top of Dryer building and used for buffer storage of water required for fire extinguishing. The tank shall be provided with necessary level switches for auto filling. The supply includes booster pump in CS construction for filling of fire water tank if required. | 01 No. |
| v. | Fire extinguishing pump Capacity : Suitable MOC : CI body with SS impeller | 01 No. |
| vi. | Control Panel for fire system | 01 Set |
| 11. | Instrumentation & Control System An Instrument panel shall be of SS 304 It shall consist of: | 01 Set |
| i. | Mimic diagram of the Dryer | - |
| ii. | Auto temperature control • For FBD heater Consisting of Temperature Sensor/ Transmitter, Temp. Controller, Steam valves with I/P Converter | - |
| iii. | 1 No. Auto feed control – VFD for high pressure Pump to control the feed with exhaust air temperature & PID | - |
| iv. | Auto Fire Extinguisher system | - |
| v. | Local Instruments - Pressure Gauges on Steam header - Vacuum gauge on feed pre-heater - Pressure Switch for Blow Through Valve - Pressure Transmitter on Drying Chamber for Alarm & exhaust Fan cut-off | - |
| vi. | Temp. Indicators, Range 0 to 100 Deg. C - for FBD hot air | - |
| vii. | Vacuum/ Differential Pressure indicator - For chamber - For cyclone - For FBD | - |
| 12.0 | Electricals, Cables, earth pit, starters cable tray, earthing material etc. | 01 Lot |
| 13.0 | Utility Pipes & Fittings Steam pipes and fittings Compressed air pipes and fittings Condensate pipes and fittings Chilled water pipes & fittings | 01 Lot |
| 14.0 | Electromagnetic hammers Electromagnetic hammers 10 nos (8 on dryer +2 nos on cyclone ) with control panel | 01 Lot |
| 15.0 | Quick moisture test machine. | 01 Set |
| 16.0 | Structural modification with consumable | 01 Lot |
| 17.0 | Miscellaneous Job | 01 Lot |

Technical Specifications

Scope of supply and installation of equipment for Dairy Whitener

| S.No | Equipment | Quantity |
| --- | --- | --- |
| 1. | SUGAR DISSOLVING VAT Dosing sugar manually Capacity: 500 lit. Material of Construction : Inner Shell : SS 304, 2.0 mm thk, Intermediate (Dimple Jacket): SS 304, 2.5 mm thk. Insulation : 100 mm Outer shell : SS 304, 2.0 mm thk It should be complete with : - High shear mixer with motor - Outlet connection with manual butterfly valve - CIP spray ball - Steam inlet connection to Jacket - Condensate drain from Jacket - Safety valve - Dial type pressure gauge - Thermo well - Air vent. | 01 No |
| 2. | SUGAR SYRUP TRANSFER PUMP MOC : SS 304 Type : Centrifugal Capacity : 500 LPH | 01 No |
| 3. | HOPPER MOC : SS 304 Capacity : 100 Lit. | 01 No |
| 4. | POUCH FILLING MACHINE FOR POWDER PRODUCT : SMP, WMP and Dairy Whitener PACK WEIGHTS : 200 gm., 500 gm. And 1000 gm. PACK STYLE : Center Sealed Pillow Pouch PACK SIZE/S : Web width for 1 Kg. : 440 mm Web Width for 500 gm. : 385 mm FILM : Heat Sealable Laminate NOMINAL OUTPUT : 42 to 47 packs/min for 200 gm. for Pillow pouch 35 to 42 packs/min for 500 gm. for Pillow pouch 30 to 35 packs/min for 1000 gm. for Pillow pouch DOSING SYSTEM : Servo Driven Auger Filler ACCURACY : For 200 g to 500 g 68% of the production will be within +/- 0.8% of the average weight. 95% of the production will be within +/- 1.6% of the average weight and 99% of the production will be within +/- 2.4% of the average weight. For 1000 gm. 68% of the production will be within +/- 0.5% of the average weight. 95% of the production will be within +/- 1.0% of the average weight and 99% of the production will be within +/- 1.5% of the average weight. Features : Quick Clamp devices for tool less changeover of forming set. - Packaging material draw down ( intermittent) with belts through separately driven AC geared motors, lubricated for life in IP54 enclosure and controlled by Digital frequency controller, for precise cycle operation of the draw down. Belt pressure adjustable pneumatically. - Basic Pneumatic equipment like Solenoid Valves, Pressure Regulators and Pneumatic Cylinders to perform Sealing, Knife Cut & Seal Cooling. - Horizontal jaw drive by pneumatic cylinder for reciprocating jaw motion. - Pneumatic longitudinal jaw movement. - Setting and adjustment for bag length through operator interface. - Film brake to steady the film during overprinting. - Semi-Automatic film tracking control to ensure that the film is material is maintained at the center of the collar. - Motorized movement of the web from the MMI. Unwinding Station - Mechanical - Packing Material unwind from a roll. - Mechanical Brake arrangement to ensure only the required quantity of film length is unwound. - Optimum tension on the film web to ensure smooth film motion. - Packaging Material Arbor with mechanically operated expansion shaft to hold film roll. - Arbor provided with scale and film roll stop for easy alignment of film. Roll Specifications Max. Roll Width : 525 mm Max. Roll Diameter : 500 mm Max. Roll Weight : 175 Kg. Max. Core Diameter : 76 mm Horizontal Sealing Jaw for Laminates For Max. Bag Width 250 mm. - Set of Front & Rear Sealing Jaws complete with pneumatically actuated knife, heaters and thermocouple. - Standard design V-groove in 1.5 mm pitch, Seam width 13.5 mm. - The integrated tool is capable of achieving Bottom Seal & the Top Seal of the next bag in a single cycle. Longitudinal Sealing Jaw for Laminates - Longitudinal Sealing tool suitable for laminates for vertical seal. - Jaw width 10 mm; Jaw length 400 mm. - Sealing tool complete with cartridge heater and thermo couple. Mark Sensor - Mark Sensor to sense eye mark on the foil for print registered bags. - Eye mark should be minimum of 8 mm width and should be in the contrasting color to the print layout. - Proper Registration of print is subject to the film/foil being printed as per our approved print layout. Control Panel - Control panel, attached to the right of the machine. - Operator interface OP-7 or equivalent. - The Operator Interface (HMI), temperature controllers, and machine control buttons including emergency stop are ergonomically laid out. - Component mounting plate is zinc plated. The complete panel is force ventilated with filters and fan. Mains ON/OFF switch located on the rear of the panel along with phase indicating lamps in Red, Yellow and Blue color, Main power cable connection through cable glands located at the bottom rear of the panel. - Wire terminations blocks are of Screw-Less Type (Spring Loaded) to ensure good electrical contact. - All wires and terminations in the panel are numbered. - 4 – Line display for monitoring machine data and operating status. Drive controls and settings through HMI. Plain English language display for machine speed, recipe parameters and error/fault screens. Counters for total number of bags. - 16-Bit high performance Siemens S7 226 PLC or Equivalent for programming and controlling machine functions. - Sealing Temperature regulation by Temperature controller with set point and actual value display. Individual control for each jaw. - Health checkup during start up - Programs for integration of filler and other optional features ordered with bagger. Static Charge Eliminator ( SCE ) - Required to eliminate static charge in film. - Controller for Static Charge Eliminator, mounted inside the machine frame. - To be used along with lonising ring. Gas Flushing Device - Purging Gas in the Forming Tube during the m/c cycle. - For displacing the air in the bag filling area, in order to prolong the shelf life of the product. - With flow control valve. - Suitable for applications other than powders. Block Bottom System - Include gusseting station. - For producing Gusseted & Block bottom bags. - Set of upper and lower tools pneumatically operated. - Operation synchronized with Jaw motion through a cam. - Gusset depth settable on machine. - Can be disabled if only a pillow has to be produced. - For producing block bottom bags. - Set of triangular formers for achieving the bottom fold. - Can be used only in conjunction with the gusseting unit. Bag Support – Pneumatically Operated. - Required for large bags. - To support the Bag, When product is being discharged. - Prevents seal opening due product weight. - May be required in smaller pack weights if very thin film is used. - Pneumatically operated to synchronize with filling. Over Printer – Hot Foil Contact Type. - For Overprinting batch code & other statutory details. - With electrically heated & thermostatically controlled print type holder. - Print transfer is through Hot Foil Ribbon. - Pneumatically operated & electrically synchronized in the machine cycle. - Print area 25 mm * 50 mm - Includes character set in brass - Numbers 0 to 9 (10 No’s) : 2 each - Vowel A,E,I,O,U ( 5 No’s) : 2 each - Consonants (21 No’s) : 1 each - (Alphabets other than Vowels) - Blank & ‘/’ : 2 each - Includes one ribbon reel. Printer Mounting Bracket for Hot foil Coder. - Mounting bracket designed for your printer. - Facility to position the printer head across the web of the film. Printer Positioning Roller Assembly. - Set of rollers with rack and pinion arrangement to adjust the position of overprint on the bag, along the length of the pouch. - Always needed when using print registered film. Format part for Laminate with provision for gas flushing. - For between 50 mm – 170 mm Bag Width - Bag Width - Comprising of Forming shoulder, holder, forming tube. - Provision for gas flushing inside the forming tube. - All parts in contact with product made of SS 304. Ionizing Ring - For removal of static charge. - To be used along with Static Charge Eliminator. - Required for each format size. Auger Filler SS 304 - For precise-=volume dosing of free-flowing/hard – to-dose, powdery or fine – granule products Standard Design Comprising : - Auger drive using AC Servomotor. Enclosure class IP 65 - Power transmission by toothed belts - Dosing hopper with quick-action closing, inspection opening. - Dosing hopper provided with N2 flushing points with plugs. - Mixer with separate drive using three-phase gear motor, enclosure class IP 54, switching to cyclic or continuous mode. - Single level sensor in feeding hopper for controlling the product feed linear screw. - Base column with height adjustment ( 200 mm ). - Aspiration connection with filter - Parts contacting the product are of stainless steel 304. - Dosing quantities input using monitor and keyboard of machine control unit Horizontal Screw Conveyor - Horizontal product feeding screw of diameter 150 mm with separate drive using 3-phase motor. - Enclosure class IP 54. In feed nozzle arranged above the swivel arbor to feed product to auger hopper. - Screw designed for gentle product handling complete in SS 304 execution. - Synchronizes product level in auger hopper, through level sensor. Enables maintenance of constant product height in the hopper. - Connecting piece to Auger hopper. - N2 flushing points. Auger Screw set (54 to 100 mm )For 1 Kg pack size - Machined Auger Screw from solid bar stock of SS 304 for additional size. - Pitch and diameter of the screw designed as per your product characteristics and fill weight. - Complete with Auger tube of SS 304 suitably finished to suit screw tolerance. - Pin type closure to minimize product dribbling at the end of the filling cycle. |  |
|  | FILLING MACHINE MAKE: HASSIAREDATRON/TETRA PACK/ OR EQUIVALENT |  |
| 5 | TABLE MOC : SS 304 | 01 No |
| 6 | INSTRUMENTATION AND CONTROL PANEL FOR ABOVE ITEMS COMPLETE WITH PANEL, CABLE, CABLE TRAYS WITH COMPLETE WORK | 01 Lot |
| 7 | SS 304 Interconnecting Pipes, Valves And Fittings with complete work. | 01 Lot |

Modification of the existing husk boiler in proper FBC

working pressure maximum 13 Kg/cm²

| SN | Work and supply description | QTY |
| --- | --- | --- |
| 1.0 | High pressure feed pump. Pump mode:- CR_-5-36, Make :- GRUNDFOS Flow 4.8 M³/hr @ 210 MLC head, Power :- 5.5 KW | 02 Nos |
| 2.0 | High pressure safety vale | 02 Nos |
| 3.0 | High pressure switch | 01 No |
| 4.0 | New FBC furnace systems with air plenum chamber and FBC nozzle, | 01 Set |
| 5.0 | Fuel feeding pneumatic speeder, | 01 Set |
| 6.0 | Screw feeder with gear motor, 2 HP motor | 01 Set |
| 7.0 | SFD fan with motor, 2 HP motor | 01 Set |
| 8.0 | High pressure FD fan 20 HP motor | 01 Set |
| 9.0 | Refectories work modification and supply as per new requirement, | 01 Set |
| 10.0 | Modification in control panel systems | 01 Set |

Sub – Section 7

battery limits

1. BATTERY LIMITS

Supplier will be responsible to undertake all the works involved in completing the project within the battery limits prescribed below

1.1 EXISTING EQUIPMENT

The bidders may visit site to study the existing equipment. The modification / revamping and layout for the new equipment to be installed has to be based on the layout of the existing equipment and affecting minimum changes.

1.2 STEAM & CONDENSATE

Steam:  Steam lines / headers are running in the existing plant.  Vendor may visit plant to access the present status. If possible the tapping for new requirement shall be taken from the existing headers in the respective plants. Supplier has to provide the peak and total load requirements.

Condensate: Condensate shall be taken to the nearest drain/ utility point.

1.3 	POWER

MCC for the new plant has to be provided by the supplier. 415 V, 3 phase 4 wire supply shall be provided to the MCC.

1.4 RAW & SOFT WATER

Raw and Soft water lines / headers are running in the existing plant.  Vendor may visit plant to access the present status. If possible the tapping for new requirement shall be taken from the existing headers in the respective plants. Supplier has to provide the peak and total load requirements.

1.5 	MILK

Required quantity of Milk/Feed shall be provided by the purchaser at the point as required by the supplier.

1.6 CIP CHEMICALS

CIP chemicals shall be supplied by the purchaser.

BOILER MODIFICATION

The boiler modifications shall be carried in the existing boiler house only.

##### Sub – Section 8

##### process performance and consumption guarantees

1. PROCESS PERFORMANCE & CONSUMPTION GUARANTEE

If the plant or any part thereof does not give the agreed process performance and consumption guarantees during the hand over till warranty period due to reasons attributable to the supplier, the supplier  shall, subject to clause below, the action shall be as detailed therein.

  - EQUIPMENT PERFORMANCE

    - The tolerence of  - 5% on 6MT  output will be considered as minimum acceptable output level i,e 5.7  MT. After the tolerence limit the eqipment performance will be claculated as below :

    - The satisfactory performance of the equipment/processing plant will be considered achieved if  the plant operates above 98% of  5.7 MT.

    - If the performance is between 95-98% of 5.7 MT, penalty will be calculated at 2% of the rupee value of the contract, per 1% of shortfall.

    - If the performance is below 95% of 5.7 MT the contractor will be required to upgrade the plant or replace the plant to comply with the above performance criteria without the cost of purchaser. Otherwise the plant will be deemed unacceptable.

  - SERVICES REQUIREMENT

    - If measure demand of services in the plant is less than 102% of the consumption declared by the contractor, the buyer will accept that the service requirements has been achieved.

    - If the requirement of any of the services in the plant is between 102% and 105% of the declared demand, penalty will be charged at 2% of every 1% rise in consumption for each of the services which falls in the category of excessive demand. For the purpose of this calculation, only the main services, steam, power and chilled water will be considered.

    - If the measured demand for services and energy is above 105%, the contractor will be required to up-grade the plant or replace the plant to comply with the declared performance criteria.

    - Otherwise the plant will be deemed un-acceptable.

1.3 MAXIMUM LIABILITY

1.3.1 The maximum liability of suppliers on all counts of penalties including above, Liquidated Damages clause and other liabilities of any kind shall not exceed 10% of Contract value.

Sub – Section 9

spare parts

To be submitted as per section 3 evaluation and qualification criteria.

Sub – Section 10

warranty

As per clause 30 of  GCC.

Sub – Section 11

tools manuals and catalogue

- Tools:

1.1	The bidder/supplier/manufacturer should supply specials tools/lifter for assembling, 	dismantling and repair for all the supplied major equipments. A list of tools should be 	attached along with the tender.

  - The bidder/supplier/manufacturer should also supply one set of electrical and mechanical tools set. A list of tools should be attached along with the tender.

- MANUALS & CATALOGUE

2.1	The bidder/supplier/manufacturer should provide complete two sets of 	manuals,catalogues and spare parts list of all the supplied equipments and 	accessories in a complied form during handover of the plant.

Sub – Section 12

tRAINING

As per section 3 evaluation and qualification criteria.

##### sub- section 13

##### Drawings data & documents

DOCUMENTS REQUIRED FROM THE BIDDER

1.1 The Bidder must enclose the following General Drawings with the Bid

- Product flow diagram including production equipment, service and product piping, controls instruments, automation, etc.

- Proposed P & ID

- CIP equipment arrangement and flow diagram.

- Utilities flow diagram including utility equipment, interconnection piping, controls, instruments, automation etc.

- Single line diagram for electrical distribution system.

1.2	PERFORMANCE TESTS

The bidder is required to detail the documentation proposed for performance tests of all

Major items of equipment and all major processes and services plant. This shall detail the

Guaranteed vs. actual throughput or output or performance (as relevant) and the tolerance

of accuracy. Also the test methods proposed to demonstrate that these guarantees have

been met.

1.3	FORMATS OF GUARANTEES

- Guarantees for throughput of various sections of plant.

- Product quality.

- Weight and Measurement tolerance.

- Milk solid loss.

- Service consumption.

- Formats for performance tests.

- Procedure for carrying out the tests.

- Method of measurement

- Test duration

- Evaluation methodology

EXISTING PLANT DRAWING

##### Deviations from Technical Requirement

No Deviation

##### PART III

##### Conditions OF CONTRACT

##### AND

##### CONTRACT FORMS

Contents

1.    Definition

2.    Application

3.    Contract Documents

4.	Fraud and Corruption

5.	Interpretation

6.	Language

7.	Joint Venture, Consortium or Association

8.	Eligibilty

9.	Definitation of Country of origin

10.	Specifications and Standards

11.	Use of Contract Documents and Information

12.	Patent Rights

13.	Performance Security

14.	Inspection and Tests

15.	Packing and Marking

16.	Delivery and Documents

17.	Responsibilities of Bidder

18.	Responsibilities of Purchaser

19.	Insurance

20.	Transportation

21.	Incidental Services

22.	Terms of Payment

23.	Prices

24.	Change Orders

25.	Schedule of Performance

26.	Contract Amendment

27.	Assignment

28.	Sub-contracts

29.	Delays in the Bidder / Supplier's Performance

30.	Liquidated Damages

31.	Warranty / Guarantee

32.	Patent Indemnity

33.	Limitation

34.	Change in Laws and Regulation

35.	Extension of Time for Completion

36.	Termination for Default

37.	Force Majeure

38.	Termination for Insolvency

39.	Termination for Convenience

40.	Resolution of Disputes

41.	Governing Language

42.	Governing Law

43.	Notices

44.	Taxes and Duties

45.	Right to use defective equipment

46.	Income Tax and Other Taxes

47.	Jurisdiction

PART III :      Conditions Of Contract And Contract Forms

Section 6:    General Conditions  Of Contract (GCC)

| 1. Definitions | 1.1 In this Contract, the following terms shall be interpreted as indicated: 1.2 "The Contract" means the agreement entered into between the Purchaser and the Bidder/Supplier, including all attachments and appendices thereto and all documents incorporated by reference therein. 1.3 "The Contract Price" means the price payable to the Bidder/Supplier under the Contract for the full and proper performance of its contractual obligations. 1.4 "The Goods" means all of the equipment, machinery, and/or other materials, which the Bidder/Supplier is required to supply to the Purchaser under the Contract. 1.5 “Services" means services ancillary to the supply of the Goods, such as transportation and insurance, and any other incidental services, such as installation, commissioning, provision of technical assistance, training and other such obligations of the Bidder/Supplier covered under the Contract. 1.6 "The Purchaser" means the Organization purchasing the Goods and services and would include the term "Owner". 1.7 "The Bidder/Supplier" means the individual or firm supplying the Goods and services under this Contract would include also the terms “contractor” or “Bidder/Supplier”. 1.8 Engineer-in-charge means the Engineer designated as such or other Engineer appointed from time to time by the Purchaser and notified in writing to the Bidder/Supplier to act as Engineer-in-charge for the purposes of contract. |
| --- | --- |
| 2. Application | 2.1 These General Conditions shall apply to the extent that provisions in other parts of the Contract do not supersede them. |
| 3. Contract Documents | 3.1 Subject to the order of precedence set forth in the Contract Agreement, all documents forming the Contract (and all parts thereof) are intended to be correlative, complementary, and mutually explanatory. The Contract Agreement shall be read as a whole. |
| 4. Fraud and Corruption | 4.1 If the Purchaser determines that the Supplier and/or any of its personnel, or its agents, or its Subcontractors, consultants, service providers, suppliers and/or their employees has engaged in corrupt, fraudulent, collusive, coercive or obstructive practices, in competing for or in executing the Contract, then the Purchaser may, after giving 14 days notice to the Supplier, terminate the Supplier's employment under the Contract and cancel the contract, and the provisions of Clause 35 shall apply as if such expulsion had been made under Sub- Clause 35.1. - For the purposes of this Sub-Clause (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a is representation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or 4.2 Should any employee of the Supplier be determined to have engaged in corrupt, fraudulent, collusive, coercive, or obstructive practice during the purchase of the Goods, then that employee shall be removed. |
| 5. Interpretation | 5.1 If the context so requires it, singular means plural and vice versa. 5.2 Incoterms (a) Unless inconsistent with any provision of the Contract, the meaning of any trade term and the rights and obligations of parties thereunder shall be as prescribed by Incoterms. (b) The terms EXW, CIP, FCA, CFR and other similar terms, when used, shall be governed by the rules prescribed in the current edition of Incoterms specified in the SCC and published by the International Chamber of Commerce in Paris, France. 5.3 Entire Agreement The Contract constitutes the entire agreement between the Purchaser and the Supplier and supersedes all communications, negotiations and agreements (whether written or oral) of the parties with respect thereto made prior to the date of Contract. 5.4 Amendment No amendment or other variation of the Contract shall be valid unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each party thereto. 5.5 Non waiver (a) Subject to GCC Sub-Clause 4.5(b) below, no relaxation, forbearance, delay, or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect, or restrict the rights of that party under the Contract, neither shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract. (b) Any waiver of a party’s rights, powers, or remedies under the Contract must be in writing, dated, and signed by an authorized representative of the party granting such waiver, and must specify the right and the extent to which it is being waived. 5.6 Severability If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract. |
| 6. Language | 6.1 The Contract as well as all correspondence and documents relating to the Contract exchanged by the Supplier and the Purchaser, shall be written in the language specified in theSCC. Supporting documents and printed literature that are part of the Contract may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified, in which case, for purposes of interpretation of the Contract, this translation shall govern. - The Supplier shall bear all costs of translation to the governing language and all risks of the accuracy of such translation, for documents provided by the Supplier. |
| 7. Joint Venture, Consortium or Association | 7.1 If the Supplier is a joint venture, consortium, or association, all of the parties shall be jointly and severally liable to the Purchaser for the fulfillment of the provisions of the Contract and shall designate one party to act as a leader with authority to bind the joint venture, consortium, or association. The composition or the constitution of the joint venture, consortium, or association shall not be altered without the prior consent of the Purchaser. |
| 8. Eligibility | 8.1 The Supplier and its Subcontractors shall have the nationality of an eligible country. A Supplier or Subcontractor shall be deemed to have the nationality of a country if it is a citizen or constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country. 8.2 All Goods and Related Services to be supplied under the Contract and financed by the Bank shall have their origin in Eligible Countries. For the purpose of this Clause, origin means the country where the goods have been grown, mined, cultivated, produced, manufactured, or processed; or through manufacture, processing, or assembly, another commercially recognized article results that differs substantially in its basic characteristics from its components. |
| 9. Definition of Country of origin | 9.1 For purpose of this Clause "origin" means the place where the Goods were mined, grown or produced, or from which the Services are supplied. Goods are produced when, through manufacturing, processing or substantial and major assembling of components, a commercially recognized new product results that is substantially different in basic characteristics or in purpose or utility from its components. The origin of Goods and Services is distinct from the nationality of the Bidder/Supplier. |
| 10. Specifications and Standards | 10.1 Technical Specifications and Drawings (a) The Goods and Related Services supplied under this Contract shall conform to standard mentioned in the technical specifications and when no applicable standard is mentioned, the standard shall be equivalent or superior to the official standards whose application is appropriate to the Goods’ country of origin. (b) The Supplier shall be entitled to disclaim responsibility for any design, data, drawing, specification or other document, or any modification thereof provided or designed by or on behalf of the Purchaser, by giving a notice of such disclaimer to the Purchaser. (c) Wherever references are made in the Contract to codes and standards in accordance with which it shall be executed, the edition or the revised version of such codes and standards shall be those specified in the Schedule of Requirements. During Contract execution, any changes in any such codes and standards shall be applied only after approval by the Purchaser and shall be treated in accordance with GCC Clause 33. |
| 11. Use of Contract Documents and Information | 11.1 The Bidder/Supplier shall not, without the Purchaser's prior written consent, disclose the Contract, or any provision thereof, or any specification, plan, drawing, pattern, sample or information furnished by or on behalf of the Purchaser in connection therewith, to any person other than a person employed by the Bidder/Supplier in the performance of the Contract. Disclosure to any such employed person shall be made in confidence and shall extend only so far as may be necessary for purposes of such performance. 11.2 The Bidder/Supplier shall not, without the Purchaser's prior written consent, make use of any document or information except for purposes of performing the Contract. 11.3 Any document, other than the Contract itself, shall remain the property of the Purchaser and shall be returned (in all copies) to the Purchaser on completion of the Bidder/Supplier's performance under the Contract if so required by the Purchaser. |
| 12. Patent Rights | 12.1 The Bidder/Supplier shall indemnify the Purchaser against all third-party claims of infringement of patent, trademark or industrial design rights arising from use of the Goods or any part thereof. |
| 13. Performance Security | 13.1 The Bidder/Supplier shall furnish performance security to the Purchaser in the amount specified in the Special Conditions of Contract. 13.2 The proceeds of the performance security shall be payable to the Purchaser as compensation for any loss resulting from the Bidder/Supplier's failure to complete its obligations under the Contract. 13.3 The Performance Security shall be denominated in Nepalese Rupees /Indian Rupees/ US Dollor or equivalent in any convertible currency and shall be in one of the following forms: - A bank guarantee issued by a Nepalese A class commercial bank and endorsed in the form provided in the Bidding Document. Such bank guarantee shall be valid till the expiry of the warranty period. IFB - Demand Draft from a Nationalised Bank in favour of DDC NEPAL. payable at Kathmandu. No interest shall be paid on the security deposit, which shall be retained till the completion of the warranty period. 13.4 The performance security will be discharged by the Purchaser and returned to the Bidder/Supplier not later than 30 days following the date of completion of the Bidder/Supplier's performance obligations, including any warranty obligations, under the Contract. |
| 14. Inspection and Tests | 14.1 The Purchaser or its representative shall have the right to inspect and/or test the Goods to confirm their conformity to the Contract. The Special Conditions of Contract and/or the Technical Specifications shall specify what inspections and tests the Purchaser requires. and where they are to be conducted. The Purchaser shall notify the Bidder/Supplier in writing of the identity of any representatives, if retained for these purposes. 14.2 The inspections and tests may be conducted on the date of delivery and/or at the Good's final destination. Where conducted on the premises of the Bidder/Supplier or its subcontractors(s), all reasonable facilities and assistance including access to drawings and production data shall be furnished to the inspectors at no charge to the Purchaser. In case of any defects or deficiency notified by the Purchaser's inspection authority, the Bidder/Supplier will rectify and make good the same without delay and not proceed with further processing of such item(s) of Goods without obtaining approval from the inspection authority. 14.3 Should any inspected or tested Goods fail to conform to the Specifications, the Purchaser may reject them and the Bidder/Supplier shall either replace the rejected Goods or make all alterations necessary to meet specification requirements free of cost to the Purchaser. 14.4 The Purchaser's right to inspect, test and, where necessary, reject the Goods after the Goods' arrival at the destination shall in no way be limited or waived by reason of the Goods having previously been inspected, tested and passed by the Purchaser or its representative prior to the Goods shipment from the country of origin. 14.5 Nothing in this clause shall in any way release the Bidder/Supplier from any warranty or other obligations under this Contract. |
| 15. Packing and Marking | 15.1 The Bidder/Supplier shall provide such packing of the Goods as is required to prevent their damage or deterioration during transit to their final destination as indicated in the Contract. The packing shall be sufficient to withstand, without limitation, rough handling during transit and exposure to temperature, salt and precipitation during transit and open storage. Packing case size and weights shall take into consideration, where appropriate, the remoteness of the Goods' final destination and the absence of heavy handling facilities at all points in transit. 15.2 The packing, marking and documents within and outside the packages shall comply strictly with such special requirements as shall be expressly provided for in the Contract including additional requirements if any specified in SCC and in ay other instructions ordered by the Purchaser. 15.3 Each package shall be marked to indicate a) Name of the Bidder/Supplier, b) Details of items in the package, c) Name of the Consignee, d) Purchase Order Number, e) Gross, net and tare weights of the item, f) Destination. |
| 16. Delivery and Documents | 16.1 Delivery of the goods shall be made by the Bidder/Supplier in accordance with the terms specified by the Purchaser in its Schedule of Requirements and the Special Conditions of Contract. For the purpose of the Contract, "FOB", "C&F", "CIF", "FOR Destination", "Free delivery at site" and other trade terms used to describe the obligations of the parties shall have the meanings as per the common trade practices. |
| 17. Responsibilities of bidder | 17.1 Developing the process design, complete engineering design, manufacturing and/or supply of goods and service and ensuring best performance of individual equipment/systems/process plant as a whole. The bidder shall avail the assistance of reputed specialists in the respective field wherever required as well as past experiences gained during installation/ commissioning of the projects. 17.2 Development of automation services, software, interfaces etc. and its incorporation in the project. 17.3 Providing technical data, technical literature, production and service load calculations. 17.4 First charge of oil/lubricants for new equipment supplied. 17.5Execution of project in accordance with prevailing ISO/bidders respective national standard or equivalent standard, wherever applicable & relevant to the project. 17.6 Testing and commissioning satisfactorily and performance of all equipment in bidder’s scope and after sales service. 17.7 Provide necessary manpower during erection, testing and commissioning along with tests. 17.8 Testing, commissioning of the system under scope as per agreed performance parameters and utility consumption. 17.9 Training Purchaser’s personnel in the field of instrumentation automation, management system, plant operation & control, maintenance & repair of systems & equipment. 17.10 The security of supplied equipments at site until installation will be the responsibility of the supplier. |
| 18. Responsibilities of purchaser | 18.1 Building layout and drainage and sewage details. 18.2 Documents on local site conditions related to climate, access and communications. 18.3 Water and power supply at one point within the powder plant premises During erection free of cost. 18.4 Lighting and domestic wiring system and internal telephone system including the switch boards for lighting. Engineering personnel to liaison with the supplier, Project Manager and the execution team. 18.5 Adequate staff including operators, supervisors and engineers for product trials. 18.6 All civil works including buildings, roads, cable trench, underground condensate piping and drainage. 18.7 Provision and cost of services, raw products, packaging materials & chemicals. 18.8 Timely provision of personnel for training. 18.9 Provide open storage area, lockable store and office space during erection and commissioning of project. 18.10 Suitable Site fabrication yard 18.11 Telephone and fax on chargeable basis. 18.12 Payment as per agreed terms and conditions. 18.13 Approval of drawing within 15 days from date of submission and decision within a week on any issue which will come up. 18.14 Project manager with team throughout the implementation. 18.15 Schedule to enable commencement of erection activities to meet the overall completion schedule. 18.16 Availability of required quantity of milk for the designed product to conduct the first run of product trials at the rated plant capacity. |
| 19. Insurance | 19.1 The goods supplied under the Contract shall be fully insured in freely convertible currency from an eligible country against loss or damage incidental to manufacture or acquisition, transportation, storage and delivery in the manner specified in the Special Conditions of Contract. Where the Purchaser requires delivery of the Goods on free delivery at site basis; the Bidder/Supplier shall arrange and pay for marine insurance naming the Purchaser as the beneficiary. The Bidder/Supplier shall provide a copy of the insurance policy along with invoice to the Purchaser who will make arrangements to extend the validity of the policy, if necessary. The Bidder/Supplier shall initiate and pursue claim till settlement and promptly make arrangements for repair and/or replacement of any damaged item/s irrespective of settlement of claim by the underwriters. |
| 20. Transportation | 20.1 The Bidder/Supplier is required under the Contract to deliver the Goods for destination, specified in the Schedule of Requirement. Transport of the Goods, up to the destination shall be arranged and paid for by the Bidder/Supplier and the cost thereof shall be included in the Contract Price. Where the Bidder/Supplier is required to effect delivery under any other terms, for example, by post or to another address in the source country, the Bidder/Supplier shall be required to meet all transport, loading/unloading and storage expenses until delivery. |
| 21. Incidental Services | 21.1 As specified in the Special Conditions of Contract, the Bidder/Supplier shall be required to provide any or all of the following services: - Performance or supervision of on-site assembly and/ or start-up of the supplied Goods; - Furnishing of tools required for assembly and maintenance of the supplied goods - Furnishing of a detailed operations and maintenance manual for each appropriate unit of the supplied Goods; and manuals covering the operation and maintenance of automation software and control systems. - Performance or supervision or maintenance and/or repair of the supplied Goods, for a period of time agreed by the parties, provided that this service shall not relieve the Bidder/Supplier of any warranty obligations under this Contract and - Conduct of training of the Purchaser's personnel, at the Bidder/Supplier's plant and/or on-site, in assembly, start-up operation, maintenance and/or repair of the supplied Goods. 21.2 The Bidder/Supplier shall guarantee the complete installation for satisfactory performance for a minimum period of twelve months from the date of commissioning & handover. The Bidder/Supplier at his own cost shall rectify any defect arising out of faulty installation or use of substandard material or workmanship. |
| 22.Terms of Payment | 22.1 The Contract Price, including any Advance Payments, if applicable, shall be paid as specified in the SCC. 22.2 The method and conditions of payment to be made to the Bidder/Supplier under the Contract shall be specified in the Special Conditions of Contract. 22.3 The Bidder/Supplier's request(s) for payment shall be made to the Purchaser in writing, accompanied by an invoice describing, as appropriate, the Goods delivered and Services performed, and by shipping documents, submitted pursuant to SCC Clause 15, and fulfillments of other obligations stipulated in the Contract. 22.4 Payments shall be made after the submission of an invoice/claim. However, the invoice/claim should be certified by the project incharge. |
| 23. Prices | 23.1 Prices charged by the Bidder/Supplier for Goods delivered and Services performed under the Contract shall not, with the exception of price adjustments authorized by the special conditions of the contract, vary from the prices quoted by the Bidder/Supplier in its bid and the Contract shall be on fixed price basis. |
| 24. Change Orders | 24.1 The Purchaser may, at any time, by a written order given to the Bidder/Supplier make changes within the general scope of the Contract in any one or more of the following: - Drawings, designs or specifications, where Goods to be furnished under the Contract are to be specifically manufactured for the Purchaser - The method of shipment or packing - The place of delivery or - The Services to be provided by the Bidder/Supplier. 24.2 If any such change causes an increase or decrease in the cost of, or the time required for, the Bidder/Supplier's performance of any part of the work under the Contract, whether changed or not changed by the order, an equitable adjustment shall be made in the Contract Price or delivery schedule, or both, and the Contract shall accordingly be amended. Any claims by the Bidder/Supplier for adjustment under this clause must be asserted within thirty (30) days from the date of the Bidder/Supplier's receipt of the Purchaser's change order agreed between both parties. |
| 25. Schedule of Performance | 25.1 The Bidder/Supplier should submit the performance schedule for Expansion of Powder Plant, dairy whitener including modification of boiler to DDC within 15 days after the signing of contract. |
| 26. Contract Amendment | 26.1 No variation in or modification of the terms of the Contract shall be made except by written amendment signed by the parties. |
| 27. Assignment | 27.1 The Bidder/Supplier shall not assign, in whole or in part, its obligations to perform under the Contract, except with the Purchaser's prior written consent. |
| 28. Sub-contracts | 28.1 The Bidder/Supplier shall notify the Purchaser in writing of all sub-contracts awarded under the Contract if not already specified in his bid. Such notification, in his original bid or later, shall not relieve the Bidder/Supplier from any liability or obligation under the Contract. 28.2 Sub-contracts must comply with the provisions of GCC Clause 4 & 7. |
| 29. Delays in the Bidder / Supplier's Performance | 29.1 Delivery of the Goods and performance of Services shall be made by the Bidder/Supplier in accordance with the time schedule specified by the Purchaser in its Schedule of Requirements. 29.2 An unexcused delay by the Bidder/Supplier in the performance of its delivery obligations shall render the Bidder/Supplier liable to any or all of the following sanctions: - Forfeiture of its performance security, - Imposition of liquidated damages, and/or - Termination of the Contract for default 29.3 If at any time during performance of the Contract, the Bidder/Supplier or its subcontractor(s) should encounter conditions impeding timely delivery of the Goods and performance of Services, the Bidder/Supplier shall promptly notify the Purchaser in writing of the fact of the delay, its likely duration and its cause(s). As soon as practicable after receipt of the Bidder/Supplier's notice, the Purchaser shall evaluate the situation and may at its discretion extend the Bidder/Supplier's time for performance, in which case the extension shall be ratified by the parties by amendment of the Contract. |
| 30. Liquidated Damages | 30.1 Subject to GCC Clause 36, if the Bidder/Supplier fails to deliver any or all of the Goods or perform the Services within the time period(s) specified in the Contract, the Purchaser shall, without prejudice to its other remedies under the Contract, deduct from the Contract Price, as liquidated damages as under: a. For the Supply Component: A sum equivalent to 0.05% per day of the contract price of the delayed goods as per the price break up furnished by the supplier and accepted by the Purchaser, which the supplier fails to supply within the time period specified in the contract. The total amount so deducted as per above, shall not exceed 10% of the Contract value. Once the maximum is reached, the Purchaser may consider termination of the Contract. 30.2 Any incremental taxes and levies on account of delay in performance of the Contract by the Bidder/Supplier shall be to the Bidder/Supplier's account. |
| 31 warranty/ guarantee | 31.1 The warranty/guarantee shall be as per provision under Clause 30 Special Condition of Contract. |
| 32. Patent Indemnity | 32.1 The Supplier shall, subject to the Purchaser’s compliance with GCC Sub-Clause 31.2, indemnify and hold harmless the Purchaser and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of any nature, including attorney’s fees and expenses, which the Purchaser may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright, or other intellectual property right registered or otherwise existing at the date of the Contract by reason of: (a) the installation of the Goods by the Supplier or the use of the Goods in the country where the Site is located; and (b) the sale in any country of the products produced by the Goods. Such indemnity shall not cover any use of the Goods or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, neither any infringement resulting from the use of the Goods or any part thereof, or any products produced thereby in association or combination with any other equipment, plant, or materials not supplied by the Supplier, pursuant to the Contract. 32.2 If any proceedings are brought or any claim is made against the Purchaser arising out of the matters referred to in GCC Sub- Clause 31.1, the Purchaser shall promptly give the Supplier a notice thereof, and the Supplier may at its own expense and in the Purchaser’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. 32.3 If the Supplier fails to notify the Purchaser within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Purchaser shall be free to conduct the same on its own behalf. 32.4 The Purchaser shall, at the Supplier’s request, afford all available assistance to the Supplier in conducting such proceedings or claim, and shall be reimbursed by the Supplier for all reasonable expenses incurred in so doing. 32.5 The Purchaser shall indemnify and hold harmless the Supplier and its employees, officers, and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of any nature, including attorney’s fees and expenses, which the Supplier may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright, or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Purchaser. |
| 33. Limitation of Liability | 33.1 Except in cases of criminal negligence or willful misconduct, (a) the Supplier shall not be liable to the Purchaser, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Supplier to pay liquidated damages to the Purchaser and (b) the aggregate liability of the Supplier to the Purchaser, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the supplier to indemnify the purchaser with respect to patent infringement. |
| 34. Change in Laws and Regulations | 34.1 Unless otherwise specified in the Contract, if after the date of 28 days prior to date of Bid submission, any law, regulation, ordinance, order or bylaw having the force of law is enacted, promulgated, abrogated, or changed in the place of the Purchaser’s country where the Site is located (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the Delivery Date and/or the Contract Price, then such Delivery Date and/or Contract Price shall be correspondingly increased or decreased, to the extent that the Supplier has thereby been affected in the performance of any of its obligations under the Contract. Notwithstanding the foregoing, such additional or reduced cost shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with GCC Clause 15. |
| 35. Extension of Time for Completion | 35.1 Should the amount of extra or additional work of any kind or any cause of delay referred to in these conditions, or exceptional adverse climatic conditions, or other special circumstances of any kind whatsoever which may occur, other than through a default of the Bidder/Supplier, be such as fairly to entitle the Bidder/Supplier to an extension of time for the completion of the works, the Purchaser shall determine the amount of such extension and shall notify the Bidder/Supplier accordingly. Provided that the Purchaser is not bound to take into account any extra or additional work or other special circumstances unless the Bidder/Supplier has within twenty eight days after such work has been commenced, or such circumstances have arisen, or as soon thereafter as is practicable, submitted to the Purchaser full and detailed particulars of any extension of time to which he may consider himself entitled in order that such submission may be investigated at the time. |
| 36. Termination for Default | 36.1 The Purchaser may, without prejudice to any other remedy for breach of contract, by written notice of default sent to the Bidder/Supplier, terminate the Contract in whole or in part: - If the Bidder/Supplier fails to deliver any or all of the Goods within the time period(s) specified in the Contract, or any extension thereof granted by GCC clause 28. - If the Bidder/Supplier fails to perform any other obligation(s) under the Contract. 36.2 In the event the Purchaser terminates the Contract in whole or in part, pursuant to Clause 36.2.1, the Purchaser may procure, upon such terms and in such manner, as it deems appropriate, Goods similar to those undelivered, and the Bidder/Supplier shall be liable to the Purchaser for any excess costs for such similar Goods. However, the Bidder/Supplier shall continue performance of the Contract to the extent not terminated. 36.3 Consequent to such termination of Contract, the Purchaser shall recover the advance paid, if any, to the Bidder/Supplier along with interest @ 18% per annum compounded quarterly on the last day of March, June, September and December on the advance paid for the entire period for which the advance was retained by the Bidder/Supplier. |
| 37. Force Majeure | 37.1 Not withstanding the provisions of GCC Clauses 28, 29 and 35, the Bidder/Supplier shall not be liable for forfeiture of its performance security, liquidated damages or termination for default, if and to the extent that, its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. 37.2 For purposes of this clause, "Force Majeure" means an event beyond the control of the Bidder/Supplier and not involving the Bidder/Supplier's fault or negligence and not foreseeable. Such events may include, but are not restricted to, acts of the Purchaser either in its sovereign or contractual capacity, wars or revolutions, fires, floods, earthquake, epidemics, quarantine restrictions and freight embargoes. 37.3 If a Force Majeure situation arises, the Bidder/Supplier shall promptly notify the Purchaser in writing of such condition and the cause thereof. Unless otherwise directed by the Purchaser in writing, the Bidder/Supplier shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. |
| 38. Termination for Insolvency | 38.1 The Purchaser may at any time terminate the Contract by giving written notice to the Bidder/Supplier, without compensation to the Bidder/Supplier, if: - The Bidder/Supplier becomes bankrupt or otherwise insolvent, - The Bidder/Supplier being a Company is wound up voluntarily by the order of a Court receiver, liquidator or Manager appointed on behalf of the debenture holders or circumstances shall have arisen which entitle the court or debenture holders to appoint a receiver, liquidator or a Manager, provided that such termination will not prejudice or affect any right of action or remedy which has accrued or will accrue thereafter to the Purchaser. |
| 39. Termination for Convenience | 39.1 The Purchaser, may by written notice sent to the Bidder/Supplier, terminate the Contract, in whole or in part, at any time for its convenience. The notice of termination shall specify that termination be for the Purchaser's convenience, the extent to which performance of work under the Contract is terminated, and the date upon which such termination becomes effective. 39.2 The Purchaser shall purchase the Goods that are complete and ready for dispatch within 30 days after the Bidder/Supplier’s receipt of notice of termination at the Contract terms and prices. For the remaining Goods, the Purchaser may decide: - To have any portion completed and delivered at the Contract terms and prices and/or - To cancel the remainder and pay to the Bidder/Supplier an agreed amount for partially completed Goods and for materials and parts previously procured by the Bidder/Supplier. Both Purchaser and Supplier shall mutually settle all terminations as per GCC clause 28, 29, 35 and 38. |
| 40. Resolution of Disputes | 40.1 The Purchaser and the Bidder/Supplier shall make every effort to resolve amicably by direct informal negotiation any disagreement or dispute arising between them under or in connection with the Contract. 40.2 If, after thirty (30) days from the commencement of such informal negotiations, the Purchaser and the Bidder/Supplier have been unable to resolve amicably a Contract dispute, either party may require that the dispute be referred for resolution to the formal mechanisms specified in the Special Conditions of Contract. These mechanisms may include, but are not restricted to, conciliation mediated by a third party, adjudication in an agreed national or international forum, and/or international arbitration. The mechanism shall be specified in the Special Conditions of Contract. |
| 41. Governing Language | 41.1 The Contract shall be written in the language of the bid, as specified by the Purchaser in the Instructions to Bidder/Suppliers. Subject to GCC Clause 41, that language version of the Contract shall govern its interpretation. All correspondence and other documents pertaining to the Contract, which are exchanged by the parties, shall be written in that same language. |
| 42. Governing Law | 42.1 The Contract shall be governed by and interpreted in accordance with the laws of the Nepal. |
| 43. Notices | 43.1 Any notice given by one party to the other pursuant to the Contract shall be sent in writing or by telegram or telex/cable and confirmed in writing to the address specified for that purpose in the Special Conditions of Contract. 43.2 A notice shall be effective when delivered or on the notice's effective date, whichever is later. |
| 44. Taxes and Duties | 44.1 The Bidder/Supplier shall be entirely responsible for all taxes, duties, license fees, etc. incurred until delivery of the contracted Goods to and taking over of the works by the Purchaser. The onus of paying all the statutory levies as per the applicable tariff heads and norms shall be on the Bidder/Supplier. |
| 45. Right to use defective equipment | 45.1 If after delivery, acceptance and installation and within the guarantee and warranty period, the operation or use of the equipment proves to be unsatisfactory, the Purchaser shall have the right to continue to operate or use such equipment until rectification of defects, errors or omissions by repair or by partial or complete replacement is made without interfering with the Purchasers' operation. |
| 46.Income Tax and Other Taxes | 46.1 The Bidder/Supplier shall be liable to pay all corporate taxes, income tax and other taxes that shall be levied according to the laws and regulations applicable from time to time and the price bid by the Bidder/Supplier shall include all such taxes. Wherever the laws and regulations require deduction of such taxes at the source of payment, the Purchaser shall effect such deductions from the payment due to the Bidder/Supplier. The remittance of amounts so deducted and issuance of certificate for such deductions shall be made by the Purchaser as per the laws and regulations in force. Nothing in the Contract shall relieve the Bidder/Supplier from his responsibility to pay any tax that may be levied on income and profits made by the Bidder/Supplier in respect of the Contract. The Bidder/Supplier's staff, personnel and labour will be liable to pay personal income taxes in respect of such of their salaries and wages as are chargeable under the laws and regulations for the time being in force, and the Bidder/Supplier shall perform such duties in regard to such deductions thereof as may be imposed on him by such laws and regulations. The Purchaser shall not, in any way, be responsible for such payments by the Bidder/Suppliers' staff. |
| 47. Jurisdiction | 47.1 Settlement of any dispute out of the purchase order/ contract against this bid shall be subject to the courts at Kathmandu, Nepal only. |

##### Section 7

##### Special Conditions of Contract

Contents

1. Definitions

2. Performance Security

3. Inspection and Tests

4. Delivery and Documents

5. Insurance

6. Incidental services

7. Spare Parts

8. Payment

9. Price

10. Schedule of Performance

11. Warranty / Guarantee

12. Resolution of Disputes

13. Notices

##### Section 7:    Special conditions of contract

The following Special Conditions of Contract shall supplement the General Conditions of Contract. Whenever there is a conflict, the provisions herein shall prevail over those in the General Conditions of Contract. The corresponding clause number of the General Conditions is indicated in parentheses:

| GCC 1 Definitions | 1.1 The Purchaser is Dairy Development Corporation and would include the term "Owner" 1.2 The Bidder/Supplier is (Name of Bidder/Supplier). 1.3 Equivalency of Standards and Codes (As mentioned in technical specification) 1.4 Wherever reference is made in the contract to the respective standards and codes in accordance with which goods and materials are to be furnished, and work is to be performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly set forth in the Contract. Where such standards and codes are national in character, or relate to a particular country or region, other authoritative standards which ensure an equal or higher quality than the standards and codes specified will be accepted subject to the Purchaser's prior review and written approval. Differences between the standards specified and the proposed alternative standards must be fully described in writing by the Bidder/Supplier and submitted to the Purchaser at least 30 days prior to the date when the Bidder/Supplier desires the Purchaser's approval. In the event the Purchaser determines that such proposed deviations do not ensure equal or higher quality, the Bidder/Supplier shall comply with the standards set forth in the documents. |
| --- | --- |
| GCC 12. Performance Security | 12.1 The Performance Security shall be in the amount of 10% of the Contract price up to thirty days after the date of completion of performance obligations including warranty obligations. |
| GCC 13. Inspection and Tests | 13.1 The inspection of the Goods shall be carried out to check whether the Goods are in conformity with the technical specifications attached to the purchase order form and shall be in line with the inspection/test procedures laid down in the Schedule of Specifications and the Contract conditions. 13.3 The purchaser will appoint a team for verification of sepcification, performance of supplied goods and installation as per the agreement. Final payment of remaining amount will be released after sucessful handover. |
| GCC 15. Delivery and Documents | 15.1 For imported goods: Upon shipment, the Bidder/Supplier shall notify the Purchaser and the Insurance Company by fax or e-mail the full details of the shipment including purchase order number, description of goods, quantity, the vessel, the bill of lading number and date, port of loading, date of shipment, port of discharge, etc. The Bidder/Supplier should send the following documents to the Purchaser, with a copy to the Insurance Company: 15.2 For imported goods: Original and three copies of: - The Supplier's invoice showing purchase order no., Goods description, quantity, unit price, total amount; - The negotiable, clean, on-board bill of lading marked freight prepaid and three copies of non-negotiable bill of lading; - Packing list identifying contents of each package; - Insurance certificate; - Manufacturer's/Bidder/Supplier's guarantee certificate; - Inspection certificate, issued by any one of SGS/LLOYEDS/VERITAS/CROWN AGENT stating the quantity and quality with packaging details as per sepcifications to be submitted bidder/suppliert; and - Excise gate pass/ Octroi receipts, wherever applicable, duly sealed indicating payments made; and - Any other document evidencing payment of statutory levies. - Certificate for Country of origin. - The Supplier's certificate certifying that the defects pointed out during inspection have been rectified. 15.3 The Purchaser shall receive the above documents at least one week before arrival of the Goods at the port and, if not received, the Bidder/Supplier will be responsible for any consequent expenses. 15.4 For Domestic Goods: Original and three copies of: - The Supplier's invoice showing purchase order no., Goods' description, quantity, unit price, total amount; - Delivery note/packing list/lorry receipt; - Manufacturer's/Bidder/Supplier's guarantee certificate; - Inspection certificate, issued by any one of SGS / LLOYEDS / VERITAS / CROWN AGENT stating the quantity and quality with packaging details as per sepcifications to be submitted bidder/suppliert; and - Excise gate pass/ Octroi receipts, wherever applicable, duly sealed indicating payments made; and - Any other document evidencing payment of statutory levies. - Single insurance policy which shall cover the entire project. Note: The nomenclature used for the item description in the invoice/s, packing list/s and delivery note/s etc. should be identical to that used in the purchase order/contract. The dispatch particulars including name of transporter, LR Number and date should also be mentioned in the invoice/s. |
| GCC 18. Insurance | 18.1 The marine/transit insurance shall cover an amount equal to 110% of the CIP destination value of the goods from "warehouse to warehouse" on "All Risks" basis including War Risks and Strike clauses valid for a period not less than 3 months after the date of arrival of Goods at final destination. 18.2 The Insurance charges shall be paid by successful Bidder/Supplier towards all risks during storage, erection, testing, commissioning and up to acceptance of the plant. |
| GCC 20. Incidental services | 20.1 The incidental services shall be provided as per the requirements outlined in the Schedule of Specifications. The cost shall be included in the contract price, if provided for in the scope of the Contract. |
| Spare Parts | Bidder/Suppliers shall carry sufficient inventories to assure ex-stock supply of consumable spares such as gaskets, plugs, washers, belts, etc. Other spare parts and components shall be supplied as promptly as possible but in any case within three months of placement of order. |
| GCC 21. Payment | 21.1 The method and conditions of payment to be made to the Supplier under this Contract shall be as follows: Payment for Goods supplied from abroad: Payment shall be made in the currency of Price Schedule in the following manner: (A) Advance Payment : 20% advance payment of goods supplied against i. Acceptance of the order a. Submission of duplicate copy of the order duly signed by the authorized signatory putting stamp of the organization. b. Executation of the contract form. i. Against bank gaurentee (Any 'A" class commercial bank of Nepal or endorsed by any "A" class commercial bank of Nepal) for equivalent amount valid for the contract period. (B) On Shipment : 40 % of the payment as per contract amount of goods on submission of document as per clause SCC 15.2 (C) Progressive payment: 40% payable value on goods in two installements. This payment will be paid in progression of erection as per joint committee report of bidder and purchaser. (D) Succesful Trial Production : 20% balance payment after satisfactory commissioning & handover of the plant to DDC. (E) Payment of Erection, Installation and Commissioning: Payment after satisfactory commissioning & handover of the plant to DDC along with the operation and maintenance training to DDC personnel. Notes: - Payment shall be made on complete supply of an item/ group of items specified in the Contract as per the Price Break up. No payment shall be made if supply of an item/ group of items is incomplete. |
| GCC 22 Price | Not applicable 22.1 Prices payable to the supplier as stated in the contract shall be subject to adjustment during performance of the contract to reflect changes in the cost of labour and material components in accordance with the formula: P = P1 + P2 In which, P = Total adjustment amount payable to the supplier P1 = Adjustment amount payable to the supplier on the Ex-factory costs of the equipment in the contract price P2 = Adjustment amount payable to the supplier on the installation and commissioning costs of the contract price and applicable to “Supply & Installation” contracts only. a) P1= PO X (a + b X L1/LO + C X M1/MO ) –PO In which, PO = Ex factory costs less corresponding advance paid for the equipment in the contract price. a = Fixed element of 15 % representing profits and overheads included in the contract price for the ex-works cost of the equipment b = Estimated percentage of labour component in the ex-works cost of the equipment in the contract price = 35 % c = Estimated percentage of material component in the ex-works cost of the equipment in the contract price = 50 % LO = All India Average Consumer Price Index Number For Industrial Workers issued by Labour bureau, Ministry of Labour , Govt. of India for the month in which the bid was submitted L1 = The corresponding All India Average Consumer Price Index Number For Industrial Workers issued by the Labour Bureau, Ministry of Labour, Govt. of Nepal for the month in which the equipment was dispatched. MO = All India Average Whole Sale Price Index Number issued by the Office of the Economic Adviser, Ministry of Industry, Govt. of Nepal for the month in which the bid was submitted. M1 = The corresponding All India Average Whole Sale Price Index Number for the month two months prior to the months when the equipment was dispatched. b) P2 = VL + VM VL = 0.85 X PL X W ( L2 – L3 ) /L3 Where, W = Total value of work done during the month under consideration excluding the value of the material issued by the purchaser to the supplier VL = Increase or decrease payable for the labour costs PL = Labour component L3 = All India Average Consumer Price Index Number For Industrial Workers issued by Labour Bureau, Ministry of Labour, Govt. of India for the month in which the bid was submitted. L2 = The corresponding All India Average Index numbers for the month (s) under consideration. VM = 0.85 X PM X W ( M2 – M3 ) / M3 Where, VM = Increase or decrease payable for the material PM = Material component – 25% M3 = All India Whole Sale Price Index Number issued by the Office of Economy Adviser, Ministry of Industry, Govt. of India for all commodities for the month in which the bid was submitted. M2 = The corresponding All India Whole Sale Price Index Number for the month in which the works were carried out. If at any time the current officially published indices are not available, provisional indices as determined by the purchaser will be used subject to subsequent correction of the amounts paid to the supplier when the current indices become available. 22.2 The above price adjustment formula shall be invoked by either party subject to the following further conditions: a) Price adjustment will be applied only if the resulting increase or decrease (reduction) is more than 3 % of the contract price. However, if it exceeds 3% of the contract price, the total escalation shall be payable. b) No price increase shall be allowed beyond the original delivery date unless specifically stated in the extension letter. As a rule no price adjustments shall be allowed for periods of delay for which supplier is entirely responsible. c) No price adjustment shall be payable on the portion of Contract price paid to the Supplier as Advance payment. |
| GCC24 Schedule of Performance | 24.1 The purchaser shall provide the work order to the Bidder/Supplier within 15 days after the submission of schedule of performance. |
| GCC 30. Warranty// Guarantee | 30.1 The Bidder/Supplier warrants that the Goods and equipment supplied, installed and commissioned under the Contract are new, unused, of the latest made models and incorporate all recent improvements in design and materials.. The Bidder/Supplier further warrants that the Goods supplied under this Contract shall have no defect arising from design, materials or workmanship. The Bidder/Supplier also guarantees that the Goods supplied shall perform satisfactorily as per the designed/rated/installed capacity. 30.2 This warranty/guarantee will be one year after the Goods has been delivered, commissioned and after the final trial and successful handover of the complete plant. 30.3 The Purchaser shall promptly notify the Bidder/Supplier in writing of any claims arising under this warranty. 30.4 Upon receipt of such notice, the Bidder/Supplier shall, with all reasonable speed, repair or replace the defective Goods or parts thereof, without costs to the Purchaser. 30.5 If the Bidder/Supplier, having been notified, fails to remedy the defect(s) within a reasonable period, the Purchaser may proceed to take such remedial action as may be necessary, at the Bidder/Supplier's risk and expense and deduct from the bidder/supplier performance security without prejudice to any other rights which the Purchaser may have against the Bidder/Supplier under the Contract. 30.6 The Bidder/Supplier should also guarantee the complete installation for satisfactory performance for one year from the date of hand over of the plant. The Bidder/Supplier at his own cost including travelling, lodging and fooding shall rectify any defect in machineries as well as defects arising out of faulty installation or use of substandard material or workmanship during warranty period. 30.7 The Bidder/Supplier should also provide one year immediate support as and when required for the periodic maintenance/repair of the supplied equipment, accessories & fittings. |
| GCC 39 Resolution of Disputes | 39.1 All disputes or differences in respect of which the decision is not final and conclusive shall, on the initiative of either party, be referred to the adjudication of sole Arbitrator. Within thirty days of receipt of notice from the Bidder/Supplier of his intention to refer the dispute to arbitration, the Purchaser shall finalize a panel of three Arbitrators and intimate the same to the Supplier. The Supplier shall within fifteen days of receipt of this list select and confirm his acceptance to the appointment of one from the panel as Arbitrator. If the Supplier to communicate his selection of name, within the stipulated period, the Purchaser shall without delay select one from the panel and appoint him as the sole Arbitrator. If the Purchaser fails to send such a panel within thirty days, as stipulated, the Bidder/Supplier shall send a similar panel to the Purchaser within fifteen days. The Purchaser shall then select one from the panel and appoint him as the sole Arbitrator within fifteen days. If the Purchaser fails to do so, the Bidder/Supplier shall communicate to the Purchaser the name of one from the panel who shall then be the sole Arbitrator. The appointment of sole Arbitrator so made shall be final and conclusive. 39.2 The Arbitration shall be conducted in accordance with the provisions of the UNCITRAL rules thereunder or any statutory modifications thereof for the time being in force. The Arbitration proceedings shall be held in KATHMANDU ONLY at the time as the sole Arbitrator may decide. The decision of the sole Arbitrator shall be final and binding upon the parties and the expenses of the Arbitrator shall be paid as may be determined by the Arbitrator. 39.3 Performance under the Contract shall, if reasonably possible, continue during the Arbitration proceedings and payments due to the Bidder/Supplier by the Purchaser shall not be withheld, unless they are the subjects of the Arbitration proceedings. 39.4 All awards for claims equivalent to Rupees thirty thousand or more shall be in writing and state the reasons for the amounts awarded. 39.5 Neither party is entitled to bring a claim to Arbitration if its Arbitrator has not been appointed within thirty days after expiration of the warranty/ guarantee period. |
| GCC 42. Notices | 42.1 For the purpose of all the notices, the following shall be the address of the Purchaser and Supplier. |
| Purchaser Dairy Development Corporation Central Office, Lainchaur, Kathmandu, Nepal. Supplier Bidders to provide details. |  |

##### SUB Section 1

##### Special Conditions of Contract

##### for

##### General Erection & Commissioning

Contents

1. Sufficiency Of Tender

2. Programme Of Installation & Commissioning

3. Preparation of Drawings for Approval

4. Superintendence, Team And Conduct

5. Purchaser's Instructions

6. Right Of The Purchaser

7. Bidder/Supplier’s Functions

8. Variations

9. Duties of the Bidder/Supplier Vis-a-Vis the Purchaser

10. Supply Of Tools, Tackles And Materials

11. Protection Of Plant

12. Unloading, Transportation And Inspection

13. Storage Of Equipment

14. Approvals

15. Review & Co-Ordination of Erection Work

Table 1 List of Drawings required Submission

##### Sub section 1 : Special conditions of contract For General  erection & commissioning

| 1. Sufficiency of Tender | 1.1 The Bidder/Supplier by bidding shall be deemed to have satisfied himself as to all the conditions and circumstances affecting the Contract Price, as to the possibility of executing the works as shown and described in the Contract, as to the general circumstances at the site of the works, as to the general labor position at site and to have determined the prices accordingly. |
| --- | --- |
| 2. Programme of Installation & Commissioning | 2.1 As soon as practicable after the acceptance of the bid, the Bidder/Supplier shall submit to the Purchaser for his approval a comprehensive programmed in the form of bar chart showing the sequence of order in which the Bidder/Supplier proposes to carry out the works including the design, manufacture, delivery to site, erection and commissioning thereof. After submission to and approval by the Purchaser of such programmed, the Bidder/Supplier shall adhere to the sequence of order and method stated therein. The submission to and approval by the Purchaser of such programmed shall not relieve the Bidder/Supplier of any of his duties or responsibilities under the Contract. The programmed approved by the Purchaser shall form the basis of evaluating the pace of all works to be performed by the Bidder/Supplier. The Bidder/Supplier shall update the PERT Network every month, submit it to the Purchaser and shall inform the Purchaser the progress on all the activities falling on schedule for the next reporting date. |
| 3. Preparation of Drawings for Approval | 3.1 The Bidder/Supplier should visit the site to acquaint himself in respect of existing site conditions and to know the details/information required for understanding the nature and type of civil construction works involved in the project. The Bidder/Supplier shall submit to the Purchaser for approval: - Within the time given in the specification or in the program, such drawings, samples, patterns and models as may be called for therein, and in numbers therein required. - During the progress of works and within such reasonable times as the Purchaser may require such drawings of the general arrangement and details of the works as the Purchaser may require. - Detail engineering drawing for plant layout P&I diagram for process and services should be submitted. But the purchaser will not bear additional cost for those drawings. 3.2 Wherever necessary, the Bidder/Supplier would be provided with a set of architectural drawings for the buildings where the erection works would be carried out and also the equipment details/ drawings of various equipment handed over to the Bidder/Supplier by the Purchaser. 3.3 The specifications/ conditions concerning the submission of drawings by the Bidder/Supplier are detailed as under: 3.3.1 Bidder/Supplier shall furnish a list of all necessary drawings, which the Bidder/Supplier shall submit for approval, identifying each drawing by a serial number and descriptive title and expected date of submission. A brief list of drawings is given in Table 1. This list shall be revised and extended if necessary, during the progress of work depending on the nature of the contract also. 3.3.2 The Purchaser shall signify his approval or disapproval of all drawings or such drawings that would affect progress of the contract as per the agreed programmed. 3.3.3 The purchaser shall issue drawing within four weeks of time requested by the Bidder/Supplier. 3.3.4 P&I Drawings, Plant Layout and GA Drawings submitted for approval shall be signed by responsible representative of Bidder/Supplier and shall be to any one of the following sizes : “ A0, A1, A2, A3 and A4” & also drawing CD (Autocad) should be provided. 3.3.5 All drawings shall show the following particulars in the lower right hand corner in addition to Bidder/Supplier’s name: - Name of the Purchaser - Project Title - Title of drawing - Scale - Date of drawing - Drawing number - Space for drawing number 3.4 In addition to the information provided on drawings, each drawing shall carry a revision number, date of revision and brief description of revision carried out. Whenever any revision is carried out, correspondingly revision number must be updated. 3.5 All dimensions on drawings shall be in metric units. 3.6 Drawings (three sets) submitted by the Bidder/Supplier for approval will be checked, reviewed by the Purchaser, and comments, if any, on the same will be conveyed to the Bidder/Supplier. It is the responsibility of the Bidder/Supplier to incorporate correctly all the comments conveyed by the Purchaser on the Bidder/Supplier's drawings. The drawings, which are approved with comments, are to be re-submitted to the Purchaser for purpose of records. If the Bidder/Supplier is unable to incorporate any comments in the revised drawings, Bidder/Supplier shall clearly state in his forwarding letter such non-compliance along with the valid reasons. 3.7 Drawings prepared by the Bidder/Supplier and approved by the Purchaser shall be considered as a part of the specifications. However, the examination of the drawings by the Purchaser shall not relieve the Bidder/Supplier of his responsibility for engineering design, workmanship, and quality of materials, warranty obligations and satisfactory performance on installation covered under the contract. 3.8 If at any time before completion of the work, changes are made necessitating revision of approved drawings, the Bidder/Supplier shall make such revisions and proceed in the same routine as for the original approval. 3.9 Date of submission: In the event, the drawings submitted for approval require many revisions amounting to redrawing of the same, and then the date of submission of the revised drawings would be considered as the date of submission for approval. 3.10 The Bidder/Supplier shall furnish to the Purchaser before the works are taken over, Operating and Maintenance instructions together with Drawings of the works as completed, in sufficient detail to enable the Purchaser to maintain, dismantle, reassemble and adjust all parts of the works. Unless otherwise agreed, the works shall not be considered completed for the purposes of taking over until such instructions and drawings have been supplied to the Purchaser. |
| 4.Superintendence, Team and Conduct | 4.1 The Bidder/Supplier shall employ one or more competent representatives, whose name or names shall have previously been communicated in writing to the Purchaser by the Bidder/Supplier, to superintend the carrying out of the works on the site. The said representative or if more than one shall be employed, then one of such representatives shall be present on the site during all times, and any orders or instructions which the Purchaser may give to the said representative of the Bidder/Supplier shall be deemed to have given to the Bidder/Supplier. The said representative shall have full technical capabilities and complete administrative and financial powers to expeditiously and efficiently execute the work under the contract. 4.2 The Bidder/Supplier shall, execute the works with due care and diligence within the time for completion and employ Bidder/Supplier’s team comprising qualified and experienced engineers together with adequate skilled, semi-skilled and unskilled workmen in the site for carrying out the works. The Bidder/Supplier shall ensure adequate workforce to keep the required pace at all times as per the schedule of completion. Bidder/Supplier shall also ensure availability of competent engineers during commissioning/start up, trial runs, Operation of the plant/equipment till handing over of the plant. 4.3 The Bidder/Supplier shall furnish the details of qualifications and experience of their senior supervisors and engineers assigned to the work site, including their experience in supervising erection and commissioning of plant and equipment of comparable capacity. 4.4 When the Bidder/Supplier or Bidder/Supplier's representative is not present on any part of the work where it may be desired to give directions in the event of emergencies, orders may be given by the Purchaser and shall be received and observed by the supervisors or foremen who may have charge of the particular part of the work in reference to which orders are given. Any such instructions, directions or notices given by the Purchaser shall be deemed given to the Bidder/Supplier. 4.5 The Bidder/Supplier shall furnish to the Purchaser a fortnightly labor force report showing by classifications the number of employees engaged in the work. The Bidder/Supplier's employment records shall include any reasonable information as may be required by the Purchaser. The Bidder/Supplier should also display necessary information as may be required by statutory regulations. 4.6 None of the Bidder/Supplier’s supervisors, engineers, or laborers may be withdrawn from the work without notice to the Purchaser and further no such withdrawals shall be made if in the opinion of the Purchaser, it will adversely affect the required pace of progress and/or the successful completion of the work. 4.7 The Purchaser shall be at liberty to object to any representative or person, skilled, semiskilled or unskilled worker employed by the Bidder/Supplier in the execution of or otherwise about the works who shall, in the opinion of the Purchaser, misconduct himself or be incompetent, or negligent or unsuitable, and the Bidder/Supplier shall remove the person so objected to, upon receipt of notice in writing from the Purchaser and shall provide in that place a competent representative at Bidder/Supplier's own expense within a reasonable time. 4.8 In the execution of the works no persons other than the Bidder/Supplier, sub-Bidder/Supplier and their employees shall be allowed on the site except by the written permission of the Purchaser. |
| 5. Purchaser's Instructions | 5.1 The Purchaser may, in his absolute discretion, issue from time to time drawings and/ or instructions, directions and clarifications, which are collectively referred to as Purchaser's instructions in regard to: - Any additional drawing and clarifications to exhibit or illustrate details. - Variations or modifications of the design, quality or quantity of work or the additions or omissions or substitution of any work. - Any discrepancy in the drawings or between the schedule of quantities and/or specifications. - Removal from the site of any material brought there by the Bidder/Supplier, which are unacceptable to the Purchaser and the substitution of any other material thereof. Removal and/or re-execution of any work erected by the Bidder/Supplier, which are unacceptable to the Purchaser. - Dismissal from the work of any persons employed there upon who shall in the opinion of the Purchaser, misconduct him, or be incompetent or negligent. - Opening up for inspection of any work covered up. - Amending and making good of any defects. |
| 6. Right Of The Purchaser | 6.1 Right to direct works - The Purchaser shall have the right to direct the manner in which all works under this contract shall be conducted, in so far as it may be necessary to secure the safe and proper progress and specified quality of the works. All work shall be done and all materials shall be furnished to the satisfaction and approval of the Purchaser. - Whenever in the opinion of the Purchaser, the Bidder/Supplier has made marked departures from the schedule of completion or when circumstances or requirement force such a departure from the said schedule, the Purchaser, in order to ensure compliance with the schedule, shall direct the order, pace and method of conducting the work, which shall be adhered to by the Bidder/Supplier. - If in the judgment of the Purchaser, it becomes necessary at any time to accelerate the overall pace of the plant erection work, the Bidder/Supplier, when directed by Purchaser, shall cease work at any particular point and transfer Bidder/Supplier’s men to such other point or points and execute such works, as may be directed by the Purchaser and at the discretion of the Purchaser. 6.2 Right to order modifications of methods and equipment - If at any time the Bidder/Supplier's methods, materials or equipment appear to the Purchaser to be unsafe, inefficient or inadequate for securing the safety of workmen or the public, the quality of work or the rate of progress required, the Purchaser may direct the Bidder/Supplier to ensure safety, and increase their efficiency and adequacy and the Bidder/Supplier shall promptly comply with such directives. If at any time the Bidder/Supplier's working force and equipment are inadequate in the opinion of the Purchaser, for securing the necessary progress as stipulated, the Bidder/Supplier shall if so directed, increase the working force and equipment to such an extent as to give reasonable assurance of compliance with the schedule of completion. The absence of such demands from the Purchaser shall not relieve the Bidder/Supplier of Bidder/Supplier's obligations to secure the quality, the safe conducting of the work and the rate of progress required by the contract. The Bidder/Supplier alone shall be and remain liable and responsible for the safety, efficiency and adequacy of Bidder/Supplier’s methods, materials, working force and equipment, irrespective of whether or not the Bidder/Supplier makes any changes as a result of any order or orders received from the Purchaser. 6.3 Right to inspect the work - The Purchaser’s representative shall be given full assistance in the form of the necessary tools, instruments, equipment and qualified operators to facilitate inspection. - The Purchaser reserves the right to call for the original test certificates for all the materials used in the erection work. - In the event the Purchaser's inspection reveals poor quality of work/materials, the Purchaser shall be at liberty to specify additional inspection procedures if required, to ascertain Bidder/Supplier's compliance with the specifications of erection work. |
| 7.Bidder/Supplier’s Functions | 7.1 The Bidder/Supplier shall provide everything necessary for proper execution of the works, according to the drawings, schedule of quantities and specifications taken together whether the same may or may not be particularly shown or described therein, provided that the same can reasonably be inferred there from and if the Bidder/Supplier finds any discrepancy therein, Bidder/Supplier shall immediately refer the same to the Purchaser whose decision shall be final and binding on the Bidder/Supplier. 7.2 The Bidder/Supplier shall proceed with the work to be performed under this contract in the best and workman like manner by engaging qualified and efficient workers and finish the work in strict conformance with the drawings and specifications and any changes/modifications thereof made by the Purchaser. |
| 8. Variations | 8.1 The Purchaser shall make any variation of the form, quality or quantity of the Works or any part thereof that may, in his opinion, be necessary and for that purpose, or if for any other reason it shall, in his opinion be desirable, he shall have power to order the Bidder/Supplier to do and the Bidder/Supplier shall do any of the following: - Increase or decrease the quantity of any work included in the contract, - Omit any such work, - Change the character or quality or kind of any such work, - Change the levels, lines, position and dimensions of any part of the works - Execute additional work of any kind necessary for the completion of the works and no such variation shall in any way vitiate or invalidate the contract, but the value, if any, of all such variations shall be taken into account in ascertaining the amount of the Contract price. 8.2 The Bidder/Supplier shall make no such variations without an order in writing of the Purchaser. Provided that no order in writing shall be required for increase or decrease in the quantity of any work where such increase or decrease is not the result of an order given under this clause, but is the result of the quantities exceeding or being less than those stated in the Contract/Bill of Quantities. Provided also that if for any reason the Purchaser shall consider it desirable to give any such order verbally, the Bidder/Supplier shall comply with such order and any confirmation in writing of such verbal order given by the Purchaser, whether before or after the carrying out of the order, shall be deemed to be an order in writing within the meaning of this clause. Provided further that if the Bidder/Supplier shall within seven days confirm in writing to the Purchaser and the Purchaser shall not contradict such confirmation in writing within 14 days, it shall be deemed to be an order in writing by the Purchaser. 8.3 All extra or additional work done or work omitted by order of the Purchaser shall be valued at the rates and prices set out in the contract if in the opinion of the Purchaser, the same shall be applicable. If the contract does not contain any rates or prices applicable to the extra or additional work, then suitable rates or prices shall be agreed upon between the Purchaser and the Bidder/Supplier. Any Extra Work, carried out by the Bidder/Supplier would be at mutually agreed. 8.4 Provided that if the nature or amount of any omission or addition relative to the nature or amount of the whole of the works or to any part thereof shall be such that, in the opinion of the Purchaser, the rate or price contained in the contract for any item of the works is, by reason of such omission or addition, rendered unreasonable or inapplicable, then a suitable rate or price shall be agreed upon between the Purchaser and the Bidder/Supplier. In the event of disagreement the Purchaser shall fix such other rate or price as shall, in his opinion, be reasonable and proper having regard to the circumstances. 8.5 Provided also that no increase or decrease mentioned above or variation of rate or price shall be made unless, as soon after the date of the order as is practicable and, in the case of extra or additional work, before the commencement of the work or as soon thereafter as is practicable, notice shall have been given in writing: - By the Bidder/Supplier to the Purchaser of his intention to claim extra payment or a varied rate or price, or - By the Purchaser to the Bidder/Supplier of his intention to vary a rate or price 8.6 If, on certified completion of the whole of the works, it shall be found that a reduction or increase greater than 15 per cent of the sum named in the Letter of Acceptance results from the aggregate effect of all Variation Orders but not from any other cause, the amount of the contract price shall be adjusted by such sum as may be greed between the Bidder/Supplier and the Purchaser or, failing agreement, fixed by the Purchaser having regard to all material and relevant factors, including the Bidder/Supplier's site and general overhead costs of the contract. 8.7 The Bidder/Supplier shall send to the Purchaser’s representative once in every month an account giving particulars, as full and detailed as possible, of all claims for any additional payment to which the Bidder/Supplier may consider himself entitled and of all extra or additional work ordered by the Purchaser which he has executed during the preceding month. 8.8 No final or interim claim for payment for any such work or expense will be considered which has not been included in such particulars. Provided always that the Purchaser shall be entitled to authorize payment to be made for any such work or expense, notwithstanding the Bidder/Supplier's failure to comply with this condition, if the Bidder/Supplier has, at the earliest practicable opportunity, notified the Purchaser in writing that he intends to make a claim for such work. 8.9 The work shall be carried out as approved by the Purchaser or his authorized representative/s from time to time, keeping in view the overall schedule of completion of the project. The Bidder/Supplier’s job schedule must not disturb or interfere with Purchaser’s or the other Bidder/Supplier’s schedules of day-to-day work. The Purchaser will provide all reasonable assistance for carrying out the jobs. 8.10 Night work will be permitted only with prior approval of the Purchaser. The Purchaser may also direct the Bidder/Supplier to operate extra shifts over and above normal day shift to ensure completion of contract as per schedule. Adequate lighting wherever required should be provided by the Bidder/Supplier at no extra cost. The Bidder/Supplier should employ qualified electricians and wire-men for these facilities. In case of Bidder/Supplier’s failure to provide these facilities and personnel, the Purchaser has the right to arrange such facilities and personnel and to charge the cost thereof to the Bidder/Supplier. 8.11 In order to enable the Purchaser to arrange for insurance of all items received at the site including the items of supply covered under this contract, the Bidder/Supplier shall furnish necessary details of all the equipment immediately on its receipt at site, to the Purchaser. Any default on the part of the Bidder/Supplier due to which any item does not get covered under the insurance of the Purchaser; the consequential losses shall be charged to the Bidder/Supplier. 8.12 The Purchaser shall not be liable for or in respect of any damages or compensation payable at law in respect or in consequence of any accident or injury to any workman or other person in the employment of the Bidder/Supplier or any sub-Bidder/Supplier, save and except an accident or injury resulting from any act or default of the supplier, his agents, or servants. The Bidder/Supplier shall indemnify and keep indemnified the Purchaser against all such damages and compensation, save and except as aforesaid and against all claims, proceedings, costs, charges and expenses whatsoever in respect thereof or in relation thereto. 8.13 The Bidder/Supplier shall ensure against such liability with an insurer approved by the Purchaser, which approval shall not be unreasonably withheld, and shall continue such insurance during the whole of the time that any persons are employed by him on the works shall, when required, produce to the Purchaser or Purchaser’s representative such policy of insurance and the receipt for payment of the current premium. Provided always that, in respect of any persons employed by any sub-Bidder/Supplier, the Bidder/Supplier's obligations to ensure as aforesaid under this sub-clause shall be satisfied if the sub-Bidder/Supplier shall have insured against the liability in respect of such persons in such manner that the Purchaser is indemnified under the policy, but the Bidder/Supplier shall require such sub-Bidder/Supplier to produce to the Purchaser or Purchaser's representative, when required such policy of insurance and the receipt for the payment of the current premium. 8.14 Whenever proper execution of the work under the contract depends on the jobs carried out by some other Bidder/Supplier, the Bidder/Supplier should inspect all such erection and installation jobs and report to the Purchaser regarding any defects or discrepancies.The Bidder/Supplier's failure to do so shall constitute as acceptance of the other Bidder/Supplier's installation/jobs as fit and proper for reception of Bidder/Supplier's works except those defects which may develop after execution. Bidder/Supplier should also report any discrepancy between the executed work and the drawings. The Bidder/Supplier shall extend all necessary help/cooperation to other Bidder/Suppliers working at the site in the interest of the work. 8.15 Bidder/Supplier shall carryout final adjustments of foundations, leveling and dressing of foundation surfaces, bedding and grouting of anchor bolts, bed plates etc. required for seating of equipment in proper position. The Bidder/Supplier shall be responsible for the reference lines and proper alignment of the equipment. However, all civil works like making cutouts in walls, floors and ceilings for pipelines shall be done by the purchaser. Adjustment & leveling are to be carried out by the Bidder/Supplier at no extra cost. The Purchaser shall arrange the necessary refilling/repairs of these cutouts and pockets. The Bidder/Supplier should arrange for laying the supports, cutouts, grouting of bolts, etc.When the civil works are in progress, so as to avoid refilling/repair works. The Purchaser at Bidder/Supplier’s costs shall make the damages occurring to civil and other works good. For fixing of piping/equipment supports on wall/beams/roof floor etc., preferably anchor bolts shall be used by the Bidder/Supplier. Drilling of holes for fixing anchor bolts & supply of anchor bolts is in the scope of Bidder/Supplier without any extra cost. 8.16 The Bidder/Supplier shall keep a check on deliveries of the equipment covered in the scope of erection work and shall advise the Purchaser well in advance regarding possible hold-up in Bidder/Supplier's work due to the likely delay in delivery of such equipment/components to enable him to take remedial actions. |
| 9. Duties of the Bidder/Supplier Vis-a-Vis the Purchaser | 9.1 The equipment and the items, if any, to be supplied by the Purchaser for erection, testing and commissioning shall be as listed in the contract. 9.2 Besides the utilities/ services as specified in battery limits, Purchaser shall also provide the following assistance/ facilities to the Bidder/Supplier for carrying out the installation work: - Plant building ready for installation of equipment/items. - Necessary temporary water for carrying out the installation shall be supplied at only one point within the project site by the Purchaser free of charge. All necessary distribution tapings from this point onwards shall be the Bidder/Supplier's responsibility. - Necessary temporary power for carrying out the installation shall be arranged by the Bidder/Supplier at Bidder/Supplier's own cost. The Purchaser on written request by the Bidder/Supplier will issue the necessary authorization letter 9.3 If the power is provided to you, the recovery @2% of total installation charges will be deducted from the erection bill of the Bidder/Supplier. However, the Bidder/Supplier shall supply all the items such as energy meter, switchgear etc. required for getting temporary power. 9.4 The details of temporary water and power requirements shall be furnished one month in advance by the Bidder/Supplier to enable the Purchaser to make timely arrangement. 9.5 If the Bidder/Supplier suffers delay and/or incurs costs from failure on the part of the purchaser to give possession of the civil works in accordance with the mutually agreed schedule, the purchaser shall determine: - Any extension of time to which the Bidder/Supplier is entitled under clause 28 of GCC (General Conditions of Contract) and |
| 10. Supply Of Tools, Tackles And Materials | 10.1 The Bidder/Supplier shall, at his own expense, provide all the necessary equipment, tools and tackles, haulage power, consumables necessary for effective execution and completion of the works during erection and commissioning. |
| 11. Protection Of Plant | 11.1 The Purchaser shall not be responsible or held liable for any damage to person or property consequent upon the use, misuse or failure of any erection tools and equipment used by the Bidder/Supplier or any of Bidder/Supplier's Sub-Bidder/Suppliers even though such tools and equipment may be furnished, rented or loaned to the Bidder/Supplier or any of Bidder/Supplier’s Sub-Bidder/Suppliers. The acceptance and/or use of any such tools and equipment by the Bidder/Supplier or Bidder/Supplier's Sub-Bidder/Supplier shall be construed to mean that the Bidder/Supplier accepts all responsibility for and agrees to indemnify and save the Purchaser from any and all claims for said damages resulting from the said use, misuse or failure of such tools and equipments. 11.2 The Bidder/Supplier and Bidder/Supplier’s Sub-Bidder/Supplier shall be responsible, during the works, for protection of work, which has been completed by other Bidder/Suppliers. Necessary care must be taken to see that the Bidder/Supplier’s men cause no damage to the same during the course of execution of the work. 11.3 All other works completed or in progress as well as machinery and equipment that are liable to be damaged by the Bidder/Supplier's work shall be protected by the Bidder/Supplier and protection shall remain and be maintained until the Purchaser directs its removal. 11.4 The Bidder/Supplier shall effectively protect from the effects of weather and from damages or defacement and shall cover appropriately, wherever required, all the works for their complete protection. 11.5 The Bidder/Supplier shall carry out the work without damage to any work and property adjacent to the area of Bidder/Supplier's work to whomsoever it may belong and without interference with the operation of existing machines or equipment. 11.6 Adequate lighting, guarding and watching at and near all the storage handling, fabrication, pre-assembly and erection sites for properly carrying out the work and for safety and security shall be provided by the Bidder/Supplier at Bidder/Supplier's cost. The Bidder/Supplier should adequately light the work area during nighttime also. The Bidder/Supplier should also engage adequate electricians/wiremen, helper etc to carry out and maintain these lighting facilities. If the Bidder/Supplier fails in this regard, the Purchaser may provide lighting facilities as he may deem necessary and charge the cost thereof to the Bidder/Supplier. 11.7 The Bidder/Supplier shall take full responsibility for the care of the works or any section or portions thereof until the date stated in the taking over certificate issued in respect thereof and in case any damage or loss shall happen to any portion of the works not taken over as aforesaid, from any cause whatsoever, the same shall be made good by and at the sole cost of the Bidder/Supplier and to the satisfaction of the Purchaser. The Bidder/Supplier shall also be liable for any loss of or damage to the works occasioned by the Bidder/Supplier or the Bidder/Supplier’s Sub-Bidder/Supplier in the course of any operations carried out by the Bidder/Supplier or by the Bidder/Supplier’s Sub-Bidder/Suppliers for the purpose of completing any outstanding work or complying with the Bidder/Supplier's obligations. |
| 12. Unloading, Transportation and Inspection | 12.1 The Bidder/Supplier agent/authorised personnel should be present at site during unloading of materials/equipment. The Bidder/Supplier shall be required to unload all the materials/equipment from the carriers, those received at site. The Bidder/Supplier shall plan in advance requirement of various tools, tackles, jacks, cranes, sleepers etc. required to unload the material/equipment promptly and efficiently. The Bidder/Supplier shall ensure that adequate and all measures necessary to avoid any damage whatsoever to the equipment at the time of unloading are taken. 12.2 Any demurrage/detention charges incurred due to the delay in unloading the material/equipment and releasing the carriers shall be on the Bidder/Supplier's account. 12.3 The Bidder/Supplier shall be responsible for the reception on site of all plant and Bidder/Supplier's equipment delivered for the purposes of the contract. 12.4 The Bidder/Supplier shall safely transport/shift the unloaded materials/equipment by the Bidder/Supplier to the storage area. |
| 13. Storage Of Equipment | 13.1 The Bidder/Supplier shall be responsible for the proper storage and maintenance of all materials/ equipment under Bidder/Supplier's custody. Bidder/Supplier shall take all required steps to carry out frequent inspection of equipment/materials stored as well as erected equipment until the same are taken over by the Purchaser. The following procedure shall apply for the same. 13.2 The Bidder/Supplier’s inspector shall check stored and installed equipment/materials to observe signs of corrosion, damage to protective coating to parts, open ends in pipes, vessels and equipment, insulation resistance of electrical equipment etc. The Bidder/Supplier shall immediately arrange a coat of protective painting whenever required. A record of all observations made on equipment, defects noticed shall be promptly communicated to the Purchaser and Purchaser's advice taken regarding the repairs/rectification. The Bidder/Supplier shall there upon carry out such repairs/ rectification at Bidder/Supplier’s own cost. In case the Bidder/Supplier is not competent to carry out such repairs/ rectification, the Purchaser reserves the right to get this done by other competent agencies at the Bidder/Supplier's responsibility and risk and the entire cost for the same shall be recovered from the Bidder/Supplier's bills. 13.3 The Bidder/Supplier's inspector shall also inspect and provide lubrication to the assembled equipment. The shafts of such equipment shall be periodically rotated to prevent rusting as well as to check freeness of the same. 13.4 The Inspector shall check for any signs of moisture or rusting in any equipment. 13.5 If the commissioning of equipment is delayed after installation of the equipment, the Bidder/Supplier shall carry out all protective measures suggested by the Purchaser during such period. 13.6 Adequate security measures shall be taken by the Bidder/Supplier to prevent theft and loss of materials handed over to the Bidder/Supplier by the Purchaser. The Bidder/Supplier shall carry out periodical inventory checks of the materials received, stored and installed by the Bidder/Supplier and any loss noticed shall be immediately reported to he Purchaser. The Bidder/Supplier shall maintain a proper record of these inventories. The Bidder/Supplier should not sell, assign, mortgage, hypothecate or remove equipment or materials which has been installed or which may be necessary for completion of the work without the written consent of the Purchaser. 13.7 Suitable grease recommended for protection of surfaces against rusting (refined from petroleum oil with lanolin minimum (70°C) and water in traces) shall be applied over all equipment as required once in every six months. 13.8 All equipment shall be stored inside a closed shed or in the open depending upon whether they are of indoor or outdoor design. The space heaters where provided into the electrical equipment shall be kept connected with power supply irrespective of their type of storage. Where space heaters are not provided adequate heating with bulb is recommended. For transformers heating of oil shall be done by giving 440 V supply and short-circuiting the LT terminals. Frequent checks on insulation resistance are essential for all electrical equipment and record of the inspection reports and mugger readings shall be maintained equipment wise. Such records shall be presented to the Purchaser whenever demanded. 13.9 All the necessary items/goods required for the Bidder/Supplier as described above shall arrange protection and such cost shall be included in the Contract price. |
| 14. Approvals | 14.1 The Bidder/Supplier shall obtain the necessary approvals of the Factory Inspector, Boiler Inspector, Electrical Inspector, Weights & Measures Inspector, Explosive Inspector and local authorities as may be required and the cost of obtaining such approvals shall be included in the contract price. 14.2 The Bidder/Supplier will furnish all the necessary details, drawings, and submission of application and proofreads to the Purchaser for verification/ signature. The Bidder/Supplier on behalf of the Purchaser shall submit the necessary application duly filled-in, together with the prescribed fees to the appropriate authorities. However all the actual statutory prescribed fees paid by the Bidder/Supplier shall be reimbursed by the Purchaser upon production of the receipt/vouchers. 14.3 Wherever necessary or required, the Bidder/Supplier shall furnish the necessary test and/or inspection certificates etc. from the appropriate authorities as per statutory regulations and the cost for obtaining these certificates shall be in the cost of Bidders. |
| 15. Review & Co--Ordination of Erection Work | 15.1 The Bidder/Supplier shall depute senior and competent personnel to attend the site coordination meetings that would generally be held at the site every month. The Bidder/Supplier shall take necessary action to implement the decisions arrived at such meetings and shall also update the erection schedule. |

Table 1

List of Drawings required Submission

SN 			Drawings

1 	GA drawings for major new fabricated equipment to be supplied.

2 	Plant Layout Drawing.

- Revised P& ID.

4	General Piping layout drawing for the new piping being done

5 	Electrical cable, conduit/ cable tray layout, for new cables being laid, WHEREVER REQUIRED.

Sub Section 2

Special Conditions of Contract

For

Mechanical Works

Contents

- Scope

- General Installation

- Service Piping Installation

- Special Instructions And Specifications

- Insulation of Piping and Equipment

- Interconnections of Services

- Guidelines For Expansion Work

- Cleaning Chemicals and Lubricants

- Testing, Commissioning and Start-Up

- Trouble shooting during the trial period

- Painting

- Code of Practice for Painting Service Pipe Lines

Table 1 Painting of Equipment & Structural Work

Table 2 Color Code For Pipelines as per ISO/bidders respective national standard or equivalent standard

Table 3 Testing Pressures for Various Pipelines

Table 4 Makes of Bought Out Items

| # 1. Scope | - General installation i.e. positioning and installing all the production, miscellaneous and service equipment as per approved layout drawings and as per the contract. - Supply and installation of structural platforms and tables. - Supply and installation of all service and product piping including ancillary items. - Insulation and cladding of piping, equipment including supply of materials. - Interconnections of services and Electrical with equipment. - Guide line for expansion work. - Clean up of work site. - Supply of all cleaning chemicals and lubricants. - Testing, commissioning and start-up. - Painting including supply of paints as approved by the Purchaser. - Training of personnel. - Detailed specifications are given in the subsequent clauses. |
| --- | --- |
| # 2. General Installation | - Positioning of Equipment - The work involves preparation of access for moving of the plant and equipment including their fittings from the work site Godown or from the place within the site where they have been unloaded, to the place of erection, de-crating and placing on the foundation wherever required. The Purchaser shall arrange all the civil foundations as per the manufacturer/Bidder/Supplier’s drawings. The Bidder/Supplier shall place the equipment and carry out final adjustment of the foundations including alignment and dressing of foundation surface, embedding and grouting of anchor bolts and bedplates. The Bidder/Supplier shall be responsible for obtaining correct reference lines for the purpose of fixing the alignment of various equipments from master benchmarks provided. Tolerances shall be as specified in equipment manufacturer's drawings or as stipulated by the Purchaser's Engineer. No equipment shall be permanently bolted down to foundations or structure until the Bidder/Supplier has checked the alignment and witnessed by the Purchaser. The Bidder/Supplier shall carry out minor alterations in the anchor bolts, pockets etc., at no extra cost and set the equipment properly as per approved layout, drawings and manufacturer's instructions. The Bidder/Supplier shall supply all the necessary foundation/anchor bolts and bedplates if required without extra cost if these have not been provided with main equipment. - The Bidder/Supplier shall supply, fix and maintain, at his own cost, during the erection work, all the necessary centering, scaffolding, staging required not only for proper execution and protection of the said work but also for protection of the surrounding plant and equipment. The Bidder/Supplier shall take out and remove any or all such centering, scaffolding, staging planking etc., as occasion shall require or when ordered to do so and shall fully reinstate and make good all things disturbed during execution of the work, to the satisfaction of the Purchaser. The Bidder/Supplier shall be paid no additional amount for the above. ## Structural Platforms and Tables - Structural platforms shall be required to provide access for various equipment. Tables shall be required for handling products. These platforms and tables shall be fabricated keeping stability and other functional as well as aesthetic requirements into consideration as approved by the Purchaser. |
| # 3. Service Piping Installation | ## General Guidelines - All piping systems shall comply with the latest editions as applicable. ## Scope of Supply - The Bidder/Supplier shall supply all piping materials like pipes, fittings, flanges, measuring instruments and all other items as shown in the P&I diagram/specifications and schedule of quantities. All the pipes & fittings and insulation material etc. should be of class and make as approved by the Purchaser. The Bidder/Supplier, for the class and make of all materials, must obtain prior approval of the Purchaser. The Bidder/Supplier should furnish the details of makes selected by him, in the pro forma given in Table 5. ## Scope of Piping Erection - The scope of erection for piping, includes all system covered in the flow diagrams and specifications. The Bidder/Supplier's work commences/ terminates at the pipe connections with valves or flanges as specified in flow diagrams/ battery limits. - The Bidder/Supplier shall also install necessary piping and any specialties furnished with or for equipment such as relief valves, built-in-bypass, primary elements for flow measurements, control valves and on-line metering equipment. - The Bidder/Supplier shall perform necessary internal machining of pipes for installing orifices, flow nozzles, control valves etc. The Bidder/Supplier shall install all pipes, valves and specialties. ## Testing of Piping - The Bidder/Supplier shall test sample piping systems including valves and specialties and instruments as required. - All piping shall be internally cleaned and flushed by the Bidder/Supplier after erection in a manner suited to the service. - For hydrostatic testing and water flushing, the Bidder/Supplier shall furnish necessary pumps, equipment, instruments and piping etc, if required. ## Other Guidelines - Color code shall be used to identify pipe material. The Bidder/Supplier shall be able to identify on request all random piping prior to field fabrication. - The Bidder/Supplier shall be responsible for the quality of welding done by them and shall conduct tests to determine the suitability of the welding procedure by him. - All piping supports, guides, anchors, hangers, rollers with structural framework shall be supplied and erected by the Bidder/Supplier. The kinds of pipe supports like CI clamps, wooden saddles, roller supports and support framework shall be as per the design approved by the Purchaser prior to taking up the work. - All piping shall be suspended, guided and anchored with due regard to general requirements and to avoid interference with other pipes, hangers, electrical conduits and their supports, structural members and equipment and to accommodate insulation and conform to buildings structural limitations. It is the responsibility to the piping Bidder/Supplier to avoid all interference while locating hangers and supports. - Anchors and/or guides for pipelines or for other purposes shall be furnished, when specified, for holding the pipeline in position for alignment. Hangers shall be designed fabricated and assembled in such a manner that any movement of the support pipes cannot disengage them. - All piping shall be wire brushed and purged with air blast to remove all rust, mill scale from inner surface. The method of cleaning shall be such that no material is left on the inner or on outer surfaces, which will affect the serviceability of the pipes. - Effective precautions such as capping and sealing shall be taken to protect all pipe ends against ingress of dirt and damage during transit or storage. The outside of the steel pipes (black) shall be painted with two coats of red oxide paint or as directed by the Purchaser. |
| # 4. # Special Instructions & Specification | ## Steam Piping - Steam piping work can be classified into two categories: - High-pressure steam piping when the working pressure of steam is morethan 3.1 kg/cm2 (50 psi). - Low-pressure steam piping when the working pressure of steam is up to 3.1 kg/cm2 (50 psi). - All the pipes and fittings used for high pressure steam piping work should conform to ISO/bidders respective national standard or equivalent standard should be certified and also to be identified with number and mark showing that they are tested by the Boiler Inspector and supported with duly authentic certificates to this effect. ALL HIGH PRESSURE STEAM PIPES SHOULD BE SEAMLESS TYPE. - The high-pressure steam piping work should also include fabrication and installation of pressure reducing stations strictly conforming to ISO/bidders respective national standard or equivalent standard. ## Other Piping - ALL THE PIPING FOR CHILLED WATER, GLYCOL, AMMONIA, SOFT AND RAW WATER, H.P. AND L.P. STEAM, AIR AND FURNACE OIL/ LSHS PIPING SHALL GENERALLY BE OF WELDED CONSTRUCTION. Whenever welding is done for pipes of smaller size special care should be exercised to avoid clogging of flow area with the welding material. |
| # 5. Insulation of Piping and Equipment | ## Cold Insulation of Chilled Water, Glycol and Ammonia Pipeline - All the chilled water, glycol & ammonia pipelines shall be insulated by PUF pipe sections. The insulation shall be carried out in the following manner: - Before starting insulation work all pipelines shall be tested as specified. - The surface of the pipes to be insulated should be properly cleaned. - Hot bitumen of 85/40 or 85/25 conforming to ISO/bidders respective national standard or equivalent standard should be applied uniformly @ 1.5 kg/m2 on the surface of the pipes. - A similar layer of bitumen should be applied on the inner surface and on the edges of the insulation sections. - The sections should then be stuck to the coated pipes with joints staggered. Adjacent sections should be tightly pressed together. All joints should be properly sealed with bitumen. - A thick vapor seal with hot bitumen @ 2.5 kg/m2 should be applied uniformly on the outer surfaces of the pipe sections and allowed to dry. - The thickness of insulation shall be as required. ## Insulation of Chilled Water Tank - The surfaces shall be cleaned with the help of brushes to remove any loose particles. - A coat of bitumen of 85/40 or 85/25 conforming to ISO/bidders respective national standard or equivalent standard @1.0 kg/m2 shall be applied over the flooring and walkathon sheets shall be press-laid to act as a vapor barrier. - Bitumen shall then be applied on the walkathon sheets and one side and edges of the insulation slabs to ensure total rate of 2.00 kg/m2 between contacting surfaces. The slabs shall then be fixed in position, making sure that there shall be no joints between slabs. - For double layers insulation bitumen shall again be applied on all contacting surfaces to ensure a total rate of 1.5 kg/m2 between contacting surfaces. - A coat of bitumen at 1.5 kg/m2 shall be applied over the insulation surfaces. ## 5.3 Hot Insulation of Steam, Condensate & Hot Water Pipe Lines - All the steam and hot water pipelines shall be insulated with mineral wool or equivalent of specified thickness. The insulation shall be carried out in the following manner and should be supplied in the form of properly required sizes. - Clean the surfaces to be insulated. Apply a coat of red oxide primer and fix glass wool/mineral wool of specified thickness, tightly to the pipes, butting all joints and tie with lacing wire. - It should then be covered with GI wire netting of 20 mm x 24 SWG. - In case the insulation does not have the desired insulation properties, the entire insulation will have to be redone at the Bidder/Supplier's cost to give the desired results. - In case of condensate return piping all the steps mentioned above shall be executed except that thickness of the insulation shall be 25 mm. ## 5.4 Aluminum/ GI Cladding/ Cement Plaster - The chilled water, glycol, ammonia, water, steam & hot water lines after insulations may be covered by/GI cladding or cement plaster. The payment will be made as per the executed items. - Aluminum cladding will be done with 22 gauge aluminum sheet with proper grooves and overlaps and screwed in position with 12 mm self tapping parker screws. - GI sheet cladding will be done with 22 gauge sheet with proper grooves and overlaps and screwed in position with 12 mm self tapping parker screws. The GI sheet cladding will finally painted 2 (coats) by approved shade and quality of paint. - In case of cement plaster, the finishing will be done with 12 mm thick sand cement plaster (1:4) over chicken wire mesh. |
| # 6. Interconnections of Services | 6.1 The Bidder/Supplier shall lay service piping and provide connections with the equipment complying strictly with the equipment manufacturers' instructions. The Bidder/Supplier shall also carry out all the interconnecting service piping with the various items of plant/system. The work shall be complete with capillary piping if required and connections with instruments and controls supplied with the equipment. 6.2 The Bidder/Supplier shall also carry out electrical connections for equipment with the control panels including equipment lighting as per the wiring diagrams of the equipment Bidder/Suppliers. Connection shall be made for small electrically operated devices on equipment installed as accessories to, or assembled with equipment. Connections regarding instruments, float switches, limit switches, pressure switches, thermostats and other miscellaneous equipment shall be done as per manufacturers' drawings & instructions. |

| # 7. Guidelines For Expansion Work | ## 7.1 Shutdowns - Plant shutdown shall be required for making tapings/ interconnections of the new equipment/ piping, to be installed under expansion, with the existing equipment/piping. These shut downs should be planned carefully well in advance to enable the Purchaser to take suitable actions for minimum shutdown period. The details of shut downs, the numbers and duration should be worked out and intimated to the Purchaser for approval. The Bidder/Supplier should ensure completion of all the necessary works well within the allowed time so that no inconvenience is caused in regular operation and working of the existing plant. ## 7.2 Cleanliness - Wherever the Bidder/Supplier is required to work in existing plant area he should take due care and extra precautions to ensure absolute cleanliness and minimum hindrance for proper working of the existing plant. ## 7.3 Change over - The programmers for change over from existing plant system to new plant system should be prepared by the Bidder/Supplier and should be got approved by the Purchaser. ## 7.4 Clean Up of Works Site - All soils, filth or other matters of an offensive nature taken out of any trench, drain or other places shall not be deposited on the surfaces, but shall at once be carted away by the Bidder/Supplier from the site of work for proper disposal. - The Bidder/Supplier shall not store or place the equipment, materials or erection tools on the drive ways and passages and shall take care that his work in no way restricts or impedes traffic or passage of men and materials during erection, the Bidder/Supplier shall without any additional payment, at all time keep the working and storage area used by him free from accumulation of dust or combustible materials, waste materials rubbish packing, wooden planks to avoid fire hazards and hindrance to other works. - If the Bidder/Supplier fails to comply with these requirements in spite of written instructions from the Purchaser, the Purchaser will proceed to clear these areas and the expenses incurred by the Purchaser in this regard shall be payable by the Bidder/Supplier. Before completion of the work, the Bidder/Supplier shall remove or dispose off in a satisfactory manner all scaffolding, temporary structures, waste and debris and leave the promises in a condition satisfactory to the Purchaser. Any packing materials received with the equipment shall remain as the property of the Purchaser and may be used by the Bidder/Supplier on payment of standard charges to the Purchaser and with prior approval of the Purchaser. At the completion of his work and before final payment, the Bidder/Supplier shall remove and shall restore the site to neat workman like conditions at his cost. |
| --- | --- |
| # 8. Cleaning Chemicals and Lubricants | 8.1 The necessary quantities of cleaning chemicals, lubricants etc., required for the installation, commissioning, testing and start-up of all the equipment till handing over are to be supplied the Bidder/Supplier and nothing extra would be paid for these. |
| # 9. # Testing, Commissioning and Start-up | 9.1 The Bidder/Supplier shall operate, maintain and give satisfactory trial run of the plant for the design product satisfactorily for a maximum period of one week or as mutually agreed by Bidder/Supplier/purchaser/Purchaser of the plant at the rated output. The Bidder/Supplier should carry out all rectification of damages/defects and routine troubleshooting during commissioning with the help of purchaser’s staff. 9.2 During this period, Bidder/Supplier shall incorporate/execute necessary minor modifications during the trial period for maximizing operational efficiency. The Bidder/Supplier should also execute minor modifications as may be suggested by the manufacturer/Purchaser, if required. The Bidder/Supplier shall suggest recommended log sheet proofread for recording necessary operating data and pass it on to the Purchaser in proof of satisfactory rated output and performance of the equipment/plant. 9.3 The commissioning shall also include, for all the equipments, the following: - Field disassembly and assembly - Clean out of lubrication system including chemical cleaning wherever required. - Circulation of lubricant to check flow. - Clean out and check out of all the service lines. - Check out and commissioning of instruments, equipment and plants, filtering of transformer and other oils so that if deteriorated, they shall attain the required properties/standards, specified tests in this regard must be carried out by approved authorities and their satisfactory reports submitted to the Purchaser before start-up. - Recharging or make-up filling of lubricant oil up to the desired level in the lubrication system of individual machine. - Operation in empty condition to check general operation details wherever required and wherever possible. - Closed loop dynamic testing with water wherever required. - Operation under load and gradual load increase to attain maximum rated output. |
| # 10. Trouble shooting during the trial period | 10.1 The Bidder/Supplier shall demonstrate proper working of all mechanical and electrical controls; safety and protective device, in presence of the Purchaser's engineer and the same should be duly recorded. 10.2 After conducting testing, in case particular equipment is not working properly or not giving rated output the Bidder/Supplier will furnish a detailed report to the Purchaser stating therein the detailed account on the performance of the equipment with possible reasons for improper or not working of the same. 10.3 The Purchaser after receipt of report from the Bidder/Supplier would take up the matter with the manufacturers and if required would invite the representative of original manufacturers. In case the Purchaser considers that the non-performance of equipment is only due to inexperience of the Bidder/Supplier, then the charges incurred for the manufacturer's representative visit would be debited to the Bidder/Supplier's account. 10.4 Further, before the commencement of testing or commissioning, the Purchaser reserves the right to invite the original manufacturer's representative at the cost of the Bidder/Supplier for start-up help, assist and guide the Bidder/Supplier during commissioning in the following cases: - The Bidder/Supplier has no previous experience of commissioning and start-up of the similar equipment. - The Purchaser is of the opinion that the Bidder/Supplier is not capable to commission and start-up of certain specific equipment. 10.5 However, in either of the cases the manufacturer's representatives would be called with prior information to the Bidder/Supplier and the Bidder/Supplier will have to extend all co-operations to such representatives in good spirit and in the interest of the work. 10.6 After satisfactory commissioning and start-up the Bidder/Supplier shall keep his representatives under whose supervision the Purchaser's staff shall be operating and maintaining the plant and equipment for a minimum period of one month. The Bidder/Supplier's representatives should be present at all times during the running and operation of plant and equipment. During this period the Bidder/Supplier shall ensure proper working of complete plant and equipment and attend any works required to be done and shall also take complete responsibility for proper operation and maintenance of the complete plant and equipment. |
| # 11. Painting | 11.1 All the equipment/ machineries like motors, pumps, HT/ LT panel, transformer, switch boards, starters, junction boxes, isolators, storage tanks, supporting structures, pipe supports and MS/ GI pipes and all exposed and visible iron parts included in the scope of erection/ commissioning shall be given double coat of paint of approved shade over a double coat of anticorrosive primer wherever necessary irrespective of the condition of original paint of equipment/ machineries/ structures/ supports. All surfaces, wherever required must be properly cleaned from scale, dirt and grease prior to painting. Spray painting must preferably be used on all the equipment/ machineries and wherever practicable. Suitable and necessary cleaning/ wiping of sight/ dial glasses, other non-metallic parts, flooring, walls and other surfaces which have been spoiled by paint during painting must also be carried out by the Bidder/Supplier. 11.2 Lettering and other markings, including capacity and flow direction markings, shall also be carried out by the Bidder/Supplier on the tanks, pipe lines, starters, motors, isolators and wherever else necessary, as directed and as per the standard practice of installation. ISO/bidders respective national standard or equivalent standard color codes and color charts as mentioned in Table 3 & Table 2 must be adhered to. 11.3 Supply of all paints and all other materials required is included in the scope of supply of the Bidder/Supplier under this contract/order. |

| # 12. Code of Practice for Painting Service Pipe Lines | ## 12.1 On Non-insulated Pipe Line & Insulated Pipeline without Aluminum Cladding - Ground color to be applied throughout the length of the pipeline. - Color bands to be applied near every valve and branch connection as well as in every room near the entry. - The 1st band should be 4" wide and the second band should be 1" wide. - On the 1st band a white arrow to be put to indicate the direction of flow. - The arrows should be put on the bottom of the pipelines so that the same are visible from below in case of horizontal bank of pipes and on sides in case of vertical bank of pipes. - The valves should be painted with the same color as the ground color of the pipeline. ## 12.2 On Insulated Pipeline with Aluminum Cladding - Ground color to be applied in a length of 500 mm of the pipe all round near every valve and branch connections as well as in every room near the entry. The complete length of the pipeline should not be painted. - Color bands should be applied in the middle of every ground color strip. The 1st color band should be 4" wide and the second band should be 1" wide. - On the 1st band a white arrow is to be put to indicate the direction of flow of the fluid. - The arrows should be put on the bottom of the pipelines, so that the same are visible from below in case of horizontal bank of pipes and on sides in case of vertical bank of pipes. - The valves should be painted with the same color as the ground color. - The ground colors and the colors of the 1st and 2nd color bands have been indicated on the enclosed list for the pipelines carrying various types of fluids and gases. The list also indicates the shade nos. of the colors to be used. In case the exact shade is not available, the nearest possible shade in the same color may be selected. - Only synthetic enamel paint should be used for the painting and band markings on the pipelines and it should be ensured that the finish should be glossy. - Where no color bands have been recommended, only the ground color is to be applied as per the above procedure. If only one color band is recommended the same should be 4" wide and applied on the ground color. In case of 2 nos. color bands, the 1st band should be 4" wide and second band 1" wide and should be applied on the ground color. - To avoid mixing of colors, it is recommended to apply the bands only after the ground color paint is dry and subsequently to apply the arrow only after the 1st band paint is dry. |
| --- | --- |

| Table 1 Painting of Equipment & Structural Work |  |  |
| --- | --- | --- |
| SN | Item | Painting Shade |
| 1 | All M.S. platforms/pipe supports/ pipe bridges and any other structures | Dark admiral grey shade |
| 2 | Pumps, Geared Motor, Fan, Steam Heater | Original colour |
| 3 | HT & LT panels | Original colour |
| 4 | LT distribution switchboards | Dark admiral grey |
| 5 | Powder Plant Chimney | Aluminium Paint |
| 6 | Refrigeration Compressor, air Compressor | Original colour |

| Table 2 Color Code For Pipelines as per ISO/bidders respective national standard or equivalent standard |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN |  | Services | Ground Color |  |  |  | First Band |  |  | Second Band |  |
| 1 |  | Cooling Water | Sea Green |  |  |  | French Blue |  |  | - |  |
| 2 |  | Boiler Feed Water |  |  |  |  | - |  |  | - |  |
| 3 |  | Condensate |  |  |  |  | Light Brown |  |  | - |  |
| 4 |  | Hot Water |  |  |  |  | Light Brown |  |  | - |  |
| 5 |  | Drinking Water |  |  |  |  | French Blue |  |  | Signal Red |  |
| 6 |  | Treated Water |  |  |  |  | Light Orange |  |  | - |  |
| 7 |  | Cold Water |  |  |  |  | French Blue |  |  | Canary Yellow |  |
| 8 |  | Untreated Water |  |  |  |  | White |  |  |  |  |
| 9 |  | Compressed Air | Sky Blue |  |  |  |  |  |  |  |  |
| 10 |  | Vacuum |  |  |  |  | Black |  |  |  |  |
| 11 |  | Steam | Silver Grey |  |  |  |  |  |  |  |  |
| 12 |  | Diesel | Light Brown |  |  |  | Brilliant |  |  |  |  |
| 13 |  | Lubricating Oil |  |  |  |  | Light Grey |  |  |  |  |
| 14 |  | Drainage | Black |  |  |  |  |  |  |  |  |
| 15 |  | Ammonia | Signal Red |  |  |  |  |  |  |  |  |
|  | Table 3 Testing Pressures for Various Pipelines |  |  |  |  |  |  |  |  |  |  |
|  | Sr No | Name |  | Test Pressure kg/cm2 |  | Test medium |  | Duration of Test (Hour) |  |  | Allowable pressure Drop (kg/cm2) |
|  | 1 | H.P.Steam pipe lines |  | 27 |  | Water |  | 1/2 |  |  | 0 |
|  | 2 | H.P.Steam pipe lines |  | 8 |  | Water |  | 1/2 |  |  | 0 |
|  | 3 | Water pipe lines1 |  | 8 |  | Water |  | 1/2 |  |  | 0 |
|  | 4 | Furnace oil/ LSHS |  | 16 |  | Water |  | ½ |  |  | 0 |
|  | 5 | SS pipes for dairy |  | 6 |  | Water |  | 1/2 |  |  | 0 |
|  | 6 | Air |  | 12 |  | Air |  | 8 |  |  | 0.1 |
|  | 7 | Ammonia pipe lines |  |  |  |  |  |  |  |  |  |
|  | 7a | Suction |  | 16 | N2 |  |  |  | 24 |  | 0.2 |
|  | 7b | Discharge |  | 24 | N2 |  |  |  | 24 |  | 0.2 |
|  | 7c | Vacuum Test of Ammonia Lines |  | Absolute Zero | Vacuum |  |  |  | 48 |  | NIL |
|  | 8 | Molasses pipe lines |  | 16 | Water |  |  |  | 1/2 |  | 0 |
|  | Engineer-in-charge shall provide water at available supply point from which the Supplier shall connect temporary piping for testing water. |  |  |  |  |  |  |  |  |  |  |

| Table 4 Makes of Bought Out Items |  |  |
| --- | --- | --- |
| SN | Items | Makes |
| 1 | Steam piping |  |
| 1a | MS C class pipes (Seamless) |  |
| 1b | Cast steel globe valves |  |
| 1c | Bronze globe valves |  |
| 1d | Non-return valves |  |
| 1e | Pressure reducing valves, safety valves, expansion joints and other steam fittings. |  |
| 1f | Pressure & temperature gauges |  |
| 2 | Furnace oil piping/ air piping |  |
| 2a | MS C class pipes (seamless/ ERW as approved) |  |
| 2b | Cast steel globe/bronze globe/ Gun metal gate valve |  |
| 2c | Pressure gauges |  |
| 3 | Water piping |  |
| 3a | GI `B' class pipe |  |
| 3b | CI globe valve |  |
| 3c | Gun metal gate valve |  |
| 3d | Gun metal globe valves/ strainers/ non return valves |  |
| 3e | Water pump |  |

##### Sub- Section 3

##### Special Conditions of Contract

##### For

##### Electrical Works

Contents

- Scope

- Standards

- Equipment And Accessories Specifications

- Power Cables (HT)

- Power Cables (LT)

- Control Cables

- Cable Trays

- Cable Glands

- Cable Connectors

- Cable Route Markers

- Cable Indicators

- Pipes for Cables

- Motor Isolators

- Motor Junction Box / Control Junction box

- Remote Push Button Stations (for other projects)

- Erection Of Equipment

- Power Control Centres, Distribution Boards, Control Panels & Bus Ducts

- Seal Maintenance Free Batteries & Battery Charger

- Erection and Testing of Motors

- Installation of Cable Network

- General Requirements for handling of Cables

- Laying of Cable (Underground System)

- Laying of Cable Under Floors

- Laying of Cable in Masonry trenches

- Laying of Cable in Cable Trays

- Laying of Cables on Building Surface/Structure

- Termination & Jointing of cables

- Dressing of Cables Inside the Equipment

- Identification of Cables/ Wires/ Cores

- Cable between Isolators/Junction Box and Motor/Control

- Testing of cables

- Earthing Network

- Earth Pit with Electrode

- Earth Bus, Earthing Lead and Earth Wire/Strip

- Two/Four Pole Structure

- Erecetion Procedure Guidelines for Instrumentation & Control System

Table 1  ISO/bidders respective national standard or equivalent standard

Table 2 Proforma for PCC, DB, Motor Control Centres Test

Table 3 Proforma for motor testing

Table 4 Proforma for Testing Cables

Table 5 Recommended Cables Sizes For Industrial Wiring

Table 6 Sizing of Earthing Lead/ Wire

| # 1. Scope | 1.1 The intent of this specification is to define the requirements for the installation, testing and commissioning of the electrical system like high-tension switchyard with accessories and equipment, transformers, HT. Panels, oil circuit breakers, LT. Panels and power control centers, distribution boards, capacitor banks & panels, power & control cables, remote push button stations, motors, earthling network, etc. Requirement of a particular project shall be as specified in schedule of quantities/approved drawings or as per the battery limits fixed in the contract. |
| --- | --- |
| # 2. Standards | 2.1 The work shall be carried out in the best workmanship in conformity with this specification, the relevant specification/codes of practice of the ISO/bidders respective national standard or equivalent standard, approved drawings and the instructions issued by the Engineer-in-charge or his authorized representative, from time to time 2.2 In addition to these standards, all works shall also confirm to the requirements of the followings: - Act and Rules framed there under. - Fire Insurance Regulations. - Regulations lay down by the Electricity Board. - Regulations lay down by the Factory Inspector - Any other regulations lay down by the local authorities. - Installation & operating manuals of original manufacturers of equipment. |
| # 3. Equipment and Accessories Specifications | 3.1 This defines specifications and requirements mainly for the equipment and accessories which are generally supplied by the erection agency and do not cover the specification of main electrical equipment such as Transformers, HT and LT panels, switchboards and motors etc which may be supplied by the Owner. 3.2 All materials, fittings and appliances to be supplied by the Bidder/Supplier shall be of best quality and shall conform to the specification given hereunder. The equipment shall be manufactured in accordance with current ISO/bidders respective national standard or equivalent standard Specifications wherever. In the absence of any specification, the materials shall be as approved by the Owner or his authorized representative. 3.3 All similar materials and removable parts shall be uniform and interchangeable with one another. 3.4 You must furnish makes of bought out items. |
| # 4. Power Cables (HT) | 4.1 Specifications as per Section |
| # 5. Power Cables (LT) | 5.1 Specifications as per Section |
| # 6. Control Cables | 6.1 Specifications as per Section |
| # 7. Cable Trays | 7.1 Specifications as per Section |
| # 8. Cable Glands | 8.1 These shall be provided at both ends of armored/ unarmored electrical cables. Cable glands to be manufactured as per performance requirements of ISO/bidders respective national standard or equivalent standard amended as on date, with BRASS material accurately machined and NICKEL finish. Single compression cable glands to be complete with checkout, gland body, 3 nose metal washers, and outer seal rubber ring and compression nut. Double compression glands to be complete with checkout, gland body, neoprene outer ring, Armor clamping cone, Armor clamping ring, Armor clamping nut, neoprene outer ring, skid washer & outer seal nut. Sample of cable gland to be got approved from the Site In charge before supply For instruments MOC of cable gland shall be polyamide. |
| # 9. Cable Connectors | 9.1 Cable connectors, lugs/sockets, shall be of copper/Aluminum alloy, suitably tinned, soldering less, crimping type. These shall be suitable for the cable being connected and type of function (such as power, control or connection to instruments, etc.) |
| # 10. Cable Route Markers | 10.1 These shall be galvanized Cast Iron plate with marking (LT/HT) diameter 150 mm with 600 mm long 25x25 mm MS. angle riveted/bolted with this plate. Sample to be got approved before use. |
| # 11. Cable Indicators | 11.1 Individual symbols / numbers printed on yellow strips of glossy PVC should be used for cable indicator. |
| # 12. Pipes for Cables | 12.1 For lying of cables under floor, G.I. class 'A' pipes shall be used. MS. Conduits are not acceptable for this purpose. For laying cable in air whereas cable trays are not being used, MS `B' class pipe shall be used. Size of pipe shall depend upon the overall outer diameter of cable to be drawn through pipe. To determine the size of pipe, assume that 40% area of pipe shall be free after drawing of cable. In dairy's process area and powder plant wherever required SS-304 pipe, 1.6 mm thick shall be used. |
| # 13. Motor Isolators | 13.1 These shall be in Aluminum cast housing, completely dust, vermin and weather proof (IP 55), suitable for 30/25 A, 415 volts, 50 Hz with rotary type switch complete with cable gland for incoming and outgoing cables. For dairy's process area and powder plant SS-304 motor isolator shall be used. Final finish of housing to be buffer mirror for SS and powder coated gray for Aluminum housing. Sample to be got approved before supply. |
| # 14. Control Junction Box | 14.1 These shall be in Aluminum cast housing, completely dust, vermin and weather proof (IP 55). For dairy's process area and powder plant SS-304 junction box shall be used. Final finish of housing to be buffer mirror for SS and powder coated gray for Aluminum housing. Sample to be got approved before use. |
| # 15. Remote Push Button Stations | 15.1 These shall be used for remote OFF for motors, away from MCC. These shall be suitable for surface/structure mounting in Cast Aluminum housing having IP-55 class of protection i.e. completely weather proof. For dairy's process area and powder plant SS- 304 push button shall be used. Final finish of housing to be buffer mirror for SS and powder coated gray for Aluminum housing. Sample to be got approved before supply. Riveted type bi-color plastic nameplate to be provided for each feeder. For outdoor installation suitable canopy to be provided. |
| # 16. Erection Of Equipments | 16.1 The cases containing the equipment (being supplied by the purchaser shall be handed over to the Bidder/Supplier. The Bidder/Supplier shall make his own arrangements for safe transportation of all the items to the erection site and also carry out complete loading/unloading during transportation. Equipment shall not be removed from packing cases unless the floor has been made ready for installing them. The cases shall be opened in presence of the Engineer-in-charge or his authorized representative. These empty packing cases shall be returned to the storage space identified by engineer in charge and any document if found with the equipment shall be handed over to the Engineer-in- charge. Any damage or shortage noticed shall be reported to the Engineer-in-charge in writing immediately after opening of packing cases. |

| # 17. Power Control Centres, Distribution Boards, Control Panels & Bus Ducts | 17.1 Erection: The manufacturers shall deliver electrical panels and bus duct in convenient shipping section. The Bidder/Supplier shall be responsible for final assembly and inter-connection of bus bars/wiring. The Bidder/Supplier shall grout foundation channel in the flooring. Switchgears shall be aligned and leveled on their base channels and bolted or tack welded to them as per the instructions of the Engineer-in-charge. The earth bus shall be made continuous throughout the length. Loosely supplied relays and instruments shall be mounted and connected on the switchgears. The contacts of the draw out circuit breakers shall be checked for proper alignment and inter-changeability. 17.2 After erection the switchboard shall be inspected for dust and vermin proofness. Any hole, which might allow dust or vermin etc. to enter the panel, shall be plugged suitably at no extra cost. 17.3 If the instrument transformers are supplied separately they shall be erected as per the direction of the Engineer-in-charge. The Bidder/Supplier shall fix the cable glands after drilling the bottom top plates of all switchboards with suitable holes at no extra cost. 17.4 Range of overload relays/timers etc. shall be checked with requirement of motor/systems actually to be connected at site and if the same is under-sized/oversized, it shall be brought to the notice of Engineer-in-charge, who shall arrange procurement of correct rated components. However, the Bidder/Supplier shall not charge anything extra for labor for such replacements. 17.5 The bus duct shall be suitably supported between switchgear and transformer. The opening in the wall where the duct enters the switchgear room shall be sealed to avoid rainwater entry. The foundation of the switchgear shall be raised suitably for minor adjustment to ensure proper alignment and connection of the bus duct at no extra cost. Expansion joints, flexible connection, etc. supplied by the manufacturer of the bus duct shall be properly connected. 17.6 Testing: Before electrical panel is energized, the insulation resistance of each bus shall be measured from phase to ground. Measurement shall be repeated with circuit breakers in operating positions and contact open. Before switchgear is energized, the insulation resistance of all DC control circuits shall be measured from line to ground. Tests shall be performed on all circuit breakers during erection as per Table 2. 17.7 Contact alignment and wipe shall be checked and adjusted where necessary in accordance with the breaker manufacturer's instructions. Each circuit breaker shall be drawn out of its cubicle, closed manually and its insulation resistance measured from phase to phase and phase to ground. All adjustable direct acting trip devices shall be set using values given by the Engineer-in-charge / manufacturer. The dielectric strength of insulating oil wherever applicable shall be checked. Before switchgear is energized tests shall be performed on each circuit breaker in its test position as per Table. 17.8 Close and trip the circuit breaker from its local control switch, push button or operating handle. Switchgear control bus may be energized to permit test operation of circuit breaker with AC closing with prior permission of the Engineer-in-charge. 17.9 Carry out tripping test of the electrically operated circuit breaker by operating mechanical trip device. Test operation of circuit breakers latch, check carriage limit switch if provided. Test proper operation of lockout device in the closing circuit, wherever provided by simulating conditions that would causes a lockout to occur. Trip breaker either manually or by applying current or voltage to each of its associated protective relays. Before switchgear is energized, the test covered above shall be repeated with each breaker in its normal operating position. 17.10 Capacitor banks in capacitor control panel shall be tested as per manufacturer’s instructions. In addition, test for output and/or capacitance, insulation resistance test and test for efficiency of discharge device shall be carried out. 17.11 All electrical equipment alarms shall be tested for proper operation by causing alarms to sound under simulated abnormal conditions. 17.12 The Bidder/Supplier shall arrange testing and calibrations of relays. The testing equipment including primary and secondary injection sets (if required) etc shall also have to be arranged by the Bidder/Supplier. Payment for above work shall be deemed to have been included in the erection of switch boards/ control panels. |
| --- | --- |
| # 18. Sealed Maintenance Free Batteries & Battery Charger | 18.1 Batteries shall be erected on stands and insulators supplied by the manufacturer of the batteries. Interconnections shall be made with leads supplied by the manufacturer. Filling of electrolyte (supplied by the manufacturers), charging, discharging and recharging shall be carried out under the supervision of the Engineer-in-charge or his authorized representative. The Bidder/Supplier under the supervision of the Engineer-in-charge or his authorized representative will carry out erection of battery charger and DC board. The Bidder/Supplier shall also offer such facilities as may be required for carrying out tests on the complete battery charger and DC board/AC board. 18.2 Battery charger shall be tested for proper operation and to verify the charger delivers its maximum rated output. The Bidder/Supplier shall supply skilled/unskilled labor for carrying out the test by the engineer-in-charge. Batteries shall be given a boost charge in accordance with the manufacturer's instructions and adjusted for float operation before being placed for regular service. |
| # 19. Erection and Testing of Motors | 19.1 Erection and coupling of motors with machines will be done under the mechanical erection. However, earthing, cable termination, testing and commissioning are covered under this section. Before starting, the alignment and coupling of motors with machines and the insulation resistance of the motors will be measured and recorded by the Bidder/Supplier. The direction of the rotation of the motor shall also be checked before the driven equipment is finally coupled. Motor bearings are to be checked and rectified including supply and changing of grease if required, checking of fans coupling with bodies etc. The Bidder/Supplier shall take adequate precaution and care while executing the work. For all damage due to negligence etc. the Bidder/Supplier shall be responsible to replace/repair at his own cost. 19.2 Before connecting power cables to motors the insulation resistance of all motor windings shall be measured. Measurement shall be repeated after power cable terminations are completed and before first charging. 19.3 Motors shall be operationally tested together with the starting gear and auxiliary apparatus such as push button stations, the contractors, level and pressure controls, signal and alarm apparatus, power and control circuits etc. 19.4 Check the anti-condensation heater and its circuit (if installed). 19.5 Check the setting of the thermal overload protection / single phase prevent or. Testing of these devices is to be done wherever required as per the instructions of the Engineer-in-charge? 19.6 Run all motors uncoupled for a maximum period of 4 hours before the driven equipment is placed in regular service. Fill up Test Certificate as per Table 3. 19.7 All outdoor-installed motors must be shrouded with cover made out of 14 gauge GI sheet with lifting hook and louvers as approved by DDC, Nepal. |

| # 20.Installation of Cable Network | 20.1 Cable network shall include power, control and lighting cables which shall be laid in underground trenches, home pipes, open trenches, cable trays, GI pipes, or on building structure surfaces as detailed in the relevant drawings, cable schedules or as per the Engineer-in-charge's instructions. Supply and installation of cable trays, GI pipes/ conduits, cable gland sockets at both ends, isolators, junction boxes, remote push buttons stations, etc shall be under the scope of the Bidder/Supplier. For selection of cable size please refer to Table 5. |
| --- | --- |
| # 21. General Requirements for Handling of Cables | 21.1 Before laying cables, these shall be tested for physical damage, continuity absence of cross phasing, insulation resistance to earth and between conductors. Insulation resistance tests shall be carried out with 500/1000 volt Megger. 21.2 The cables shall be supplied at site, wound on wooden drum as far as possible. For smaller length and sizes, cables in properly coiled form can be accepted. The cables shall lie by mounting the drum of the cable on drum carriage. Where the carriage is not available, the drum shall be mounted on a properly supported axle, and the cable laid out from the top of the drum. In no case the cable will be rolled on, as it produces kinks, which may damage the conductor. 21.3 Sharp bending and kinking of cables shall be avoided. The bending radius for PVC insulated and sheath armored cable shall not be less than 10 D Where `D' is overall diameter of the cable. 21.4 While drawing cables through GI pipes, conduits, RCC pipe, ensure that size of pipe is such that, after drawing cables, 40 % area is free. After drawing cable, the end of pipe shall be sealed with cotton/bituminous compound. 21.5 High voltage (11 kV and above), medium voltage (230 V and above) and other control cables shall be separated from each other by adequate spacing or running through independent pipes/trays. 21.6 Armored cables shall never be concealed in walls/floors/roads without GI pipes, conduits RCC pipes. 21.7 Joints in the cable throughout its length of lying shall be avoided as far as possible and if unavoidable, prior approval of site engineer shall be taken. If allowed, proper straight through epoxy resin type joint shall be made, without any additional cost. 21.8 A minimum loop of 3 M shall be provided on both ends of the cable, or after every 50 M of uncounted length of cable and on both ends of straight through cable joint. This additional length shall be used for fresh termination in future. Cable for this loop shall be paid for supply and lying. 21.9 Cable shall be neatly arranged in the trenches/trays in such a manner so that crises crossing are avoided and final take off to the motor/switchgear is facilitated. Arrangement of cables within the trenches/trays shall be the responsibility of the Bidder/Supplier. 21.10 All cable routes shall be carefully measured and cable cut to the required lengths and undue wastage of cables to be avoided. The routes indicated in the drawings are indicative only and the same may be rechecked with the Engineer-in-charge before cutting of cables. While selecting cable routes, interference with structures, foundations, pipeline, future expansion of buildings, etc. should be avoided. 21.11 All temporary ends of cables must be protected against dirt and moisture to prevent damage to the insulation. For this purpose, ends of all PVC insulated cables shall be taped with an approved PVC or rubber insulating tape. Use of friction type or other fabric type tape is not permitted. Lead sheathed cables shall be plumbed with lead alloy. 21.12 Wherever cable rises from underground/concrete trenches to motors/switchgears/push buttons, these shall be taken in G.I./MS pipes of suitable size, for mechanical protection unto 300 mm distance of concerned cable gland or as instructed by the Engineer-in-charge. 21.13 Where cables pass through foundation/walls of other underground structures, the necessary ducts or openings will be provided in advance for the same. However, should it become necessary to cut holes in existing foundations or structures of the electrical. Bidder/Supplier shall determine their location and obtain approval of the Engineer-in-charge before cutting is done. |
| # 22. Laying of Cables (Underground System) | 22.1 Cables shall be so laid in ground that these will not interfere with other underground structures. All water pipes, sewage lines or other structures, which become exposed by excavation, shall be properly supported and protection from injury until the filling has been rammed solidly in places under and around them. Any telephone or other cables coming in the way are to be properly shielded diverted as directed by the Owner. 22.2 Cables shall be laid at minimum depth of 750 mm in case of LT & 1200 mm in case of HT, from ground level. Excavation will be generally in ordinary alluvial soil. The width of the trench shall be sufficient for lying of required number of cables. 22.3 Sand bedding 75 mm thick shall be made below and above the cables. A layer of bricks (full size) shall be laid on the edge, above sand bedding on the sides of cables and a flat brick to cover cable completely. More than one cable can be laid in the same trench by providing a brick on edge between two cables. However the relating location of cables in trench shall be maintained till termination. The surface of the ground after back filling the earth shall be made good so as to conform in all respects to the surrounded ground and to the entire satisfaction to the Engineer-in-charge. 22.4 For all underground cables, route markers should be used 22.5 Separate cable route markers should be used for LT, HT and telephone cables. 22.6 Route markers should be grounded in ground with 1:2:4 cement concrete pedestal size 230 x 230 x 300 mm. 22.7 Cable markers should be installed at an interval not exceeding 50 M along the straight routes of cables at a distance of 0.5 M away from centre of cable with the arrow marked on the cable markers plate indicating the location of cable. Cable markers should also be used to identify change in direction of cable route and for location of every joint in underground cable. 22.8 RCC Hume pipe for crossing road in cable laying shall be provided by Owner. No deduction shall be made for cable lying in home pipe for not providing bricks, sand and excavation. RCC home pipe at the ends shall be sealed by bituminous compound after laying and testing of cable by electrical Bidder/Supplier without any extra charge. |
| # 23. Laying of Cables under Floors | 23.1 GI class a pipe shall be used for lying of outgoing cables under floors from distribution boards to motors, isolators/junction boxes of motors, starter of motors and push button stations. Preferably one cable shall be drawn through one pipe. Size of pipe shall be such that after drawing of cable 40 % area is free. If length of pipe is more than 30 M, free area may be increased to 50 %. 23.2 Use of elbows is not allowed at all and number of bends shall be kept minimum. Instead of using bends with sockets, pipe-bending machine shall be used for making long smooth bends at site. 23.3 Ends of pipe shall be sealed temporarily while laying with cotton/ jute/ rubber stopper etc to avoid entry of building material. 23.4 Exact location of equipment motor/ isolator/ push buttons etc shall be ascertained prior to lying of pipe. |
| # 24. Laying of Cable in Masonry Trenches | 24.1 Masonry/ concrete trenches for lying of cable shall be provided by Owner. However steel members such as MS angles/ flats etc shall be provided & grouted by electrical Bidder/Supplier to support the cables without any extra charge. Cables shall be clamped to these supports with Aluminum saddles/ clamps. More than one tier of cables can be provided in the same trench if the number of cables is more. If required cable trays can also be provided in trenches. 24.2 Entry of cables in trenches shall be sealed with bituminous MASTIC compound to stop entry of water in trenches. |
| # 25. Laying of Cables in Cable Trays | 25.1 Cable trays and supporting steel members such as MS angle/ channel/ flats etc shall be provided and fixed by the Bidder/Supplier. 25.2 Cables shall be fixed in cable trays in single tier formation and cables shall be clamped with Aluminum flat clamps and galvanized bolts/unit. 25.3 Earthing flat/ wire can also be laid in cable tray along with cables. 25.4 After lying of cables minimum 20 % area shall be spare. |
| # 26. Laying of Cables on Builing Surface/ Structure | 26.1 Such type of cable lying shall be avoided as far as possible and will be allowed only for individual cables or small group of cables, which run along structure. 26.2 Cables shall be rigidly supported on structural steel/masonry using individual cast/malleable iron galvanized saddles and these supports shall be approximately 400 to 500 mm for cables unto 25 mm overall diameter and maximum 1000 mm for cables larger than 25 mm. Unsightly sagging of cables shall be revenged. Only/GI clamps with GI bolts/nuts shall be used. 26.3 If drilling of steel structure must be resorted to, approval must be secured from the Engineer-in-charge and steel must be drilled where the minimum weakening of the structure will result. |
| # 27. # Termination & Jointing of Cables | 27.1 Use of Glands: All PVC cable unto 1.1 kV grade, armored or Unarmored shall be terminated at the equipment/junction box/ isolators/push buttons/control accessories, etc. by means of suitable size single/double compression type cable glands. Armor of cable shall be connected to earth point. The Bidder/Supplier shall drill holes for fixing glands wherever necessary. Wherever threaded cable gland is to be screwed into threaded opening of different size, suitable galvanized threaded reducing bushing shall be used for approved type. 27.2 In case of termination of cables at the bottom of the panel over a cable trench having no access from the bottom, close fit holes should be drilled in the bottom plate for all the cables in one line, then bottom plate should be split in two parts along the centre line of holes. After installation of bottom plate and cables with glands, it shall be sealed with cold sealing compound. 27.3 Use of Lugs/ Sockets: All cable leads shall be terminated at the equipment terminals, by means of crimped type solder less connectors unless the terminals at the equipment ends are suitable for direct connecting without lugs/sockets. 27.4 The following is the recommended procedure for crimped joints and the same shall be followed: - Strip off the insulation of the cable end with every precaution, not to severe or damage any strand. All insulation to be removed from the stripped portion of the conductor and ends of the insulation should be clean and square. - The cable should be kept clean as far as possible before assembling it with the terminal/socket. For preventing the ingress of moisture and possibility of re-oxidation after crimping of the aluminum conductors, the socket should be fitted with corrosion inhibiting compound. This compound should also be applied over the stripped portion of the conductor and the palm surface of socket. - Correct size and type of socket/ ferrule/ lug should be selected depending on size of conductor and type of connection to be made. Make the crimped joint by suitable crimping tool. If after crimping the conductor in socket/ lug, some portion of the conductor remains without insulation the same should be covered sufficiently with PVC tape. |
| # 28. Dressing of Cable inside the Equipment | 28.1 After fixing of cable glands, the individual cores of cable shall be dressed and taken along the cableways (if provided) or shall be fixed to the panels with polyethylene straps. Cable shall be dressed in such a manner that small loop of each core is available inside the panel.28.2 For motors of 20 HP and above, terminal box if found not suitable for proper dressing of Aluminum cables, the Bidder/Supplier shall modify the same without any additional cost. Cables inside the equipment shall be measured and paid for. |
| # 29. # Identification of Cables/ Wires/ Cores | 29.1 Power cables shall be identified with red, yellow & blue PVC tapes for trip circuits identification, additional red ferrules shall be used only in the particular cores of control cable at the termination points in the switchgear/control panels and control switches. 29.2 In case of control cables all cores shall be identified at both ends by their wire numbers by means of PVC ferrules or self-sticking cable markers, wire numbers shall be as per schematic/connection drawing. For power circuit also wire numbers shall be provided if required as per the drawings of switchgear manufacturer. |
| # 30. Cable between Isolators/ Junction box & Motors/ Controls | 30.1 Wherever possible Copper cables with glands shall be used between isolator/junction box (installed near motor/controls) and motors/controls. If terminal box of the motor or control switch is not suitable for accepting armored cable or it is difficult to lay, copper conductor, multi-core, Unarmored flexible cable in PVC flexible conduit steel (reinforced) with flexible conduit glands shall be used. |
| # 31. Testing of Cables | 31.1 Before energizing, the insulation resistance of every circuit shall be measured from phase to phase and from phase to ground. This requires 3 measurements if one side is grounded and 6 measurements for 3 phase circuits. 31.2 Where splices or terminations are required in circuits rated above 650 volts, measure insulation resistance of each length of cable before splicing and/or terminating. Report measurements after splices and/or terminations are complete. 31.3 DC High Voltage test shall be made after installation on all 1100 Volts grade cables in which straight through joints have been made and all cables above 1100 V grade. 31.4 For record purposes test data shall include the measured values of leakage current versus time. The DC High Voltage test shall be performed as detailed below: 31.5 Cables shall be installed in final position with the entire straight through joints complete. Terminations shall be kept unfinished so that motors, switchgear, transformer etc are not subjected to test voltage. 31.6 The test voltage and duration shall be as per relevant codes and practices of ISO/bidders respective national standard or equivalent standard . Fill up the Test Certificate as per Table 4. |
| # 32. Earthing Network | 32.1 The entire earthing installation shall be done in accordance with the earthing drawings, specification and instructions of the Engineer-in-charge. The entire earthing system shall fully comply with the Indian Electricity Act and Rules framed there under. The Bidder/Supplier shall carry out any changes desired by the electrical inspector or the Owner in order to make the installation conform to the Rules, at no extra cost. The exact location of the earth pits, earth electrode and conductors and earthing points of the equipments shall be determined at site, in consultation with the Engineer-in-charge. Any change in the methods, routing, size of conductor etc. shall be subject to approval of the owner/engineer-in-charge before execution. |
| # 33. Earth Pit with Electrode | 33.1 Plate or pipe type earth electrode with earth pit shall be provided for this work unless otherwise advised by the Engineer-in-charge due to typical site conditions. Earthing electrode and pit shall be as per code of practices for Earthing. All earth electrodes shall preferably be driven to a sufficient depth to reach permanent moist soil. 33.2 Prior approval of the engineer-in-charge shall be taken for selecting type of earth electrode (pipe or plate). 33.3 Earth pit centre shall be at a minimum distance of 2 m from nearest building, unless otherwise advised. The minimum 3 m distance shall be maintained between centers of 2 earth pits. |
| # 34. Earth Bus, Earthing Lead & Earth Wire/ Strip | 34.1 All electrical equipment is to be doubly earthed by connecting two-earth strip/ wire conductor from the frame of the equipment to an earthing pit/ main earthing ring. The earthing ring will be connected via links to several earth electrodes. The cable armored will be earthed through the cable glands. Conductor size for connection to various equipments shall be as specified in the drawing or as instructed by the Engineer-in-charge. However, the length of the branch leads from equipment to earthing grid/ ring shall not be more than 10 to 15 meters. 34.2 All hardware for earthing installation shall be hot dip galvanized. Spring washers shall be used for all earthing connections of equipment having vibrations. 34.3 Size of earthing lead/ wire shall be as specified in schedule of quantities/ drawings. Table 6 may be considered as general guidelines. 34.4 When earthing wire is to be drawn under floor/in underground, Aluminum wire 10 mm dial. With PVC insulation shall be used. Instead of GI wire, PVC insulated copper conductor wires can also be used. 34.5 However, while deciding type & size of earth lead, the resistance between the earthing system and the general mass of the earth shall be as per code of practice. The earth loop impedance to any point in the electrical system shall not be in excess of 1.0 ohms in order to ensure satisfactory operation of protective devices. 34.6 G.I. wire/ Aluminum wire shall be connected to the equipment by providing crimping type socket/ lug. 34.7 Wherever earthing strip to be provided in cable tray, it shall be suitably bolted on cable tray and electrically bonded to the cable tray at regular interval. 34.8 Excavating & refilling of earth, necessary for laying underground earth bus loops shall be the responsibility of the Bidder/Supplier. 34.9 Wherever earth leads/ strips/ wire are laid in cable trenches, these shall be firmly and suitably cleared to the walls/ supporting steel structure on which cable is clamped. 34.10 The neutral of the transformer shall be connected to earth pit independently and earth pit shall have copper earth plate. 34.11 Long runs of GI strip shall be connected at each end with lap type welding to ensure continuity. |
| # 35. Two/Four Pole Structure | 35.1 ISMB 200 x 100 mm to be grounded in concrete 1:2:4 for at least 1/5th length i.e. 2 meters size of concrete pedestal 500 x 500 mm. All necessary civil works such as excavation, centering, concreting and back filling is included in Bidder/Supplier's scope of work. 35.2 Interconnecting by Aluminum conductor jumpers with connectors/ PG clamps etc. 35.3 Installation, testing and commissioning of complete two/four pole structure including ISMB & cross channels, G.O. switch, insulators and other items mentioned under equipment supply for two-pole structure. - Complete structure to be provided with two coats of Aluminum paint. |

| # 36. Erection Procedure Guidelines for Instrumentation & Control System | 36.1 The erection of Instrumentation & Control System shall be carried out generally conforming to General Technical Standards as described herein. However, the Bidder shall select and adopt methods and procedures for equipment erection to suit the nature of equipment and erection work, involved according to the best modern practice and his own experience. 36.2 Shop tests as well as Site tests shall be performed to ensure that all equipment / sub-systems / systems furnished are manufactured and tested conforming to the requirements of the specification and approved Quality Assurance Program. 36.3 All assembly and erection procedures adopted by the supplier shall be open for inspection and approval by the Client. Acceptance of erection procedures shall not in any way relieve the supplier of his responsibility for proper erection of the equipment. 36.4 Transmitters, converters and pressure & temperature switches shall generally be installed on Instrument Stands made of 2” SS pipes located at convenient points. Level transmitters shall normally be flanged for direct mounting in the tank / equipment. 36.5 Temperature / Pressure Stub on equipment and pipelines shall preferably be of same material or higher grade of material 36.6 Suitable Root Valves shall be provided with every tap-off point. 36.7 Installation of Pressure and Differential Pressure Transmitter shall be as per standard engineering practice incorporating Drain Valves, Isolation Valves, 2/3-Valve Manifold, Syphon etc. as applicable. 36.8 For instrument air, SS. Pipe shall be used for air distribution from Battery Limit to the designated point of use. Take-off connections to instruments / actuators shall be with suitable size nipples and shut-off valves. Individual air supply shall be provided by 6 mm OD PU tube through an isolating needle valve and air filter regulator. 36.9 Perforated Aluminum Trays (minimum 2 mm thick) shall be utilized for routing of signal tubing / cables in field. All cables / tubes in the supporting trays / channels shall be tagged properly. The loading of the cable trays shall not exceed 60 % of the available space. Proper gap between the electrical trays, as per the voltage level, shall be maintained in the cable tray layout. Tray numbers shall be provided at suitable intervals. 36.10 Rigid and flexible conduits along with necessary fittings shall be used for cable laying from instrument to JB or instrument to trays etc. |
| --- | --- |

| Table 1 ISO/bidders respective national standard or equivalent standard |  |  |
| --- | --- | --- |
| SN | Description |  |
| 1 | PVC insulated cables (light duty) for working voltage unto 1100 volts |  |
| 2 | PVC insulated cables (heavy duty) for voltage unto 1100 volts |  |
| 3 | -- Do -- for voltage 3.3 kV to 11 kV |  |
| 4 | Specification for polyethylene insulated PVC sheathed heavy duty electric cables, voltage not exceeding 1100 V |  |
| 5 | -- Do -- voltage 3.3 kV to 11 kV |  |
| 6 | Guide for marking of insulated conductors |  |
| 7 | Code of practice for installation and maintenance of paper insulated power cables |  |
| 8 | Code of practice for earthing |  |
| 9 | Guide for safety procedures and practices in electrical work |  |
| 10 | Code of practice for installation and maintenance of AC induction motor starters |  |
| 11 | Code of practice for installation and maintenance of induction motors |  |
| 12 | Code of practice for installation and maintenance of switchgears |  |
| 13 | Code of practice for installation and maintenance of transformers |  |
| 14 | Code of practice for electrical wiring installation, voltage not exceeding 650 V |  |
| 15 | Code of practice for electrical wiring installation (system voltage exceeding 650V) |  |
| 16 | Guide for testing three phase induction motor |  |

| Table 2 Pro forma for PCC, DB, Motor Control Centres Test |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN |  |  | Test |  |  |  |  | Report |  |
| 1 |  |  | Circuit (Breaker/Bidder/Supplier Module Designation/Bus Number) |  |  |  |  |  |  |
| 2 |  |  | Insulation resistance (Contacts open, breaker Racked in position) |  |  |  |  |  |  |
| a. |  |  | Between each Phase & Bus (Mega Ohm) |  |  |  |  |  |  |
| b. |  |  | Between each phase and earth (Mega Ohm) |  |  |  |  |  |  |
| c. |  |  | DC and AC control & auxiliary circuits (Mega Ohm) |  |  |  |  |  |  |
| d. |  |  | Between each phase of CT/PT and between CT & PT circuit if any (Mega Ohm) |  |  |  |  |  |  |
| 3 |  |  | CT Checks |  |  |  |  |  |  |
| a. |  |  | CT ratio |  |  |  |  |  |  |
| b. |  |  | CT secondary resistance |  |  |  |  |  |  |
| c. |  |  | CT polarity check |  |  |  |  |  |  |
| 4 |  |  | Check for contact alignment and wipe |  |  |  |  |  |  |
| 5 |  |  | Check/test all releases/ relays |  |  |  |  |  |  |
| 6 |  |  | Check mechanical interlocks |  |  |  |  |  |  |
| 7 |  |  | Check electrical interlocks |  |  |  |  |  |  |
| 8 |  |  | Check switchgear/control panel wiring |  |  |  |  |  |  |
| 9 |  | Checking breaker/Bidder/Supplier circuits for |  |  |  |  |  |  |  |
| a. |  | Closing- local and remote (wherever applicable) |  |  |  |  |  |  |  |
| b. |  | Tripping-local and remote (wherever applicable) |  |  |  |  |  |  |  |
| 10 |  | Opening time of breaker/ contactor |  |  |  |  |  |  |  |
| 11 |  | Closing time of breaker/ contactor |  |  |  |  |  |  |  |
| Signature and seal of Engineer-in-charge of DDC, Nepal |  |  |  | Signature and seal of Engineer-in-charge of Bidder/Supplier |  |  |  |  |  |
|  | Table 3 Pro forma for motor testing |  |  |  |  |  |  |  |  |
|  | SN | Test |  |  |  | Report |  |  |  |
|  | 1 | Name plate details |  |  |  |  |  |  |  |
|  | A | Voltage |  |  |  |  |  |  |  |
|  | B | HP / KW |  |  |  |  |  |  |  |
|  | C | Mounting |  |  |  |  |  |  |  |
|  | D | Current |  |  |  |  |  |  |  |
|  | E | RPM |  |  |  |  |  |  |  |
|  | F | Frame size |  |  |  |  |  |  |  |
|  | G | Make |  |  |  |  |  |  |  |
|  | H | Sr No |  |  |  |  |  |  |  |
|  | I | Others |  |  |  |  |  |  |  |
|  | 2 | Insulation test (before cable connection) |  |  |  |  |  |  |  |
|  | A | Between Phase and Earth (Mega Ohms) |  |  |  |  |  |  |  |
|  | B | Between each Phase (Mega Ohms) |  |  |  |  |  |  |  |
|  | 3 | Insulation test (after cable connection) |  |  |  |  |  |  |  |
|  | A | Between Phase and Earth (Mega Ohms) |  |  |  |  |  |  |  |
|  | B | Between each Phase (Mega Ohms) |  |  |  |  |  |  |  |
|  | 4 | No load current |  |  |  |  |  |  |  |
|  | A | R Phase Amps |  |  |  |  |  |  |  |
|  | B | Y Phase Amps |  |  |  |  |  |  |  |
|  | C | B Phase Amps |  |  |  |  |  |  |  |
|  | 5 | Full load current |  |  |  |  |  |  |  |
|  | A | R Phase Amps |  |  |  |  |  |  |  |
|  | B | Y Phase Amps |  |  |  |  |  |  |  |
|  | C | B Phase Amps |  |  |  |  |  |  |  |
|  | 6 | Temperature rise after 4 hours run |  |  |  |  |  |  |  |
|  | A | On no load degree C |  |  |  |  |  |  |  |
|  | B | On full load degree C |  |  |  |  |  |  |  |
|  | C | Ambient temperature during test degree C |  |  |  |  |  |  |  |
|  | 7 | Operation of thermal overload relay |  |  |  |  |  |  |  |
|  | A | At normal Full Load current of motor |  |  |  |  |  |  |  |
|  | B | At twice Full Load current of motor trips in seconds |  |  |  |  |  |  |  |
|  | Signature and seal of Engineer-in-charge of DDC, Nepal |  |  |  | Signature and seal of Engineer in-charge of Bidder/Supplier |  |  |  |  |

| Table 4 Pro forma for Testing Cables |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr | Test |  |  | Report |  |  |  |
| 1 | Date of Test |  |  |  |  |  |  |
| 2 | Drum Number (from which cable is taken) |  |  |  |  |  |  |
| 3 | Cable From -> To |  |  |  |  |  |  |
| 4 | Length of run of this cable (meter) |  |  |  |  |  |  |
| 5 | Insulation resistance test (In Mega Ohm) |  |  |  |  |  |  |
| A | Voltage of Megger Volts |  |  |  |  |  |  |
| B | Between core-1 to earth |  |  |  |  |  |  |
| C | Between core-2 to earth |  |  |  |  |  |  |
| D | Between core-3 to earth |  |  |  |  |  |  |
| E | Between core-1 to core-2 |  |  |  |  |  |  |
| F | Between Core-2 to Core-3 |  |  |  |  |  |  |
| G | Between Core-3 to Core-1 |  |  |  |  |  |  |
| 6 | High Voltage Test (Voltage Duration) |  |  |  |  |  |  |
| A | Between Cores and Earth |  |  |  |  |  |  |
| B | Between Individual Cores |  |  |  |  |  |  |
| Signature and seal of Engineer-in-charge of DDC, Nepal |  |  |  | Signature and seal of Engineer-in-charge of Bidder/Supplier |  |  |  |
| Table 5 Recommended Cables Sizes For Industrial Wiring |  |  |  |  |  |  |  |
| 3 Ø 415 V Motor HP |  | Aluminium Conductor Cable Size (in mm2) |  |  |  |  |  |
|  |  | Rotor Resistance Starter |  |  | Star Delta Starter |  |  |
|  |  | Supply side | Motor Side (2 Cables) |  | Supply side | Motor Side (2 Cables) |  |
| 10 |  | 6 | 6 |  | 6 | 4 |  |
| 15 |  | 10 | 10 |  | 10 | 4 |  |
| 20 |  | 16 | 16 |  | 16 | 6 |  |
| 25, 30 |  | 25 | 25 |  | 25 | 10 |  |
| 40 |  | 35 | 35 |  | 35 | 16 |  |
| 50 |  | 50 | 50 |  | 50 | 25 |  |
| 60 |  | 70 | 70 |  | 70 | 35 |  |
| 75 |  | 95 | 95 |  | 95 | 50 |  |
| 100 |  | 120 | 120 |  | 120 | 70 |  |
| 125 |  | 150 | 150 |  | 150 | 95 |  |
| 150 |  | 225 | 225 |  | 225 | 120 |  |
| 180 |  | 300 | 300 |  | 300 | 150 |  |
| 215 |  | 300 | 300 |  | 300 | 185 |  |
| For DOL Starter up to 10 HP Motor, 4 mm2 cables should be used. |  |  |  |  |  |  |  |

| Table 6 Sizing of Earthling Lead/ Wire |  |  |
| --- | --- | --- |
| Sr No | ITEM | Size |
| 1 | Control switches | G.I. wire 14 SWG |
| 2 | Motor unto 10 HP | G.I. wire 8 SWG |
| 3 | Motor above 10 HP unto 125 HP | G.I. strip 25 x 3 mm |
| 4 | Motor above 125 HP | G.I. strip 25 x 6 mm |
| 5 | Switch Board | G.I. strip 25 x 6 mm |
| 6 | Power control centre/ LT panel of sub-station | G.I. strip 40 x 6 mm |

Sub – Section 5

##### Tools, manuals &catalogues

1. Tools

1.1 The bidder/supplier/manufacturer should supply specials tools/lifter for assembling, dismantling and repair for all the supplied major equipments. A list of tools should be attached along with the tender.

1.1.1 The bidder/supplier/manufacturer should also supply one set of electrical and mechanical tools set. A list of tools should be attached along with the tender.

2. manuals & catalogues

2.1 The bidder/supplier/manufacturer should provide complete two sets of manuals, catalogues and spare parts list of all the supplied equipments and accessories in a complied form during handover of the plant.

Section 8 – Contract of Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Table of Forms

Letter of Intent	8-177

Letter of Acceptance	8-178

Contract Agreement	8-179

Performance Security	8-180

Advance Payment Security	8-181

Letter of Intent

Notes on Letter of Intent

Notice will be published in the National news paper.

Letter of Acceptance

[on letterhead paper of the Employer]

. . . . . . . date. . . . . . .

To:	. . . . . . . . . .   name and address of the Contractor . . . . . . . . . .

Subject:	. . . . . . . . . .   Notification of Award

This is to notify that your Bid dated . . . . date . . . .  for execution of the . . . . . . . . . .name of the contract and identification number, as given in the Contract Data/SCC . . . . . . . . . . for the Contract price of  the equivalent of [iamount in figures and words in the currency…….………….], as corrected in accordance with the Instructions to Bidders is hereby accepted by our Agency..

You are hereby instructed to contract this office to sign the formal contract agreement within 15 days. As per the Conditions of Contract, you are also required to submit Performance Security, as specified in SCC, consisting of a Bank Guarantee in the format included in Section 9 (Contract Forms) of the Bidding Document.

The Employer shall forfeit the bid security, in case you fail to furnish the Performance Security and to sign the contract within specified period.

Authorized Signature:

Name and Title of Signatory:

Section 9 Contract Agreement

THIS AGREEMENT made the . . . . . .day of . . . . . . . . . . . . . . . . ., . . . . . . ., between . . . . . name of the Employer. . . . .. . . . . (Hereinafter “the Employer”), of the one part, and . . . . . name of the Contractor . . . . .(hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as . . . . . name of the Contract. . . . .should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement.

-	the Letter of Acceptance;

-	the Letter of Bid;

-	the Addenda Nos . . . . . insert addenda numbers if any. . . . .

-	the Special Conditions;

-	the General Conditions;

-	Bills of Quantities (BOQ);

-	the Specification;

-	the Drawings;

-	the completed Schedules; and

-	Any other document

3.	In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works  and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of . . . . . NEPAL. . . . .on the day, month and year indicated above.

On behalf of the Purchaser:		On behalf of the Supplier

Signature :		Signature :

Name :		Name :

Designation :		Designation :

Seal :		Seal :

Witness:	Witness

Signature :		Signature :

Name:	Name:

Address:	Address:

Date:	Date:

Performance Security

Bank’s Name and Address of Issuing Branch or Office

Beneficiary: 	Name and Address of Employer

Date:

Performance Guarantee No.:

We have been informed that . . . . . name of the Contractor. . . . .  (hereinafter called "the Contractor") has  entered into Contract No. . . . . . reference number of the Contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of Works. . . . .  (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we . . . . . name of the Bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) such sum being payable in Nepalese Rupees, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the . . . . . Day of . . . . . . . . . . , . . . . . .  **, and any demand for payment under it must be received by us at this office on or before that date.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . 
Seal of Bank and Signature(s)

Note:  All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

* The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Contract in Nepalese Rupees.

** Insert the date twenty-eight days after the end of Defect Notification Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee”.

Advance Payment Security

Bank’s Name, and Address of Issuing Branch or Office

Beneficiary: 	Name and Address of Employer

Date:

Advance Payment Guarantee No.:

We have been informed that . . . . . name of the Contractor. . . . .  (hereinafter called "the Contractor") has  entered into Contract No. . . . . . reference number of the Contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of Works. . . . .  (hereinafter called "the Contract").

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum  . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) is to be made against an advance payment guarantee.

At the request of the Contractor, we . . . . . name of the Bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number . . . . . Contractor’s account number. . . . .   at . . . . . name and address of the Bank. . . . .  .

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that eighty (80) percent of the Contract Price has been certified for payment, or on the . . . day of . . . . . . . , . . . . .**, whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . 
Seal of Bank and Signature(s)

Note:  All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

* The Guarantor shall insert an amount representing the amount of the advance payment in Nepalese Rupees of the advance payment as specified in the Contract.

** Insert the date Thirty days after the expected completion date. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee”.

Name of two buyers to whom similar equipment are supplied, installed and commissioned in the past five years of upgrading/establishment of  SMP Plant with Reverse Osmosis  and  dairy whitener.

11 Soft, Raw, Chilled and Glycol